## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact | Pioneer a model for simultaneously restoring oyster reef, seagrass meadow and saltmarshes to areas that have suffered population decline.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | At least three hecatres of oyster reef will be restored across the Solent. Benefits of the restored reef will be proven and demonstrated, and a replicable model of integrated ecosystem restoration will be produced to encourage further oyster restoration around the UK coast. | OC.0.1 | At least 3 ha of oyster reef is restored in the Solent [area of habitat restored, condition of habitat] | 1, 4 | 2.1.1, 1.4.2 | 1.4, 2.1
|  |  | OC.0.2 | Ecosystem services/wider benefits are quantified and/or valued and demonstrated [£ per service/L of water filtered/biodiversity value etc.] | 2, 3 | 2.4.1, 4.2.1, 4.2.2, 3.2.2, 4.3.1 | 2.4, 4.2, 3.2, 4.3
|  |  | OC.0.3 | Recommendations and guidance for oyster reef restoration around the UK is published [number of reports/supporting evidence provided for restoration of critical habitat]. | 5 | 2.4.1 | 2.4
[8 empty] | Action | July 2023 notes
|  |  | 1 | Phased restoration of native oyster reefs in the Solent is completed. |  |  |  | Remain in this logframe as barclays | Stay - have done two, working on extending one of these reefs. Scoping site in Chichester as part of ELP
|  |  | 2 | Benefits of restored oyster reefs demonstrate through a report and the production of a film. |  |  |  | Remain in this logframe as barclays | Film made already, Luke working on report. At end of Barclays no longer need to report against this
|  |  | 3 | Produce feasibility report for the potential for integrated saltmarsh, seagrass and oyster restoration |  |  |  | Move across to ELP - should match ELP logframe | Will be doing this as part of ELP, re-allocated original Barclays budget to do other things. Such as mapping work by consultant. Report not likely to be released for another 4 years
|  |  | 4 | Implement restoration of seagrass and saltmarsh close to oyster restoration sites. |  |  |  | Move across to ELP - should match ELP logframe | Part of ELP work, will be restoring these within the same harbours as oyster reefs
|  |  | 5 | Develop a report detailing lessons learned from this integrated approach, benefits from restoring the habitats simulatneously, and considering other target sites for the restoration approach to be applied. |  |  |  | Move across to ELP - should match ELP logframe | Part of ELP work,

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
5 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Phased restoration of native oyster reefs in the Solent is completed. | O.1.1 | Marine license is acquired [number of, for X number of activities, for X area] |  | Number of licences | NA - progress | [8 empty] | 1 | Marine Licence issued in July 2021 |  |  | 0 | Already achieved in July 2021.
|  |  | O.1.2 | Juvenile oysters are produced at hatchery [number of, condition] |  | Number of oysters produced at hatchery | NA - progress | [8 empty] | 0 |  |  |  | ? | spat on shell produced in hatchery during August 2022
|  |  | O.1.3 | Cultch that is suitable for oyster restoration is sourced [amount of cultch, condition of cultch] |  | NA | NA - progress | [8 empty] | 0 |  |  |  | 468 | Tons of cultch aquired for Hamble reef
|  |  | O.1.4 | X amount of cultch is layed across X area within X [number of] field visits to form suitable habitat for oyster (given in area) |  | Area (km2) | 2.1.1 |  |  |  |  | 0.01 |  |  |  | 0.001 | Laid in Sept 21, 361 m3 of cultch across 1000m2 |  |  | 0.0025 | Laid in April 2023, 388m3 over 2500m2
|  |  | O.1.5 | X number of oysters are 'reseeded' on top of cultch [success/survival rates of reseeding - maybe add details here about any planned monitoring of reseeded area, unless all covered in output below] |  | Number of oysters deployed | 2.2.1 | [8 empty] | 36000 | 15k: reseeded in Oct 21 21k: reseeded in Feb 22 |  |  | 19939 | Oyster deployment in April at Hamble Reef (15k) | 21000 | Oysters reseeded in feb 22
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on R7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray just spotted this 1000km3. is that right? Reply: Actually - I think I've just realised it should be 1000m3 buut let me know I've got this right and I'll change Reply: It should be 1,000km2 in size. 361m3 of cultch was laid.

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
5 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Benefits of restored oyster reefs demonstrate through a report and the production of a film. | O.2.1 | Growth and survival data/rates recorded [number of datasets produced; number of monitoring studies conducted] |  | Number of pieces of new evidence | 2.4.1 | [8 empty] | ? |  |  |  | 0 | Survey 1 - Aug 22: Fiona video surveys (Langstone) Survey 2 - Aug 22 -- Fiona grab sampling survey - Langstone Survey 3 - Sept 22 - Diver surveys (survival) - Langstone only Survey 4 - Mar 23 - grab surveys | 0 | Survey 1 - Aug 22: Fiona video surveys (Langstone) Survey 2 - Aug 22 -- Fiona grab sampling survey - Langstone Survey 3 - Sept 22 - Diver surveys (survival) - Langstone only Survey 4 - Mar 23 - grab surveys
|  |  | O.2.2 | Biodiversity recorded [number of datasets produced; number of monitoring studies conducted; number of species (invasive, common, commercially important, endangered or other conservation importance) |  | Number of pieces of new evidence | 2.4.1 |  |  |  |  | 0 | 120 surveys 60 samples |  |  | ? |  |  |  | 0 | 4 BRUV surveys in Langstone (June, July, Aug, Sept) - 22 2 BRUV surveys in Hamble (July & Sept) - 22 2 BRUV surveys in Feb 23 2 BRUV surveys in Aug 23 | 0 | 4 BRUV surveys in Langstone (June, July, Aug, Sept) - 22 2 BRUV surveys in Hamble (July & Sept) - 22 2 BRUV surveys in Feb 23 2 BRUV surveys in Aug 23
|  |  | O.2.3 | Unsure what 'development of oyster restoration' referred to - suggest including the main metrics that will be measured and number of reports produced (assuming it'll be 3 to cover the Barclays grant years) | [11 empty] | 0 | Not done in Y2 – needs at least a year post-deployment for monitoring results. Under PhD student. Might be released as an impact statement – high level public-facing document. Report to MMO annually for permit conditions. |  |  |  |  | 0 | 0
|  |  | O.2.4 | Film produced with X partners/collaborators that communicates the benefits of oyster restoration [reach; engagement; interactions; article/news features; shares...] |  | Number of films | 4.2.2 | [8 empty] | 0 | 1 film released on youtube July 2022 | 1 |  | 1 | 1 film released on Youtube July 2022 (this has been captured already in column R but in the wrong time frame) major press: BBC, HELLO!, Hampshire Live, https://www.bbc.co.uk/news/uk-england-hampshire-65404393 https://www.bbc.co.uk/news/uk-england-hampshire-63930408 https://www.hellomagazine.com/royalty/490062/princess-eugenie-reveals-why-motherhood-inspired-passion-project/ | 1 | 1 film released on Youtube July 2022 (this has been captured already in column R but in the wrong time frame) major press: BBC, HELLO!, Hampshire Live, https://www.bbc.co.uk/news/uk-england-hampshire-65404393 https://www.bbc.co.uk/news/uk-england-hampshire-63930408 https://www.hellomagazine.com/royalty/490062/princess-eugenie-reveals-why-motherhood-inspired-passion-project/
|  |  | O.2.5 | DO NOT COMPLETE - Reach of film |  | Number of film views | 4.2.1 | [8 empty] | 0 | 27 attendees of premier 147 views as of 21/07/22 ALL IN Y3 SO NUMBERS MOVED ACROSS |  |  | 607 | Youtube views 2,438 in Sept 23 = increase of 1771 from Nov 22 60 - L2M Sept 22 27 attendees - Premier in July 22 | 607 | Youtube views 2,438 in Sept 23 = increase of 1771 from Nov 22 60 - L2M Sept 22 27 attendees - Premier in July 22
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1
A.2.2

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
7 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Produce feasibility report for the potential for integrated saltmarsh, seagrass and oyster restoration | O.3.1 | X number of local stakeholders and X number of national experts are engaged with on an informal and/or formal partnership/advisory basis. |  | Number of stakeholders | 4.2.1 |  |  | 50 | 50: March 2021, brought together over 50 people to takl about inegrated restoration, led by ZSL and Blue Marine | 215 | 215: recorded in outreach spreadsheet 236: reached through outreach activities from outreach spreadsheet: https://bluemarinefoundation.sharepoint.com/:x:/s/Projects/Eb9bXM6qJ-FDl1XiqSfjmo4BhFTIugPY4hmpYSMPE9_NUw?e=awMG1g |  |  | 236 | 236: reached through outreach activities from outreach spreadsheet: https://bluemarinefoundation.sharepoint.com/:x:/s/Projects/Eb9bXM6qJ-FDl1XiqSfjmo4BhFTIugPY4hmpYSMPE9_NUw?e=awMG1g |  |  | 590 | 590: reached through outreach activities from outreach spreadsheet in Y3: https://bluemarinefoundation.sharepoint.com/:x:/s/Projects/Eb9bXM6qJ-FDl1XiqSfjmo4BhFTIugPY4hmpYSMPE9_NUw?e=awMG1g | 590 | 590: reached through outreach activities from outreach spreadsheet in Y3: https://bluemarinefoundation.sharepoint.com/:x:/s/Projects/Eb9bXM6qJ-FDl1XiqSfjmo4BhFTIugPY4hmpYSMPE9_NUw?e=awMG1g
|  |  | O.3.2 | stakeholder workshops are completed with diverse representation from scientific, technical and other sectors [number of attendees, number of workshops] |  | Number of outreach activities | 4.2.2 |  |  | 1 | 2021-03-01 | 18 | 9 outreach events (see spreadsheet linked above) 1 working group workshop in Mar 22 6 solent seascape working group 2 x solent seascape recovery plan workshops |  |  | 9 | 1: completed March 2022 – solent oyster restoration working group. 6: solent seascape workshops with stakeholders to determine best opportunities and next steps for integrated restoration. 2: Solent seascape recovery plan workshop |  |  | 4 | 1 - Social media workshop in October - 8 attendees 2- RansTrans workshop in Nov 22 - 50 attendees 3- Solent Seascape recovery workshop - this was done in July 2022 but covered in column R already 4 - ZSL led Seascape workshop - not specifically about Solent but Solent project used as case study during discussions to develop seascape approaches nationally. | 4
|  |  | O.3.3 | X number of suitable locations are identified for integrated restoration |  | Pieces of evidence to support restoration | NA - progress |  |  |  |  | 11 | 11 sites identified throughout Y2 | [6 empty] | 0
|  |  | O.3.4 | X methods are identified and developed [as in create our own method specifically for integrated restoration vs. standalone restoration of a single habitat?] for seargass and saltmarsh restoration that will also function alongside oyster restoration, supported by X number of scientific/industry experts. |  | NA | NA - progress |  |  |  |  | 0 | [7 empty] | 1 | ELP monitoring method developed for the SSP | 1 | ELP monitoring method developed for the SSP
|  |  | O.3.5 | Add in metrics being recorded that are of relevance to BLUE re. saltmarsh/oyster trial |  | ?
|  |  | O.3.6 | number of funding/advisory/other formal partnerships formed to support integrated restorationa ctivities. |  | Number of partnership organisations | 4.3.1 | [8 empty] | 10 | Solent seascape project, formally formed in Sept 21, 10 organisations |  |  | 0 | £3.6mil funding received in total ELP funding - Nov 22 GAF - 100K - Nov 22 SF - 35K - Sept Andy Woolmer natuve oyster supplier - Nov 22 Miel de Botton - 90k Sept 23
|  |  | O.3.7 | NEW JULY 2022 number of stakeholders actively participating |  | Number of stakeholders | 3.2.2 |  |  |  |  | 34 |  |  |  | 34 | Contacts in working group (Solent Oyster Restoration Working Group) – aim to meet quarterly. |  |  | 35 | SORP WG plus ELP project partners | 35 | SORP WG plus ELP project partners
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1
A.3.2
A.3.3
A.3.4
A.3.5
A.3.6
X number of local stakeholders and X number of national experts are engaged with on an informal and/or formal partnership/advisory basis. 4.2.1
X number of stakeholder workshops are completed with diverse representation from scientific, technical and other sectors [number of attendees, number of workshops] 4.2.2
X number of suitable locations are identified for integrated restoration 2.4.1
X methods are identified and developed [as in create our own method specifically for integrated restoration vs. standalone restoration of a single habitat?] for seargass and saltmarsh restoration that will also function alongside oyster restoration, supported by X number of scientific/industry experts. NA - progress
Add in metrics being recorded that are of relevance to BLUE re. saltmarsh/oyster trial
number of funding/advisory/other formal partnerships formed to support integrated restorationa ctivities. 4.3.1
NEW JULY 2022 number of stakeholders actively participating (3.2.2)
NEW JULY 2022 Number of new industry partnerships for cooperative ocean conservation (4.3.1)
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Were we also involved in the development of this? Reply: Yes sorry have updated
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray Were all of these done in 2022? Reply: Yes all in 2022 - the six workshops were because they were split in to habitat types and media. Reply: Ok great. Next year (not for this deadline) please could you add the months of each of these in? Reply: Ah sorry, for reference if you need it, it's 6 workshops held in Feb 2022 and the seascape recovery plan workshop was held in Aug 2022.
Note on V9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny MurrayThis one is specifically for the number of formal partnerships formed so I have moved the bit about the funding into the description cell. If there are any new organisations that have joined (we have 10 listed in Y2) then perhaps list those out here, if not, no action required from you Reply: No other formal partnerships as of yet other than ELP.

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Implement restoration of seagrass and saltmarsh close to oyster restoration sites. | O.4.1 | Marine license is acquired [number of, for X number of activities, for X area] |  |  | NA - progress | [8 empty] | NA |  |  |  | 0
|  |  | O.4.2 | CHANGED JULY 2022 area of marine and coastal habitat restored |  | km2 | 2.1.1 | [12 empty] | 0.0049 | 0.25 oyster reef - Hamble, 0.24 BUDS trial - Itchenor
|  |  | O.4.3 | X area identified for seagrass restoration, materials and equipment deployed. |  |  | NA - progress | [12 empty] | 0 | 2 new sites identified by Project Seagrass - Priory Bay and Thorness General areas identified for seagrass restoration sites by HIWWT - one at Calshot and Chilling, and two potential sites in the Hamble
|  |  | O.4.4 | NEW JULY 2022 number of beneficiares |  |  | 4.1.2 | [12 empty] | 0
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1
A.4.2
A.4.3

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Develop a report detailing lessons learned from this integrated approach, benefits from restoring the habitats simulatneously, and considering other target sites for the restoration approach to be applied. | O.5.1 | Include your chosen metrics relevant to monitoring of pilot areas (survival rates, biodiversity, water quality etc..)
|  |  | O.5.2 | Number of reports issued |  |  | 2.4.1
|  |  | O.5.3 | Report published that outlines results/recommendations for other areas that could benefit from restoration [record reach/engagement/distribution of report if relevant] |  |  | 2.4.1 | [12 empty] | 0 | MMO monitoring report - Nov 22 | 0 | MMO monitoring report - Nov 22
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on V6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this was there already - Louise and I don't think this is relevant, and want to remove but I didn't want to in case it caused problems Reply: That's fine - I'll remove the 0 so the detail is there but it's not getting counted

## Output 6 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
0 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
0 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
0 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
0 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
0 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Funding generated from ELP | 5000000 | GBP | 6.1.2 | [6 empty] | 5000000 | funding from ELP
U.2 | PhD students as monetary beneficiaries | 3 | Number of students | 4.1.1 | [8 empty] | 7 | 1 PhD started in October 2022, then the other two were in Sept 2020. We had 2 interns start in the hatchery in June 2021 (captured in Y2) and then three interns in April 2022 |  |  |  |  | 4
U.3 | Internships (non-monetary beneficiaries) | 2 | Number of interns | 4.1.2 |  |  |  |  | 2 | 2 x interns
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray could you please confirm the start month of these beneficiaries? Reply: 1 PhD started in October 2022, then the other two were in Sept 2020. We had 2 interns start in the hatchery in June 2021 and then three interns in April 2022 (sorry forgot to add those).

## Partners Funders
Outcome | Output | Partner | Funder
1 | O.1.1
O.1.2
O.1.3
O.1.4
O.1.5
2 | O.2.1
O.2.2
O.2.3
O.2.4
O.2.5
3 | O.3.1
O.3.2
O.3.3
O.3.4
O.3.5
O.3.6
O.3.7
4 | O.4.1
O.4.2
O.4.3
O.4.4
5 | O.5.1
O.5.2
O.5.3

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 5 | 9 | O.1 | O.1.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 5 | 9 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 7 | 11 |  | O.1.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 4 | 8 |  | O.1.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 3 | 7 |  | O.1.5 |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 0 | 4 | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 0 | 4 |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 0 | 4 |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 0 | 4 |  | O.2.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 0 | 4 |  | O.2.5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0.01 | 0.001 | 0.0074 | 0 | 0 | 0 | 0.0184 | 0 | 0.0184 | 0 | 0 | 0 | 0
|  |  |  | O.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.6 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 36000 | 19939 | 0 | 0 | 0 | 55939 | 0 | 55939 | 0 | 21000 | 21000 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 34 | 34 | 35 | 0 | 0 | 0 | 103 | 0 | 103 | 0 | 35 | 35 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7 | 7 | 0 | 4 | 0 | 4
[14 empty] | 4.1.2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 215 | 236 | 1197 | 0 | 0 | 0 | 1648 | 0 | 1648 | 0 | 1197 | 1197 | 0
[14 empty] | 4.2.2 | 18 | 9 | 5 | 0 | 0 | 0 | 32 | 0 | 32 | 0 | 5 | 5 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0