## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01 | Tash presentation at Severn Estuary Forum and sponsored evening wine reception (12th Oct) Significant effort invested in reaching out to location facilitators ahead of the November workshop, to bring them all together. i.e. disseminating reports, following up with them 1-1, online meetings, site visits etc
2021-11-01 | Workshop bringing together national thinkers (SWG members) and Location Facilitators from 10+ locations across the UK (21st Nov) to share the journey's so far, and discuss the NMP framework (Purpose, objectives, principles)
2021-12-01 | Strategy meeting with Dan and other Blue staff Finalising Insights from PSNMP and building blocks
2022-01-01 | Scoping reporting by Lucy Clutton
2022-02-01 | Legal review for England and Wales commissioned.
2022-03-01 | 3rd Strategic Working Group reviewing & feedback on revised National Framework
2022-04-01 | National Framework survey analysis and preparedness for wider consultation
2022-05-01 | Draft reports to internal consultation & design
2022-06-01 | REPORTING & consultation on national framework/advocacy to Government
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joe Richards please can you review and add key milestones/activities for Scotland. Thanks

## Impact and Outcome
Impact | Use a network of national marine parks to reconnect the UK public to the sea, revitalise deprived coastal communities and increase appreciation and understanding of marine conservation and conservation designations.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | The NMP Vision catalyses the creation of National Marine Parks around the UK coast. By 2030 bottom-up support and test sites will have proved the concept and demonstrated value to the marine environment and society. | OC.0.1 | Number of locations across the UK that Blue Marine have enlisted support in the NMP vision (Scoping) | 2,3,4,8 | 4.2.1, 4.2.2, 4.2.3, 1.4.1, 1.4.3 | 4.2, 4.3, 1.4 | Local level stakeholder and community support to engage with the National Marine Park vision, consider its local application and steps required to move towards NMP status | Key stakeholders recognise National Marine Parks as a priority for environmental/social wellbeing There is enough local demand to support NMPs from the bottom up Public/stakeholders are actively engaged by Plymouth City Council, and their vision is relevant enough to inform other locations.
|  |  | OC.0.2 | Wide recognition of the value/aspiration for NMPs across Britain (National SWG) | 1,5,6,7,8 | 4.2.1, 4.2.2, 4.2.3, 1.4.1, 1.4.3 | 4.2, 4.3, 1.4 | National level stakeholder support for National Marine Parks
|  |  | OC.0.3 | Plymouth NMP is widely recognised as a pioneer for bottom-up engagement. | 2 | 4.2.1, 4.2.2, 4.2.3, 1.4.1, 1.4.3 | 4.2, 1.4 | Engagement and sharing of insights emerging from Plymouth NMP
1 = Release a “Vision for national marine parks” report and film to inspire all stakeholders and unite them behind the concept
2 = Report providing insights to learnings from scoping visits and about bottom-up Marine Park creation and management in Plymouth, including recommendations. Report recommendations (building blocks) shared with stakehodlers
3 = Local support is enlisted across the 10 prospective locations from the vision report.
4 = Further locations are scoped and 3 locations pursue formal NMP status.
5 = To encourage wider ownership of the vision (beyond Blue Marine), establish a NMP Strategic Working Group and support them meet on a quarterly basis to develop strategic thinking i.e. National Framework
6 = Hold a national conference called “The campaign for national marine parks" in 2023 which showcases progress and unites location facilitators with national momentum.
7 = Conduct a media campaign.
8 = Ensure that a case is made to Government for the formal adoption of national marine parks.

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Release a “Vision for national marine parks” report and film to inspire all stakeholders and unite them behind the concept | O.1.1 | Evidence collected from key stakeholders to inform vision, and a technical report produced | 1 | Report | 1.4.1 | Mapping and 25 interviews identifying potential locations for a NMP | Location facilitators are willing to work with Blue Marine The National Marine Park vision is received positively by stakeholders and there is local willingness and capacity to progress the vision to the next stage |  |  |  |  | 0 | Interview 25 people for research and produce and finalise technical report | 1 | Technical report finalised and used as a basis for NMP vision (April 2021) |  | Technical report shared with invited members of the 12 SWG members and location facilitators on request.
|  |  | O.1.2 | Vision report written and presented/shared (printed copy) with relevant stakeholders | 1 | Report | 1.4.1 | Significant interest in report during engagement activities, and number of printed copies which are handed out during events | [5 empty] | 0 | Publish NMP vision report | 1 | NMP vision report published (May 2021) |  | Dissemination of printed reports at events and linking to online social media/comms opportunities. |  | More then 40 copies of the vision report have been shared during scoping visits (June 2022-Oct 2022), and beyond. Twitter monitoring TBC
|  |  | O.1.3 | Relationships built with key stakeholders (location facilitators/SWG members/community) | 10 | Locations | 4.2.1 | Meeting minutes, correspondence etc. to support information/formal relationships | [5 empty] | 10 | Location facilitators to be identified and engaged with to start scoping visit phase of the project | 10 | Location facilitators identified in 10/10 locations, and vision report shared with them in preparation for scoping visits before EOY 2023. (?) |  | Location facilitators to be further engaged with the vision through scoping visits, national workshop and byeond. | 16 | 16/21 Location facilitators from the contact database have been enagegd with through emails/meetings/workshops.Plus more local stakeholders who are not on the contact database. There is potential to focus in on 3 areas in 2023. (Contact database: https://bluemarinefoundation.sharepoint.com/:x:/s/Projects/EXFLoeT3-S9Eij-X1F5S7rYBzZ7kjMWcaNnWB_KAe02Psg?e=qtQUEF)
|  |  | O.1.4 | Film announcing national marine park vision is produced and distributed to increase awareness of the vision | 1 | Film | 4.2.2 | Significant reach based on ? metrics (number or views?) | [5 empty] | 0 | Film created , added to Blue marine's website | 1 | Film created and posted on the website. (April 2021) |  |  |  | 167 views of the film on youtube (Dec 2022) , and played to Severn Estuarary Forum attendees (Oct 2022)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lucy Clutton Can you please input months for all the activities listed? Reply: Have done what I can @Natasha Bradshaw please can you add for cell R6 - this was before I joined
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Natasha Bradshaw to add to. this was before I started

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Report providing insights to learnings from scoping visits and bottom-up experience from Plymouth NMP creation and management, including recommendations. Report recommendations (building blocks) shared with stakehodlers | O.2.1 | Coastal Futures presentation 2022 with Kat Deeney (PCC). Report provided to internal (Blue/others) and external key stakeholders (copy, or presentation during workshops or other meetings) | 1 | Report | 1.4.1 | Copy of presentation, report and workshops/ meeting dates/ minutes |  |  | Unplanned |  | Unplanned |  | Objectives for this work arose due to progress with Plymouth NMP and appointment of an Interim CEO, plus interest from location facilitators to learn from Plymouth. | 0 | Research conducted with 15 key players in Plymouth and initial Plymouth report drafted (June-August 2022) | 1 | Report to be finalised following review rounds and plan to shared with blue staff in full by EOY 2022/ Q1 2023, plan to share more publically in a condensed version (without Plymouth) | 4 | Preliminary findings presented during Strategic Working Group (Sept 2022) and national workshop (Nov 2022), in partnership with Plymouth Sound NMP CEO but report still needs finalising and decision needs to be made on whether to share internally or more widely 4 reports published on website in Sept 2023 * NATIONAL MARINE PARKS – A VISION FOR BRITISH SEAS * NATIONAL MARINE PARKS – GUIDANCE * NATIONAL MARINE PARKS – NATIONAL FRAMEWORK * NATIONAL MARINE PARKS – LEGAL REVIEW
|  |  | O.2.2 | Reach of report [where it was distributed, to how many key stakeholders] |  |  | 4.2.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Report comissioned and interviews completed and analysed |  |  | Complete | Draft report from Lucy to Natasha
|  |  | A.2.2 | Report drafted and shared for review with Blue staff and small stakeholder group |  |  | In Progress | tbc whether PCC want to quote/add to it. tbd wether the report is shared internally or more widely
|  |  | A.2.3 | Extracting from the report for national guidance/recommendations |  |  | In Progress
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Natasha Bradshaw - things like workshop we can report on as outreach activities - have these been counted anywhere? Reply: Oh I have just seen that it is covered in Output 3 but only one - I will update and tag you in a comment on that cell to check I've updated correctly Reply: OK

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Local support is enlisted across the 10 prospective locations from the vision report. | O.3.1 | A national workshop in 2022 to bring together strategic national thinkers (SWG) and Location Facilitators to feedback and discuss the national marine park framework (objectives, principles, purpose) | 1 | workshop | 4.2.2 | Workshop report | There will be interest for a NMP workshop | [7 empty] | SWG underway bringing national thinkers together to provide leadership to location facilitators. |  | Host a workshop in November 2022 and invite location facilitators plus some SWG members to bring together national and local thinkers | 2 | Workshop was hosted in Nov 2022 (see below) and SWG Sep 2022 with 17 participants | 1 | Workshop was hosted in Nov 2022
|  |  | O.3.2 | Reach of workshop [how many key stakeholders attended] | 30 | People | 4.2.1 | Workshop delegate list/attendance | [10 empty] | Host a workshop in November 2022 and invite location facilitators plus some SWG members | 59 | 41 attendees present, 8 external speakers presented on the progress in their location, and 10 SWG members attended (Nov 2022) | 59 | 41 attendees present, 8 external speakers presented on the progress in their location, and 10 SWG members attended (Nov 2022)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Workshop delivered Nov 21st 2022. 41 attendees which surpassed expectations |  |  | Complete
|  |  | A.3.2 | Newsletter summarising status in each location, SWG and plymouth work shared with workshop participants |  |  | Complete | Finalising and due to public EOY 2022
|  |  | A.3.3 | Workshop report drafted and due to be sent to workshop participants and speakers for comments |  |  | Complete
|  |  | A.3.4 | Workshop outputs analysed and integrated into the SWG feedback on NMP principles |  |  | Complete
|  |  | A.3.5 | Scoping activities to support bottom-up engagement in the vision |  |  | Complete
|  |  | A.3.6 | Reporting of scoping activity across ten locations (link Output 4) |  |  | In Progress
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hi Lucy I think we need a row above this to reflect the effort invested in reaching out to location facilitators ahead of the workshop, otherwise it looks like all we had to do was invite them to a workshop, whereas a LOT of preparatory work was involved to bring them to the table - disseminating the reports, following up with them 1-1, online meetings, site visits etc. See the slide in my NMP workshop presentation for all the activities. Reply: Hi @Natasha Bradshaw and @Lucy Clutton - I think this is where the difference between impact/progress comes into play. Holding those meetings as outlined above is progress, but is not impact. Progress can be recorded in the 'Key Updates' tab rather than these output tabs. I can see there are some other comments regarding this so I will also respond to those Reply: thanks for clarifying Appin. I have added to the key updates
Note on U4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Natasha Bradshaw this was 1 - have updated to 2, and updated the comments section to talk about both Nov and sept (previously just referenced Nov) is this correct? Reply: @Natasha Bradshaw Reply: Natasha says yes that's fine so comment can be closed out
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: we have this number, will populate it when the workshop report is delivered Reply: ok great Reply: done
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we also have attendee numbers on the Sep workshop @Natasha Bradshaw ?

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Further locations are scoped and 3 locations pursue formal NMP status. | O.4.1 | Number of scoping visits conducted | 10 | locations |  | Scoping visit reports produced to document visits and insights | [5 empty] | 2 |  | 2 | Iscles of Scilly and Pembrokeshire scoped. IoS: Islands Partnership engaged in national strategic working group. Pemb: Comms continue | 10 | Plan to scope all locations by EOY 2022 with scoping visit report published in Q1/2 2023 | 9 | Scoping activity undertaken across 9 locations. Over 30 location facilitators offering support to widen discussion about the vision and consider next steps. (Dec 2022)
|  |  | O.4.2 | Level of stakeholder support for championed marine park sites [questionnaire results/number of meetings or outreach workshops conducted etc. that reflect local stakeholder support for certain sites]. | tbc | stakeholders | 4.2.1 | [12 empty] | 185 | Local support indicated during scoping visists where vision was presented to stakeholders in Severn (79 stakeholders) and Dorset (106 stakeholders). and formal feedback received indicating interest in the vision. Dorset: 7/16 "yes" or "maybe" to attending a workshop hosted by DCF. 14/16 think it has at least some significance for Dorset. Severn: 7/10 said "yes" to a workshop in Severen, and 7/10 rated the vision significant ( selected 5,6,7 on a scale of 1-7 significant) (Dec 2022)
|  |  | O.4.3 | Eventually, number of locations pursuing formal NMP status where policy/advocacy 'hooks' are leveraged | 3 | locations | NA - progress | NMP status reached (tbd how this happens, i.e. declaration, awarded, designated?)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
| A.4 |  | A.4.1 | Wales: Scoping visit to Pembrokeshire undertaken with ongoing comms. |  |  | Complete
|  |  | A.4.2 | Cornwall: Engagement in 3Cs project steering group (scoping for Mounts Bay) completed. |  |  | Complete
|  |  | A.4.3 | Isles of Scilly: Islands Partnership engaged in national strategic working group. |  |  | Complete
|  |  | A.4.4 | NW England: Morecambe Bay NMP flyer circulated in collaboration with Morecambe Bay Partnership |  |  | Complete
|  |  | A.4.5 | NE England: Seascapes project hosted Blue Marine site visits and hosted a workshop engaging approx 25 local stakeholders |  |  | Complete
|  |  | A.4.6 | South England: Sussex Bay local authorities promoting a common vision for a marine park and engaging in national strategic working group. |  |  | Complete
|  |  | A.4.7 | South England: Dorset Coast Forum invited Blue Marine to present the NMP vision to 106 local/regional users/stakeholders and encouraging feedback received |  |  | Complete | Workshop request from Dorset CF ongoing
|  |  | A.4.8 | The Severn Sea: Severn Estuary Partnership invited Blue Marine to present the NMP vision to 79 local/regional users/stakeholders and we hosted an evening reception, and encouraging feedback received |  |  | Complete | Workshop delivered April 2023
|  |  | A.4.9 | East Anglia: ongoing discussions with Norfolk Council and The Wash Estuary Strategy: planning to meet a wider group of local stakeholders in early 2023. |  |  | Complete | Roundtable in March 2023 concluded preference to wait for 'national' leadership
|  |  | A.4.10 | Scoping visit reports drafted and plan to integrate them into a larger scoping insights report for wider sharing |  |  | In Progress | Internal consultation (May) for publication (June)
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could we put stats such as number of attendees at a forum presentation here or is it elsehwere? Reply: Ignore! I see it is associated with this line as a year 3 indicator, so still NA here? Reply: Yes you could include the number of attendees under this line - this would be recorded under 4.2.1 Reply: have updated to 4.2.1
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: could be 1.1 or 1.2 - but these are restricted to an MPA which isn’t what NMPs are Reply: Hmmm yes you're right, they specifically refer to designations which incorporate additional protections. I'd say let's leave as NA - progress for now, and we can have a think about this in the longer term.

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | To encourage wider ownership of the vision (beyond Blue Marine), establish a NMP Strategic Working Group and support them to meet on a quarterly basis to develop strategic thinking i.e. National Framework | O.5.1 | National stakeholders agreed to sit on SWG | 13 | People | NA - progress | List of NMP SWG membership | There is national interst in developing thinking beyond the vision report. MWC continue to support NMP SWG Secretariat | NA - progress |  | NA - progress |  | 13 | Establish NMP SWG membership and agree ToR | 13 | National strategic working group mobilised engaging 12-14 key strategic thinkers including Natural England, Campaign for National Parks, English Heritage and others. | 13 | Maintain membership | NA - progress
|  |  | O.5.2 | Number of SWG meetings conducted | 4 | meetings | Na - progress | meeting minutes/ strategic working group reports | [5 empty] | n/a - Progress | Hold 1st SWG meeting | n/a - Progress | 1st SWG held online meeting to agree ToR (June 2022) and report created | n/a - Progress | 2nd SWG meeting to be held in Sept 2022 to review national framework, 3rd meeting to be held in Feb 2023, and 4th tbc | n/a - Progress | Sept 2022 online meeting held and feedback to framework provided using a online survey and group discussion. Report created to document the meeting
|  |  | 0.5.3 | NMP National Framework developed | 1 | Framework |  | Framework delivered to Government | A framework is what's wanted and needed to drive NMP status |  |  |  |  | 0 | Draft National Marine Park National Framework | 0 | NMP National Framwork drafted and shared with NMP members for input | 1 | NMP National Framework reviewd and finalised by NMP members |  | Feedback analysed and integrated into draft 3 (Feb 2023)
Activities | [8 empty] | MWC continue to support NMP SWG Secretariat
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | 1st SWG meeting held to agree ToR ( June 2022) |  |  | Complete
|  |  | A.5.2 | 2nd SWG held to start discussio in National Framework (Sept 2022) |  |  | Complete
|  |  | A.5.3 | NMP Framework drafted |  |  | Complete
|  |  | A.5.4 | Questionaire created and shared with SWG members to collect feedback on the national framework |  |  | Complete | Responses analysed and integrated cross-checked/aggregated with Nov workshop feeedback for draft 3 of framework
|  |  | A.5.5 | 3rd SWG meeting in March 2023 included presentation of revised NMP framework & survey to quantify level of support |  |  | Complete
|  |  | A.5.6 | National Framework sign-up by SWG members |  |  | Complete | V3 presented at 3rd SWG for feedback by end April. Final draft version invited for sign-up during May 2023; to launch external consultation June 2023.
A.5.7
A.5.8
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson please can you advise on what indicators fit here? Reply: @Lucy Clutton - as outlined in the other comment, this is something we can record as progress, but we wouldn't typically record this as 'impact' Reply: okay - thanks! Have updated accordingly

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Hold a national conference called “The campaign for national marine parks" in 2023 which showcases progress and unites location facilitators with national momentum. | O.6.1 | Number of conferences | 1 | Number of conferences | 4.2.2 | Conference report | There will be a desire from locations, national thinkers, and others to come together in a conference to discuss NMPs | [10 empty] | 1 | A Parliamentary event was hosted on 4 September 2023 by Blue Marine and Luke Pollard MP
|  |  | O.6.2 | Reach, engagement and impact of conference [based on social media impact report; conference impact report; press exposure etc.] | tbc | Number of stakeholders reached | 4.2.1
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Parliamentary event date, venue booked |  |  | Complete | Postponed until National Framework available for external consultation, endorsed by national SWG - tbc June 2023.
|  |  | A.6.2 | Programme set, invitations issued |  |  | Complete
|  |  | A.6.3 | Report of event published on Blue Marine's webpage |  |  | Complete

## Output 7
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 | Conduct a media campaign. | O.7.1 | Media campaigns completed | 1 |  | 4.2.2 | [11 empty] | Build momentum with NMP allies: Plymouth NMP; CNP; SCNP; NTS; WCL and other NGOs
|  |  | O.7.2 | Reach of media campaign | 1000 |  | 4.2.1 | Social media posts/re-posts; evidence of joint sign-ups to campaign letters etc. | Political context enables other NGOs to offer support for seascapes as well as protected landscapes.
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1 | 1st edition NMP Newsletter (2022) |  |  | Complete | Shared with NMP SWG members and location facilitators; available online
|  |  | A.7.2 | Internal campaign/advocacy strategy |  |  | Not started | Strategy meeting planned for Feb23 postponed (with Charles/Clare/Dan) due to internal priorities within Blue.
|  |  | A.7.3 | Blogs / Newspaper article? |  |  | Not started

## Output 8
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 | Ensure that a case is made to Government for the formal adoption of national marine parks. | O.8.1 | Legal review of legislation that could be leveraged to designation NMPs | 2 | report | NA - progress | Legal review report delivered | The legal route is the direction Blue Marine want to take | NA - progress |  | NA - progress |  | 1 | Review of Scottish NP Act commisioned in April 2022 -to be condcuted by James Harrison | 1 | Legal review of NP Report produced in May 2022 | 1 | Legal review conducted for England/Wales/Isles of Scilly | 0 | Legal review comissioned and delivered Q1 2023
|  |  | O.8.2 | Number of legal reports/evidence/material provided to Government (DEFRA, NatureScot, Marine Scotland etc) | 5 |  | 1.4.1 | meeting mins/emails/ reports. Consultations | [9 empty] | 2 | Establish dialogue over NMP vision and routes to action with Government(s). Legal review in Scotland to be shared with Nature Scot along with consultation response Submitt Scotland National Park Consultation Response | 2 | Legal review for Scotland was shared with Nature Scot on 01 Dec 2022. Blue Marien Submit Scotland National Park consultation response on November 30 2022 | 2 | Legal review for Scotland was shared with Nature Scot on 01 Dec 2022. Blue Marien Submit Scotland National Park consultation response on November 30 2022
|  |  | O.8.3 | Number of organisations that respond to the legal review and its implications |  |  | NA - progress | Responses to legal review/ support | [11 empty] | 10 | SWG members endorsement of legal review findings
|  |  | O.8.4 | Number of organisations that respond to the offer to co-brand the NMP Insights Report (2023) including guidance for locations and national advocacy | 5 | Organisations |  | Logos offered for report branding | [11 empty] | 5 | Organisations visibly co-branding NMP Insights report
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1 | Review of 1949 Act and devolved legislation for England, Wales and IoS is underway. 1st draft due to be delivered in early 2023 |  |  | Complete
|  |  | A.8.2 | Commision legal review of Natonal Park (Scxptland) Act 2000 |  |  | Complete
|  |  | A.8.3 | Share legal review with partners, Government and regulators |  |  | Complete | Initial findings presented to 3rd national SWG (March23)
|  |  | A.8.4 | Informal dialogue with Defra marine and fisheries division lead on stakeholder engagement. |  |  | In Progress | 2nd invitation to present (Feb23)
|  |  | A.8.5 | Hire a consultant in Scotland to engage with National Park Consultation and create a strategy for the next national park in Scotland to include a marine element. |  |  | In Progress | James McKenzie onboard and draft advocacy strategy (April 2023)
|  |  | A.8.6 | NMP Insights Report |  |  | In Progress | Natasha to collate findings from location scoping, national advocacy and Plymouth research for 'Findings on the Journey' report (2021-2023)
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Natasha Bradshaw do you think we are talking cross-purposes and O.8.1 and O.8.2. are the same thing?
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joe Richards could you include the month that this was done? Reply: done :) Reply: thank youuuu!
Note on U4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joe Richards which month please and should this be 1 rather than zero? Reply: @Joe Richards
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @lucy and @Appin Williamson I've put this as 5 for now as there will be the English review and a couple more consultation sin Scotland before end of Barclays so I Believe there will be around 5 reports that can be shared with gov at the end. Reply: Thanks Joe!

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023) |  | Progress achieved 2022 (for Appin to do)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | activities not planned but still have an impact... like presentations/talks that are unexpected when we origonally planned the project
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 4 | 8 | O.1 | O.1.1 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 2 | 6 |  | O.1.2 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 2 | 6 |  | O.1.3 | 0% | 0% | 100% | 100% | 0% | 100% | 0% | 160% | 260% | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 3 | 7 |  | O.1.4 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 3 | 7 | O.2 | O.2.1 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 400% | 400% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 4 | 8 | O.3 | O.3.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 200% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.3.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 196.7% | 196.7% | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | 0% | 0% | 20% | 20% | 0% | 20% | 100% | 90% | 110% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | #VALUE! | #REF! | #VALUE! | #VALUE! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #VALUE! | #VALUE! | 100% | 100% | 0% | #VALUE! | 100% | #VALUE! | #VALUE! | 1.4.1 | 0 | 2 | 6 | 0 | 0 | 0 | 8 | 0 | 8 | 6 | 2 | 2 | 0
|  |  |  | O.5.2 | 0% | 0% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0.5.3 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  | O.6 | O.6.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #VALUE! | #VALUE! | 50% | 50% | 0% | #VALUE! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | 50% | 0% | #VALUE! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | 40% | 40% | 40% | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | 0% | 200% | 200% | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 10 | 260 | 0 | 0 | 0 | 270 | 0 | 270 | 1040 | 59 | 59 | 0
[14 empty] | 4.2.2 | 0 | 1 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 1 | 1 | 1 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0