## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact | Establish effective marine reserves and models of sustainably managed fisheries in Greece
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 |  | OC.0.1
OC.0.2
OC.0.3

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Legal intervention | O.1.1 | Submission of complaints to EU regarding breaches of Habitats Directive | 1 | Number of pieces of evidence to support further protection | 1.4.1 | evidence on breaches of EU and international legislation, in particular, the Habitats Directive, the Water Framework Directive and the Bern Convention. Evidence on lack of protection | we will have enough and strong evidence of breaches | 0 | in planning phase | 0 | in planning phase | 1 | 1 case against Greece on breaches of EU and international legislation | 0 | needs to be further developed | 1 | 1 case against Greece on breaches of EU and international legislation | 0 | needs to be further developed. Planning a study with the Science Unit and the Italian project on assessing the network of marine Natura 2000 sites across the EU mediterranean countries adn the implementaiton of the Habitats directive.
|  |  | O.1.2 | Make initial assessment of Erimitis | 1 | Number of pieces of evidence to support further protection | 1.4.1 | evidence on breaches of EU and international legislation, in particular, the Habitats Directive, the Water Framework Directive and the Bern Convention. | we will have enough and strong evidence of breaches | 0 | in planning phase | 0 | in planning phase | 1 | evidence on breaches of EU and international legislation, in particular, the Habitats Directive, the Water Framework Directive and the Bern Convention. | 1 | Produced an assessment of the legal implications of the Kassiopi project on the marine ecosystems around Erimitis that was provided to the Ionian Environment Foundation (IEF) as additional elements to a complaint made to the EU Commission about the Kassiopi project. | 1 | Gather evidence for the protection of Erimitis | 0 | Currently implementing a project in collaboration with the Ionian Environment Foundation with the aim to safeguard the Erimitis peninsula. The idea is to work on two fronts, both on land and sea, so as to highlight the importance of the area and gather the necessary information and data to propose the legal protection of Erimitis. BMF aims to reinforce the work at sea to highlight the richness of the marine environment in the area. We started the field work on mapping the posidonia meadows and the monk seal surveys.
|  |  | O.1.3 | Create an overview of ocean conservation in Greece | 1 | Number of pieces of evidence to support further protection | 1.4.1 | briefing |  | 0 | in planning phase | 0 | in planning phase | 1 | this work was not in our planning | 0 | we have been doing initial talks internally and with other partners (Thalassa Foundation & WWF Greece), still in planning phase, to be implemented in 2023 | 1 | Joint proposals with other NGOs on ocean policy in Greece | 0 | Discussions with Greenpeace and WWf in Greece to create a coalition of NGOs that will submit joint policy proposals for ocean conservation on Greece with paricular focus on the 30x30 goal (May-June) We have started discussions with WWF and Greenpeace Greece and other NGOs in Greece, planning an overview of ocean condervation in Greece for the first trimester of 2024 in view of the Our ocean conference in April
|  |  | O.1.4 | Catalyse the creation of new legislation for ocean conservation in Greece | 2 | new legislation | 1.4.3 | Ministerial decisions for the creation of Fishing protected Area in Amorgos fro the first time, a ministerial decision for a underwater protected seascape in Santorini for the first time. |  | 0 | in planning phase | 0 | in planning phase | 2 | All the relevant work to create no take zones in Amorgos and Santorini, including the fisheries study, study on Santorini and draft ministerial decision as well as edliberations with the relaveant officials. | 0 | Sept 2022 We signed the MoU with relevant stakeholders for Amorgos and began the fisheries study as agreed with the Fisheries department of the Ministry, we have completed the study and the draft Ministerial Decision for Santorini. The MoU was signed by Blue Marine, the Ministry of Agriculture (and Fisheries), The General Secretariat of Island Policy, the Municipality of Amorgos, the Cyclades Preservation Fund, the local association of small-scale fishermen and the Agricultural University of Athens. | 2 | Submit proposals for Santorini & Amorgos | 0 | Amorgos: the fisheries study is still underway, we are in continues talks with the relevant authorities that will process the proposal and draft the legislation probably towards the end of the year. Santorini: Pending talks with the ministry of Environment after the Greek elections. The fisheries study for Amorgos was completed in October and the proposal was submitted in November to the Ministry of Fisheries. We expect this to go to the Fisheries Committee of the ministry for review and once approved a MInisterial Decision will have to be signed by the Minister (hopefully in the first 6 months of 2024).
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Assessment on the legal implications of the Kassiopi project on the marine acosystems around Erimitis |  |  | Complete | assess the legal implications of the Kassiopi project on the marine ecosystems around Erimitis. The information to be provided to the Ionian Environment Foundation (IEF) as additional elements to a complaint made to the EU Commission about the Kassiopi project.
|  |  | A.1.2 | Show case shortcomings and gaps in designing management plans for Natura 2000 sites |  |  | In Progress | Habitat and biodiversity surveys in 3 existing marine 2000 Natura 2000 sites. Assessment of the way the mapping of Posidonia has been conducted inin these areas, potentailly highlight the inadequate information that has been gathered for these marine Natura 2000 sites and the gaps in knowledge. This can also be valuable in the coming official evaluation of the Natura 2000 network expected sometime in 2023-2024.
|  |  | A.1.3 | holistic Assessment on ocean conservation in Greece |  |  | In Progress | Create a "snapshot" of the situation in Greece regading ocean conservation in Greece: the obligations, the good stuff but also the shortcomings, delays and breaches with recommendations
|  |  | A.1.4 | Relationship building and engagement with Environment, Fisheries and and relevant officials to identify and agree on the right stpes that will lead to the legal designation of Amorgos and Santorini |  |  | In Progress | All the relevant work to create no take zones in Amorgos and Santorini, including the fisheries study, study on Santorini and draft ministerial decision as well as edliberations with the relaveant officials.
A.1.5
A.1.6
"1"
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there existing management plans in place that aren't being adhered to? If so, we can also consider impact indicator 1.2.2 (MPAs exercising management plans) Reply: too ealry to assess this
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou I've changed this to zero because it seems like we haven't issued the report yet, but please let me know if I have got this wrong!
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou I am going to change this to zero if the policy hasn't changed yet - we can make that a '1' when the policy changes Reply: Οκ

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Significant increase of no-take zones in line with Greece's obligations | O.2.1 | Identify priority sites for designation | 3 | Number of pieces of evidence | NA | Proposals submitted for these areas | The necessary data and information exist and are publicly available for initial scoping | 0 | in planning phase | 0 | in planning phase | N/A | Identify priority areas to work on | 3 | Identified and stablished relevant partnerships to work on Amorgos, Santorini and Formikula | 2 | Identify more areas | 2 | Identified two more potential areas: Erimitis & Limnos
|  |  | O.2.2 | Create proposals for new NTZs | 3 | Number of reports | 1.4.1 | Surveys/datasets/fisheries studies in order to produce reports that justify the closure of areas | Data selection is not weather depending or time consuming (e.g fisheries studies that need to include a series of years) | 0 | in planning phase | 0 | in planning phase | N/A | Submit proposals for closures | 2 | a. Created joint proposal with Tethys Institute and iSea for Formikul/ b. created a report and draft ministerial decision for Santorini / c. set the foundations for compiling the evidence for Amorgos | 3 | 1. complete fisheries study for Amorgos and submit proposal for closure, 2. achieve ministerial decision fo Formikoula and 3. Submit report and draft ministerial decision for Santorini. | 0 | 1. Fisheries study completed and submitted to the Fisheries MInistry for review, 2. Formikoula and Santorini on track again after a pause due to Greek elections. Deliberations with the new ministry of environment
|  |  | O.2.3 | Create consensus and support for these proposals with relevant stakeholders (government,regional government, policy, fishers, tourism operators and others) | 100 | Number of stakeholders reached | 3.2.2 | Meeting minutes, correspondence etc. to support informal/formal relationships | These stakeholders are willing to work with Blue Marine, a relatively new presence in the conservation arena of Greece | 0 | in planning phase | 0 | in planning phase |  | At least five stakeholder representatives per area | 12 | For Amorgos: MoU signed between: Fishers' Association (40 fishers), BMF, CPF, Ministry of Fisheries, Ministry of Maritime affairs, Municipality of Amorgos, Prefecture of South Aegean, Agricultural University of Athens. For Santorini: Municipality of Santorini and Fishers Association. MInistry of Environmentt engaged but has not agreed yet and For Formikula: Ministry of Environment and Municipality of Lefkas have agreed | 12 | Maintain support and find new supporters for all areas. | 100 | 1. Amorgos: In talks with the Fisheries MInistry authorities responsible for the EMFF funds to release funds once the area is designated (started in March, still in progress). Santorini & Formikoula: still in talks with relevant stakeholders, also with fishers (professional and recreational, boat owners and other sea related professions). Met with the new Fisheries Minister for Amorgos. Submitted the study to the ministry and also presented it to the fishers' Association whose members voted to support the proposal. pending to meet new deputy Minister of Environment for Formikoula and Santorini. Re activated converations with the fishers of Santorini and the new mayor to jointly sumbint the proposal for an MPA in Santorini
|  |  | O.2.4 | Commitment announced publicly to protect these areas | 3 | Statements/Ministerial decisions | 1.4.3 | Commitment statment is made publicly available and outlines details of protected area/Ministerial decision published in Government's gazette | Commitment is received by the wider public and/or relevan stakeholder in adjacent areas | 0 | in planning phase | 0 | in planning phase | N/A | Some commitments for protection | 2 | The Ministry of Fisheries has agreed to support the designation of no take zones in Amorgos and the Ministry of Environment has officially agreed to proceed with a Ministerial Decision for Formikula | 3 | Maintain commitment for Amorgos and Formikoula, obtain commitment for Santorini |  | We still have support and commitmnet for Amorgos and Formikoula though we need to re-establish this with the new MInisters after the Greek elections nad commence more active tlaks about Santorini. Met with the new Fisheries Minister for Amorgos and pending to meet new deputy Minister of Environment for Formikoula and Santorini. We are engaging with the organising committee of the "Our Oceans Conference" to include Amorgos, Santorini and Formikoula in Greece's commitments for protection
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Relationship building and engagement with Fisheries Ministry, Environment Ministry, Maritime Ministry, Municipality, Prefecture, fishers and NECCA for Amorgos |  |  | In Progress | An MoU of collaboration has been signed between the Fishers' Association of Amorgos, BMF, the Cyclades Preservation Fund, the Municipality of Amorgos, The Prefecture of Souther Aegean, the Ministry of Fisheries and the Ministry of Maritime Affairs.
|  |  | A.2.2 | Fisheries study and gathering of scientific evidence for Amorgos |  |  | Complete | Agreed on a fisheries study with the Agricultural University of Athens, which started in September 2022 and will be completed in September 2023
|  |  | A.2.3 | Design/implement a 5 year management and patrolling system in Amorgos |  |  | In Progress | To be designed in 2023 together with the stakeholders mentioned above
|  |  | A.2.4 | Media Promotion of Amogos (video/stills asssets) |  |  | Complete | hired two videographer to produce 1. underwateer stills and video and 2. two promotional videos and photos that showcase the AMORGORAMA initiative
|  |  | A.2.5 | Relationship building and engagement with Fisheries Ministry, Environment Ministry, Maritime Ministry, Municipality, Prefecture, fishermen, NECCA for Santorini |  |  | In Progress | Initial talks have started with Ministry of Environment fo the designation of the area, and talks with municipality and local stakeholders to consolidate support for the proposal
|  |  | A.2.6 | Gathering of scientific evidence for Santorini |  |  | Complete | Completed a report gathering of ncecessary evidence and drafted the Ministerial Decision for the designation of a protected seascape
|  |  | A.2.7 | Design a scientific monitoring system ans patrolling for Santorini |  |  | In Progress | to be designed with the stakeholders mentioned above and the relevant scientific team from HCMR
|  |  | A.2.8 | Media Promotion of Santorini (video/stills asssets) |  |  | Not started | There are already a lot of materials produced, nee to design a promotion plan
|  |  | A.2.9 | Relationship building and engagement with Fisheries Ministry, Environment Ministry, Maritime Ministry, Municipality, Prefecture, fishermen, NECCA for Formikoula |  |  | In Progress | Sumbited a joint proposal for the closure of Formikula to the Ministry of Environment that has relied in a positive way, conducted a workshop with relevant local stakeholders.
|  |  | A.2.10 | Gathering of scientific evidence for Formikoula |  |  | Complete | Posidonia and biodiversity documentation in the area, compiled a joint report with iSea and Tethys submitted to the Ministry
|  |  | A.2.11 | Design a scientific monitoring system ans patrolling for Formikoula |  |  | Not started | Needs to be designed with iSea, Tethys, the Minstry, the Management body of the area and local stakeholders
|  |  | A.2.12 | Media Promotion of Formikoula (video/stills asssets) |  |  | Not started | Production of video and stills assets
|  |  | A.2.13 | Overlay existing scientific data with Fishers' empiric knowledge and create a proposal of on take zones within the Natura 2000 network of Cyclades. |  |  | Not started | Commission this to a scientist
A.2.14
A.2.15
A.2.16
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: maybe it should be number of identified areas
Note on O4: Angela Lazou: There was no specific goal
Note on V6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Angela Lazou this is a lot of great information. Do you know which months these meetings with fishermen and mayor were held? Is 100 the number of people that have been met with? Reply: Amorgos: we are already in close collaboration with the Association of fishers, they have around 40 members with 20 active fishers. We are at the stage that we submitted the results of the fisheries study to the MInistry of Fisheries and waiti ng for a decision. Formikoula: in talks with the new MInister of Environment. This small islet has no local fishers. There are fishers going to fish there from the wider ares of the Inners IOnian Archipelago. Our partners having been doing interviews with seveal fishers (34 questionnaires). Santorini: we met with the new mayor and the President of the Fishers Association two weeks ago. we have agreed to jointly submit the study and the draft ministerial decision to the new Minister of Environment. The association Ι think has around 200 member but only around 50 are actually active fishers.

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
7 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Tackling invasive species | O.3.1 | Develop public-facing campaigns to create local markets for edible invasive species | 5 | Number of outreach activities (media campaigns, presentations/stalls and markets) | 4.2.2 | number of gastronomy events, seminars, alien species removals conducted | the public and the stakeholders will be interested enough to attand these events | 0 | in planning phase | 0 | in planning phase | 21 | 10 Informative events and 11 gastronomy event | 21 | 10 Informative events and 11 gastronomy event | 5 | 1. Participation in one major food festival in Athens, 2. Implementation of the blue crab festival in Thessaloniki for a second year, 3. culinary events in the Argolic. | 6 | Participation in the fisher's celebration in Amorgos (June). Implemented the blue crab event in Thessaloniki, 2 events in Spetses and Hydra to happen in October, Street Food Festival Crete,
|  |  | O.3.2 | Number of beneficiaries through targetted campaigns | 100 | Stakeholders reached | 4.1.2 | chefs, professional fishers, recreational fishers and processing companies reached through these events, educated about the issue | Chefs and Fishers will see an opportuntity | 0 | in planning phase | 0 | in planning phase | N/A | 60 fishers and 22 chefs, XXX recreational fishers? | 86 | 60 fishers and 22 chefs, 2 processing companies, one supermarket, one export company, XXX recreational fishers? | N/A | 1. Mapping of interested seafood processing companies and local food cooperatives (e.g. NAIAS Paros) in selected areas 2. Supply of edible alien species (especially spinefoots) caught to the selected processing companies and cooperatives for the preparation of novel products with edible alien species such as smoked, salted or sundried products 3. Participation in at least one local food festival (e.g. sardine festival in Amorgos, fishers celebration in Koufonissia) with the abovementioned products and cooperatives (CPF & iSea) | N/A | 1. Communication with the Gastronomic Association of Amorgos for the processing of invasive fish (spinefoots) and trying new recipes 2. Culinary event in June: The fisher’s celebration in Amorgos with salted spinefoot 3. Initial contact with restaurants in Amorgos for the inclusion of processed products in the menu 4. Investigation of the quantities, sizes and price of fresh fish (Amorgos and Koufonisia these numbers will come with the final report in January
|  |  | O.3.3 | Number of citizens reached through targetted events | 1800 | Citizens reached | 4.2.1 | people from the general public informed during the events | People will be interested and open in trying new flavours | 0 | in planning phase | 0 | in planning phase | N/A | no goal was put for this | 1800 | 1800 people informed during the events | N/A | don't have numbers | 2500 | 2500 people informed during the events
|  |  | O.3.4 | Create supply chain models | 2 | case studies | 3.4.1 | surveys, datasets and questionnaires to identify all the types of key stakeholders, the different contraints that occur in the supply chains per species and area and insights on how invasive species can successfully enter the market | Answers will be accurate and will reflect the realities of the market | 0 | in planning phase | 0 | in planning phase | 2 | two case studies on how invasive species can enter successfully the markets | 0 | interviews have been conducted with professional and recreational fishers in all areas of interest, the social and economic interactions, ecological impacts, knowledge and perception of fishers for the most common alien species in each area will be accessed. Additionally, the round table discussion have provided us with valuable information on the realities of the market. The case studies have not been produced yet |  | Supply of edible alien species to the selected processing companies and cooperatives for the preparation of novel products with edible alien species such as smoked, salted or sundried products | N/A | working on understaning the numbers, the finances and the needs for this
|  |  | O.3.5 | Create a selective method of catching lionfish | 36 | traps used |  | report on catches through an online logbook (number and species of fish cught etc), go pro camers to be used on some traps | Fishers will be truthful and consistent in reporting the relevant data | 0 | in planning phase | 0 | in planning phase | 36 | traps to be sent to be used in seasonal basis, with multiple sampling per season in each area,report on catches through an online logbook (number and species of fish cught etc) | 36 | the traps have been sent to the fishers and we are getting the first reports back, this will be completed in a year | 36 | The pilot use of the lionfish traps will continue for 2023 investigating the efficacy of the traps catching lionfish | 36 | In the context of the pilot testing, we have visited Crete (May) and Amorgos (June) to monitor and record the use of the traps underswater. Constant communication with the fishers for the collection and the reporting of the logbooks. Still working on the traps. 36 traps were given to fishers in Amorgos, Rhodes and Crete
|  |  | O.3.6 | Create Promotion assets for this campaign | 4 | promotional assets (online leaflets, ammbassadors testimonies, interactive map) | 4.2.2 | Significant media reach achieved based on tracking metrics | the public will be interested in the campaign | 0 | in planning phase | 0 | in planning phase | 4 | 1. guide on responsible seafood consumption 2. Interactive map with chefs, restaurants and fishers that are part of the network 3. Ambassadors’ testimonies 4. Information signs on ports | 4 | All assets have been produced | 5 | 1. The creation of informative material specialized for each group of stakeholders to be uploaded in a specialized MOOC 2. The responsible seafood consumption guide will be updated with more species, adding also freshwater species, 3. the recipes eBook will be updated adding the recipes that the collaborating chefs will create, 4. the interactive map will be updated with more restaurants, fishers and fishmongers 5. Involvement of a nationally recognizable chef in the project (e.g. Akis Petretzikis) that will create new recipes with edible alien species and promote responsible seafood consumption. | 2 | the recipes book has been updated (June), the map is constantly updated, still working on the Mooc to be completed soon
|  |  | O.3.7 | Number of citizens reached throughCommunications campaign | 10000 | citizens reached | 4.2.1 | people from the general public informed through this campaign | the public will be interested in the campaign | 0 | in planning phase | 0 | in planning phase | 10000 | Facebook, Instagram, Twitter, LinkedIn & TikTok. Press releases will be sent and shared to local (focusing on local actions) and national media in order to attract people in the events and promote the materials created. All the materials, already existing and new ones will be disseminated among the locals (authorities, fishers, restaurants, chefs) in each area. | 175805 | a. Posts on FB reach 9.344 b. Posts on Instagram Reach 151.363 c. Posts on Twitter 11.770 impression d. Posts on LinkedIn 3.328 impressionss | N/A | don't have numbers | N/A | a. Posts on FB reach 215.067 b. Posts on Instagram Reach 17.103 c. Posts on Twitter 11.749 impressions d. Posts on LinkedIn 8.006 impressions
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Gastronomy events with chefs from local restaurants for informing local stakeholders and communitties |  |  | Complete | Gastronomy events with chefs from local restaurants, in Amorgos, Paros, Santorini, Heraklion, Agios Nikolaos, Zakynthos, Kefallonia, Paxoi, Corfu, Hydra Spetses, Kos, Rhodes and a Blue crab festivel in Thessaloniki. the participants were informed about alien species, with emphasis on the species prepared for the occasion. iSea representatives were also asking the participants’ opinion and reactions on the tasting value of the recipes and alien species, as a feedback for the chance of introducing them in their diet.
|  |  | A.3.2 | Seminars/workshops for local stakeholders (chefs, taverna owners and fishers) |  |  | In Progress | Informative events with stakeholders in Amorgos, Paros, Santorini, Heraklion, Agios Nikolaos, Zakynthos, Kefallonia, Paxoi, Corfu, Hydra Spetses, Kos, Rhodes, Lefkada & Ithaca. the participants were informed about the invasive alien species found in each area, their impact, possible measures to mitigate their expansion and abundance, as well as the ecological value of apex predators, the threats they face and examples of responsible seafood consumption. roundtable discussions on how to create connections between chefs and fishers
|  |  | A.3.3 | Informative signs installed at the local ports and other areas of interest |  |  | Complete | Informative signs installed in Amorgos, Paros, Santorini, Heraklion, Agios Nikolaos, Kos, Rhodes
|  |  | A.3.4 | Meetings and round tables with key players of the fishing industry and supply chain chains |  |  | In Progress | Meetings with Supplier in Kavala and with AB Supermarket chain
|  |  | A.3.5 | Pilot traps: pilote use of gear designed for lionfish trapping oi order to catch them in a more selective/sustainable way |  |  | In Progress | Thirtysix lionfish traps are being teseted in the islands of Amorgos, Rhodes and Crete in collaboration with fishers, test started in September 2022 and will be completed in September 2023
|  |  | A.3.6 | Alien species removal events |  |  | Complete | Alien species removals in xxxx
A.3.7
A.3.8
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Angela Lazou do you know the month for the blue crab event and crete street food festival?
Note on V6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou it sounds like we have been reaching out to restaurants and talking with people. Can we start tracking how many people we're reaching? These are good numbers to have - if it would help to set something up that you can log this information in I'm happy to help (or is it that we need this information from partners?)
Note on V9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Angela Lazou just to check - the 2 is the book and map? Reply: yes

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
5 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Reforming fishing | O.4.1 | Work with small-scale fishing communities to combine sustainable fishing with tourism (responsible fishing tourism) | 200 | Number of fishers actively participating in workshops | 3.2.2 | Signing a participation form | Fishers will be interested enough to show up | 0 | in planning phase | 0 | in planning phase | 200? | collect data about the fishing tourism in the Cyclades and the number of fishers who already have a fishing tourism license. address fishers about the benefits of sustainable and responsible fishing tourism | 50 | With CPF we run three seminars for fishers in Koufonisia, Amorgos and Paros | N/A | 1. Run more seminars in the Cyclades, 2. Create a guide for Responsible Fishing Tourism | 50 | Responsible Fishing Tourism Guide published in December. In talks with 50 Fishers around the Cyclades
|  |  | O.4.2 | Help fishermen access EU funding sources that can be channelled into the development of sustainable fishing livelihoods | 10 | Number of beneficiaries of funding | 4.1.1 | Submission of applications | Fishers will understand that the benefits exceed the effort to apply for these funds | 0 | in planning phase | 0 | in planning phase | 10 | 1. Work with relevant authrorities responsible for the Greek EMFF to understamd the money available, the actions that will be funded and the criteria. 2. identify fishers and work with them to apply for funds | 0 | This has not been deveolped, it will commence once the rest of the activities take off. Also the Greek allocation of EMFF funds with be announced early 2023 |  | New funds announced for fishing tourism and new applications by small scale fishers |  | In preliminary discussions with the relevant authorities (since March). No announcement yet
|  |  | O.4.3 | Replicate and scale up Amorgos' example in the rest of Cyclades (Cycladorama) | 100 | Number of fishers actively participating in different in one or all three actions described in the notes below | 3.2.2 | days abstaining, km of nets changed, co-signed proposals for closure of areas. | Fishers will want to work with BMF and will be open to discuss the possibility of measures | 0 | not planned | 0 | not planned | 0 | not planned | N/A | The strategy for this work was designed this year, Since there are many potential Cycladic islands, we started with an ititial scoping and mapping of the islands to identify priority areas. The mapping included hathering info on biological, economic, social and fishing sector characteristics about the areas of interest. initial talks and visits happened in Paros, Antiparos, Naxos, Koufonissia, Santorini, Milos and Kimolos. | 50 | 1. Promotion of Amorgorama to other fishing communities. 2. Visit Paros, Antiparos, Naxos, Santorini, Koufonisia, Milos, Kimolos, Sifnos & Serifos). Create a network of fishers that can act as local champions for sustainable fisheries 3. Meetings, workshops/seminars for: sustainable fishing practices, selectivity of gear, accidental entanglement of marine mammals, benefits of no-take zones / MPAs / FRAs, financing opportunities (public and European funding mechanisms) 4. Field trips and fishers’ exchanges between islands and other areas of Greece but also with fishers from successful MPAs in other countries (like Italy and Turkey). 6. Replicate beach clean-ups by fishers in April and May in new areas. 7. Implement replacement of fishing gear schemes (for more selective ones). | N/A | 1. Created a photo/video assets from Amorgos that we can use in our visits, 2. Visited Paros, Antiparos and Naxos (April/May). Need to do more trips.
|  |  | O.4.4 | Replicate and scale up Amorgos' example in the Argolic (Argolicorama) | 30 | Number of fishers actively participating in different in one or all three actions described in the notes below | 3.2.2 | days abstaining, km of nets changed, co-signed proposals for closure of areas. | Fishers will want to work with BMF and will be open to discuss the possibility of measures | 0 | not planned | 0 | not planned | 0 | not planned | 16 | 16 professional fishers of Spetses have temporarily stowed their nets and been clearing the island's more inaccessible beaches of the tonnes of plastic waste that unfortunately washes up with every winter storm. There are talks for the fishers to create their association and initial talks on co-developing best practices in fishery and management (voluntary code of conduct, proposal for no take zones etc) |  | 1. Continue the programme in Spetses. 2. Expand Argolicorama to other fishing ports like Nea Kios. 3. In these areas, abstain from fishing during the days of the fish reproduction (April/ May) which will offer direct benefits to the marine population and participate in a joint effort to conduct coastal clean – ups, 4. Create a fishing Association in Spetses. 5.Provide opportunities to fishers to learn more about sustainable fishing practices through trainings; 6.Provide opportunities to fishers to learn more about fishing tourism and how to acquire fishing tourism licences | 38 | 1. We implemented the programme in Spetses for a second year with 16 fishers in Spetses and for the first time with 22 fishers in Nea Kios/ 2. Conducted trainings on Responsible Fishing Tourism and on Safe handling and release of sharks and ray in both areas. (end of May).
|  |  | O.4.5 | Replicate and scale up Amorgos' example in the Ionian | 50 | Number of fishers actively participating in different in one or all three actions described in the notes below | 3.2.2 | days abstaining, km of nets changed, co-signed proposals for closure of areas. | Fishers will want to work with BMF and will be open to discuss the possibility of measures | 0 | not planned | 0 | not planned | 0 | not planned | 0 | not planned yet, this work to happen begin in 2023 |  | Design a programme for 2024 | N/A | In discussions with fishers and local stakeholders, Conducting a survey with questionnaires, still in progress
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | create a manual on Responsible fishing tourism, with basic information starting from licensing and taxes to socio-economic benefits and of course sustainable fishing methods to be shared and promoted amongst fishers, and work with a number of fishers to undertake this activity |  |  | Complete | collect data about the fishing tourism in the Cyclades and the number of fishers who already have a fishing tourism license. address fishers about the benefits of sustainable and responsible fishing tourism and create the content of a guide but also the content of seminars to run in different islans along with an external associate, expert in fishing trips, Mr Dimitris Tsafoutis who is primarily involved with fishing tourism and how it can be an activity that can attract more professional fishers.
|  |  | A.4.2 | Transition to more responsible fishing methods and environmentally friendly activities by using EU funds |  |  | In Progress | use EU funds to make necessary amendments for fishig tourism, engage in abstaining from fishing in April and May (important reproductive months), change their gear (larger net mesh size), put photovoltaics, change batteries etc
|  |  | A.4.3 | Identify, persuade and work with other fishing communitites in the Cyclades to engage in sustainable fisheries by being inspired and following the lead and vision of Amorgos |  |  | In Progress | engaged in abstaining from fishing in April and May (important reproductive months), changing their gear (larger net mesh size), and / or be open to the possibility of establishing no take zones / MPAs in their area of operation
|  |  | A.4.4 | Identify, persuade and work with other fishing communitites in the Argolic to engage in sustainable fisheries by being inspired and following the lead and vision of Amorgos |  |  | In Progress | engaged in abstaining from fishing in April and May (important reproductive months), changing their gear (larger net mesh size), and / or be open to the possibility of establishing no take zones / MPAs in their area of operation
|  |  | A.4.5 | Identify, persuade and work with other fishing communitites in the Ionian to engage in sustainable fisheries by being inspired and following the lead and vision of Amorgos |  |  | Not started | engaged in abstaining from fishing in April and May (important reproductive months), changing their gear (larger net mesh size), and / or be open to the possibility of establishing no take zones / MPAs in their area of operation
A.4.6
Note on Q4: Angela Lazou: need confirmation for numbers/final year report still pending

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
6 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Promoting sustainable management of Habitats Directive designations | O.5.1 | Develop specific measures in 'paper parks' to create model of MPA management | 1 | Number of management plans being adhered to | 1.2.2 | 1 report | we will have enough evidence to argue for additional measures | 0 | in planning phase | 0 | in planning phase | N/A | In desiging phase for the Amvrakikos to be launched in 2023 | 0 | Desiging the project with a series of other stakeholders (iSea, Tethys, Ornithological Society of Greece, The sea turtle society of Greece and NECCA |  | 1. Stakeholder identification & engagement 2. Cover certain knowledge gaps pertaining to certain species 3. Disseminate current knowledge of the ecological value and challenges the Amvrakikos Gulf is facing-1 Layman's report |  | Signed the project agreement in May with the other entities. First face to face meeting in June, underway the following work: >>Mapping of all stakeholders in the area / 112 stakeholder contacts have been made >>Improving our understanding about marine megafauna and the threats they face in the Gulf. over 100 questionnaires have been filled with threats and feedback from the local communities + two stakeholders meeting in June and September >>Producing a food web model of the Gulf/ the data has been collected by the Fisheries department of Patras from the different pasterns. It is now being analysed >>Drone (UAV) surveys to identify potential new areas with high concentrations of marine turtles Surveys conducted in July and August >>Assessment of avian mortality due to electrocution and/or collision on the power distribution network Protocols completed and fieldwork in August >>Detecting and mapping possible Posidonia oceanica meadows and coralligenous formations sediment sampling and marine habitat ground truthing campaign in August Layman's report being drafted
|  |  | O.5.2 | Create a film to showcase process from start to finish | 1 | Film | 4.2.2 | assets produced | the public will be interested in this story | 0 | in planning phase | 0 | in planning phase | 1 | Produce video asssets in one area of interest | 3 | Have started producing assets for Amorgos and document the process of a stablishing an MPA and a management plan/ in final stage of produceing two videos and a photo album |  | Create more assets for Formikoula and Limnos | 1 | Launched the video and stills for Amorgos in June and we are in discussions for a video production in Formikoula. /still discussing for Formikoula
|  |  | O.5.3 | Reach of film | 500 | Stakeholders reached | 4.2.1 | Significant media reach achieved based on tracking metrics | the public will be interested in this story | 0 | in planning phase | 0 | in planning phase | 500 | Promotion plan for the video | 0 | not launched yet/need to design a comms plan |  |  | 112 | Mapping of all stakeholders in the area / 112 stakeholder contacts have been made (text taken from O.5.1 text)
|  |  | O.5.4 | Contribute to the Special Environmental Studies and management plans of the sites as well as the national evaluation process of these areas in the future | 4 | briefings with recommendations | 1.4.1 | gathering of existing data, collect new data, assess socio-economic elements | we will have enough evidence to argue for additional measures | 0 | in planning phase | 0 | in planning phase | N/A | three areas that belong to the Natura 2000 network have been selected to cunduct Posidonia mappings, biodiversity surveys, for which the data of Posidonia beds is listed as “Poor” in the Standard Data Forms (SDFs), indicating that more research is needed, while the threats they receive are not sufficiently assessed or monitored (i.e., fishing, tourism, coastal development, pollution etc). | 4 | All three documentations have been completed For Formikula a proposal has been sumbited to the MInistry of Environment. In the final stage for results and compiling reports to be sent to Ministry of Environment. Also contributed to the comments submitted for the Sporades National Marine Park with Thalassa Foundation |  | Send reports and contrinute to the public consultation of the management plans for Limnos and Nisyros |  | Still waiting for public consultation (long election period)/this process hasn't moved
|  |  | O.5.5 | Design and implement an exemplary management plan (create a model) | 1 | report |  | increasing stocks, and biodiversity metrics, socio-economic metrics | we assume that we will have positive results | 0 | in planning phase | 0 | in planning phase | 1 | not planned | 0 | the rollout not designed yet |  | not designed yet
|  |  | O.5.6 | Economics unit develop mechanisms of finance to ensure economic sustainability | 1 | Number of pieces of evidence compiled to demonstrate economic benefits of ocean conservation | 5.1.1 | Self-funded protection?? |  | 0 | in planning phase | 0 | in planning phase | 1 | not planned yet | 0 | not designed yet |  | design a project | 0 | in discussions with Kaja to design a biodiversity credits project in Amorgos
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Independent assessments of Natura 2000 sites |  |  | In Progress | Increase knowledge on distribution, coverage and health of important habitats (such as seagrass), conduct biodiversity surveys and document threats with the aim to propose additional protection measures (and no-take zones) within Natura 2000 sites. Sumbit proposals to Ministry of environment and participate in national consultation for the management plans of these areas.
|  |  | A.5.2 | Improve management in Amvrakikos Gluf (National Park) |  |  | In Progress | long-term partnership among different stakeholders operating in the Amvrakikos Gulf, for improving management and supporting the livelihood of the locals by increasing scientific knowledge and investing in habitat and biodiversity restoration through targeted interventions.
|  |  | A.5.3 | Create a film documenting the work in Amvrakikos |  |  | Not started | Video assets to document the importance of the area and the efforts to improve management
|  |  | A.5.4 | Create a guide from steps taken to implement a management plan and a patrolling system in Amorgos |  |  | Not started | A blueprint that guides other stakeholders championing the estaablishment of new MPAs by providing useful insights to support longterm successful protection. Or contribute to BMF's existing blueprint??
|  |  | A.5.5 | Create a film documenting the work in Amorgos |  |  | Complete | Video assets to document all steps of the process
A.5.6
A.5.7
A.5.8
Note on T5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou I have moved this from achieved in 2022 to planned in 2023, as it sounds like it's not released yet, but please let me know if I misunderstood this ☺️ Reply: hopefully they will be finalised this December Reply: ok great - in that case I will move them back Reply: OK great, thank you
Note on O6: Angela Lazou: not sure about this
Note on F7: Angela Lazou: difficult to put a number on this at the moment
Note on V9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou have changed this to zero as it's not developed yet

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Increase protection of important habitats such as Posidonia meadows | O.6.1 | Identify priority areas for protection interventions | 3 | Areas identified for protection/additional measures | 1.4.1 | measures proposed for these areas, a prioritisation modelling for the Ionian | that the necessary data will be available and reliable | 0 | in planning phase | 0 | in planning phase | 0 | not in the initial plan | N/A | in designing phase for 2023, talk with the Ionian Environment Foundation, iSea and the management body in the Ionian | N/A | Prioritisation modeling for the Ionian identifying hotspots (areas with seagrass under threat by various anthropogenic activites) | 1 | The Layman’s report ‘Prioritising Posidonia oceanica meadows in the Ionian Sea’ was produced by iSea, in collaboration with terraSolutions.mer, Ionian Environment Foundation and Blue Marine Foundation, within the framework of REPOSIDONIA project, to shed a light on the gaps of knowledge regarding the threats that Posidonia face in the Ionian Sea and prioritise the meadows that are of urgent need of protection. See report here https://bluemarinefoundation-my.sharepoint.com/:b:/p/angela/EVGXIm2pHnpFhcYojPJ2WJwBLwU2OFR7d5jd7j2TKTFpqw?e=dwRdaB
|  |  | O.6.2 | Conduct Posidonia mapping, health assessments and blue carbon calculation | 3 | Quantity of pieces of evidence (1 map, 1 health assessment, 1 blue carbon calc) | 1.4.1 | maps with coverage, health assessments, biodiversity lists | that the maps and methodology will be accepted by the relevant authorities | 0 | in planning phase | 0 | in planning phase | N/A | maps with coverage, health assessments, biodiversity lists in unidentified areas | 3 | three mappings (total 90km) have been completed | 2 | Map other areas. | 0 | Planning more mapping in Erimitis (corfu), Amvrakikos Gulf and Hydra island (for autumn). Erimitis fieldwok happened in July, waiting for results. Waiting for maps of coraligenous seabed in Preveza (amvrakikos), Hydra mapping completed but waiting for results in January
|  |  | O.6.3 | Propose additional measures and targeted interventions (in relation to the threats) | N/A | reports | 1.4.1 | reports submitted, piloting interventions (such as eco moorings) |  | 0 | in planning phase | 0 | in planning phase | N/A | proposing of additional measures in unidentified areas | 0 | We are in the process of compiling reports to be sent to Ministry of Environment for Limnos and Nisyros | 2 | Submit results and proposals for effective management during the NAtura 200 sites national consultation. | 0 | Process pending, still waiting for consultation/ the process hasn't moved
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Prioritisation modelling for Ionian |  |  | In Progress | Spatial assessemnt for Posidonia in the Ionian, mapping of anthropogenic activities, and overlaying these in order to conduct a prioritisation modelling for identifying prioriry areas and and proposing a regional action plan for Posidonia
|  |  | A.6.2 | Seagrass and other habitats documentation |  |  | In Progress | Select area belong to the Natura 2000 network have been selected to cunduct Posidonia mappings, biodiversity surveys, for which the data of Posidonia beds is listed as “Poor” in the Standard Data Forms (SDFs), indicating that more research is needed, while the threats they receive are not sufficiently assessed or monitored (i.e., fishing, tourism, coastal development, pollution etc). COnduct mappings, health assessments and biodiversity surveys
|  |  | A.6.3 | Sumbit proposals for improving habitat protection |  |  | In Progress | Compile existing and new data to sumbit proposals for additional protection in the areas mapped
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou I've been reading through a few of the outputs tabs, are there any that are being counted multiple times? I'm thinking of the impact indicators that we have against 1.4.1, I have seen Formikula mentioned a few times Reply: yes it is mentioned because it contributes to several objectives. For example, we mapped the island for the posidonia meadows which falls under protecting important habitats but the opportunity arouse to protect the island so we are pushing for this (it falls under our no take zones pillar Reply: Ok - we need to make sure we're not double counting anything across our outputs or it will look like we have done more than we really have. Please could you pick an output that you would like these to be reported under, and you can include a comment in the other output tabs like 'please see output 6 for impacts relating to XX'?
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Angela Lazou - is this the same report as mentioned in output 5 that got sent to MoE for Formikula? If so, we will need to remove from either this tab or output 5 to make sure we're not counting twice Reply: yes it is the same Reply: OK - could you pick which output it sits best in and delete it from the other? Reply: I deleted it from here

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 |  | O.7.1
O.7.2
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 |  | O.8.1
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | 1. Fishermen of Amorgos (working together to designate an MPA): 40 | 40 | Number of non-monetary beneficiaries | 4.1.2 |  |  |  |  | 40 | 1. Fishermen of Amorgos (working together to designate an MPA): 40
U.2 | 2. Fishermen involved in a network for marketing edible invasive species: 60 around Greece | 60 | Number of non-monetary beneficiaries | 4.1.2 |  |  |  |  | 60 | 2. Fishermen involved in a network for marketing edible invasive species: 60 around Greece
U.3 | 3. Fishermen who participated in Argolicorama: 16 | 16 | Number of non-monetary beneficiaries | 4.1.2 |  |  |  |  | 16 | 3. Fishermen who participated in Argolicorama: 16
U.4 | 4. Attendees of events for invasive species: 1800 | 1800 | Number of stakeholders reached | 4.2.1 |  |  |  |  | 1800 | 4. Attendees of events for invasive species: 1800
U.5 | 5. Chefs involved in the campaign for invasive species: 13 | 13 | Number of non-monetary beneficiaries | 4.1.2 |  |  |  |  | 13 | 5. Chefs involved in the campaign for invasive species: 13
U.6 | 6. Two new jobs were created: a. a research assistant for the Agricultural University of Athens for the fisheries srtudy in Amorgos and b. a project officer for Cyclades Preservation Fund working with fishing communities in the Cyclades. | 2 | Number of monetary beneficiaries | 4.1.1 |  |  |  |  | 2 | 6. Two new jobs were created: a. a research assistant for the Agricultural University of Athens for the fisheries srtudy in Amorgos and b. a project officer for Cyclades Preservation Fund working with fishing communities in the Cyclades.
U.7 | Social media reach including FB, Insta, Twitter, LinkedIn | 10000 | Number of stakeholders reached | 4.2.1 |  |  |  |  | 175805 | a. Posts on FB reach 9.344 b. Posts on Instagram Reach 151.363 c. Posts on Twitter 11.770 impression d. Posts on LinkedIn 3.328 impressionss
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected
Output 1 | 4 | 8 | O.1 | O.1.1 | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 4 | 8 |  | O.1.2 | 0% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 7 | 11 |  | O.1.3 | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 5 | 9 |  | O.1.4 | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 6 | 10 | O.2 | O.2.1 | 0% | 0% | #VALUE! | 100% | 0% | 100% | 66.67% | 66.67% | 166.7% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | O.2.2 | 0% | 0% | #VALUE! | 66.67% | 0% | 66.67% | 100% | 0% | 66.67% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | O.2.3 | 0% | 0% | 0% | 12% | 0% | 12% | 12% | 100% | 112% | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 | O.3 | O.3.1 | 0% | 0% | 420% | 420% | 0% | 420% | 100% | 120% | 540% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.3.2 | 0% | 0% | 86% | 86% | 0% | 86% | #VALUE! | #VALUE! | #VALUE! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 |  | O.3.4 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | #VALUE! | #VALUE! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | 0% | 0% | #VALUE! | 25% | 0% | 25% | #VALUE! | 25% | 50% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | 0% | 0% | 0% | #VALUE! | 0% | #VALUE! | 50% | #VALUE! | #VALUE! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | 0% | 0% | #VALUE! | 0% | 0% | 0% | 0% | 0% | 0% | 1.4.1 | 0 | 10 | 1 | 0 | 0 | 0 | 11 | 0 | 11 | 12
|  |  |  | O.5.2 | 0% | 0% | 100% | 300% | 0% | 300% | 0% | 100% | 400% | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.4 | 0% | 0% | #VALUE! | 100% | 0% | 100% | 0% | 0% | 100% | 1.4.3 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5
Outputs: | 10 |  | O.6 | O.6.1 | 0% | 0% | 0% | #VALUE! | 0% | #VALUE! | #VALUE! | 33.33% | #VALUE! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | 0% | 0% | #VALUE! | 100% | 0% | 100% | 66.67% | 0% | 100% | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 78 | 188 | 0 | 0 | 0 | 266 | 0 | 266 | 280
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 10
[14 empty] | 4.1.2 | 0 | 86 | 0 | 129 | 0 | 0 | 86 | 129 | 215 | 100
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 177605 | 2612 | 177605 | 0 | 0 | 180217 | 177605 | 357822 | 12300
[14 empty] | 4.2.2 | 0 | 28 | 9 | 0 | 0 | 0 | 37 | 0 | 37 | 5
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0