## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | BLUE's M&E Guide.pdf
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-11-01 | * CSS announced at COP26, Glasgow * Bloomberg Press article "Scientists Want to Find Out How Much Carbon the Oceans Can Absorb" *he | https://www.bloomberg.com/news/articles/2021-11-05/how-much-carbon-can-the-oceans-absorb?leadSource=uverify%20wall
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01 | * CSS official start and receipt of first donation tranche
2022-05-01 | * Recruitment and team onboarding phase initiated
2022-06-01 | * CSS website (phase 1) and social media platforms launched on World Ocean Day
2022-07-01 | * Steering Committee Meeting, Convex HQ, London
2022-08-01 | * Advisory Board members interviewed and contracted
2022-09-01 | * Tender and selection process for digital and education partners completed
2022-10-01 | * Contracts signed with Unseen Studios and EncounterEdu * CSS Strategy Day, Falmouth, Cornwall * Prof Callum Roberts podcast on CSS for Convex Conversation released online | https://convex.podbean.com/e/callum-roberts/
2022-11-01 | * Fishmongers Hall Launch Event, London * Carbon Measuring and Monitoring Workshop for scientific leads * Blue Marine Parliamentary Reception, Downing Street, attended by Stephen Catlin * Presentation by Gabriella Gilke at COP27 Sharm el-Sheikh Climate Change Conference * Carbon mesocosm experiment filming, Stretton Campus, Exeter * Steering Committee Meeting, Convex HQ, London
2022-12-01 | * UN Biodiversity Conference (COP15), Montreal, Blue Marine representing CSS * Citizen Science and Outreach Strategy Day
2023-01-01 | * Lesson: Ocean and Climate Science (KS2, KS3 and KS4) available on EncounterEdu hub * Carbon Cycle Interactive Diagrams and Activities available on EncounterEdu hub * Film: Intro to CSS launched on YouTube * Film: Deep Dive with Earth Scientist Sarah Bradley launched on YouTube * Film: Meet Historical Ecologist Dr Ruth Thurstan launched on YouTube
2023-02-01 | * Live Lesson: Women on the frontiers of climate science * Steering Committeee Meeting, Covex HQ, London * First Advisory Board Meeting, Convex HQ, London * Science Strategy Day, Exeter, Cornwall * Presentation by Rachel Delhaise at World Ocean Summit, Lisbon, Portugal
2023-03-01 | * Live Lesson: Seabed Safari * Year One Annual Report submitted * Film: How is blue carbon mixed in the seafloor? Launched on YouTube * £3.5m bid submitted to the NERC (Highlight Topic) for additional funding to develop and reproduce the PML trawl experiment.
2023-04-01 | * Live Lesson: How do we know about climate change? * George Duffield podcast on CSS for Convex Conversation released online
2023-05-01 | * Live Lesson: How to teach the carbon cycle * Great British Bioturbation-athon fieldwork, Millport, Scotland * Article by Annabel Kemp published on the Divernet website | https://divernet.com/scuba-news/conservation/help-to-pinpoint-dive-sites-of-scientific-interest/
2023-06-01 | * Article by Annabel Kemp published in the SSI Dive blog * Article by Annabel Kemp published on the AAUS website * Article by Annabel Kemp published on CMAS Europe's website * Blue Marine project staff restructuring (Grant Manager recruited) * Live Lesson: Whales, carbon and climate * WalkWithWhales augmented reality filter launched on World Ocean Day * Presentation by George Duffield at Brilliant Minds event, 20 attendees * Al Jazeera Bioturbation-athon coverage released online * Steering Committee Meeting, Convex HQ, London * Second Advisory Board Meeting, online * Presentation by Gabriella Gilkes and George Duffield at the Convex Town Hall Meeting * Media Training Session for CSS scientists * Met with Bermuda contact for discussoin of CSS education roll-out | *https://cmas-europe.eu/2023/06/05/dive-into-marine-conservation-with-the-convex-seascape-survey/ *https://aaus.org/Shared_Content/News_and_Announcemnts/Convex_Seascape_Survey.aspx *https://www.divessi.com/blog/Convex-Seascape-Survey-9028.html
2023-07-01 | * CSS highlighted on Theresa's blogs on the Pacific Row website * Poster at Urbanization, Water and Food Security Conference in Tuscany, 80 delegates * Carbon Analyser procured and installed for Penryn campus. * Infographics and activities on ocean life on EncounterEdu hub * Lesson: How is life adapted to ocean habitats? (KS2 and KS3) on EncounterEdu hub * CSS Art Trail Exhibit in Exeter (across 20 locations) | https://pacific-discovery.com
2023-08-01 | * Citizen science campaign laucnhed across CSS social media channels
2023-09-01 | * Fieldwork commenced by Exeter scientists on the Isle of Arran * First CSS Newsletter produced and circulated to mailing list * Presentation by Gabriella Gilkes in keynote for British Science Festival, Exeter * Mud and Mixology event for the British Science Festival, Exeter * Gail Fordham and Matt Jarvis visit to Arran for media capture * Steering Committee Meeting, Convex HQ, London * Ad campaign delivered with Clarity on META for citizen science * Prof Callum Roberts presenting keynote lecture at Shackleton Conference, London * Article by Annabel Kemp published in BSAC magazine (28,000 members) * CSS citizen science featured in UK Blue Carbon Forum's September Newsletter * Sophie Ward presented at the Shel Sea Oceanography workshop (50 attendees).
2023-10-01 | * CSS Digital Experience website launch * The Times Earth Summit, Bristol. George Duffierld on a panel and spoke on CSS * Blue Carbon Forum event, RGS London. Gail Fordham and Ben Harris in attendence. * Met with Lisa (Convex) and Warwick Academy regarding edu roll out in Bermuda
2023-11-01 | * Chris Levine CSS showcase Southampton Uni to University of Exeter 6th-7th * Steering Committee Meeting, Convex HQ, London * Ad campaign delivered with Clarity on LinkedIn for citizen science * Poster submission entered for UN Ocean Decade, Barcelona (2024) * Contract signed with EncounterEdu for year-two delivery of CSS education program * Agreement with DP World signed, providing funding for seascape animation * Posters produced for Naomi Hart's art workshops
2023-12-01 | * Onboarding The Prophets press agency * COP28, UAE, Gabriella Gilkes, Prof Callum Roberts and Rachel Delhaise attending - Blue Economy Dinner at Jameel Residence, Chris Gorell Barnes spoke on CSS 02.12.23 - Gabriella Gilkes presenting CSS at Blue Marine/PML side event 05.12.23 - CSS Round table event at Goals House 06.12.23 - Gabriella Gilkes presenting CSS in Blue Zone 09.12.23 * Gail Fordham met Sussex Underwater to gain their help promoting citizen science * Contract signed for sponsorship of World Ocean Summit * Live Lesson: COP28 Review and Q&A * Vibrocore testing | https://bluemarinefoundation.sharepoint.com/:v:/s/Fundraising/EaMu0H1pw95Eh1bbUOaDl54Bwa9PPQfVHwVqG-W7iyj9hg?e=RzEU5h
2024-01-01 | * Arran Expedition film release * Bioturbation press release picked-up by ECO Magazine | https://www.ecomagazine.com/news/research/huge-carbon-storage-potential-discovered-in-seabed-dwelling-creatures-by-the-convex-seascape-survey
2024-02-01 | * Women in science reel release on the 11th * Project Away Days in Windsor 19th-20th * CSS Newsletter produced and circulated to mailing list
2024-03-01 | * World Ocean Summit, 11th-13th March, Lisbon, Portugal * Live Lesson on the 12th: Time to heal the sea, feat. Mara, Tara, Ben * Live Lesson on the 14th: Time to rewild the sea, feat. Mara, Tara, Ben
2024-04-01 | * UN Ocean Decade Conference, 10th-12th, Barcelona, Spain * Possible start of Jersey fieldwork * Zoe Roseby joining EGU geoscience conference 14th-19th, Vienna, Austria * Out of the Blue event, The Conduit
2024-05-01 | * Bermuda Convex trip, presentation to GEC
2024-06-01 | * Chris Levine artwork release for World Ocean Day 8th June * Oceans Past X conference Ruth Thurstan presenting CSS historical ecology, Penryn.
2024-07-01
2024-08-01
2024-09-01
2024-10-01 | * Zoe Roseby joining QUEST cruise to collect sediment cores in the Irish Sea
2024-11-01

## Impact and Outcome
Impact | The proper integration of the ocean into political and policy efforts to slow and stabilise climate change.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | Study blue carbon stored in the coastal seafloor and seascape to deliver new, reliable, opensource data which will educate, inspire and enable informed and climate-wise decisions on ocean use. | OC.0.1 | Multi-disciplinary research workstreams generate empirical evidence on how the ocean impacts climate change by quantifying the additional carbon value and co-benefits of whole seascape recovery. | 1, 2, 3 | 1.4.1 | 1.4
|  |  | OC.0.2 | Educate young people, the public, governments and decision-makers in the UN climate change process on the value of a vibrant, living ocean for climate action. | 4 | 4.2.1, 4.2.2, 4.3.1, 4.4.1, 4.4.2 | 4.2, 4.3, 4.4
|  |  | OC.0.3 | Policy changes result in continental shelf seabed habitats being proactively managed to enhance their carbon storage potential. | 1, 2, 3, 4 | 1.4.1, 4.2.1, 4.2.2, 4.3.1, 4.4.1, 4.4.2 | 1.4, 4.2, 4.3, 4.4
Blue Marine Foundation, the University of Exeter and Convex Insurance Group Limited have partnered on an ambitious, five-year global research programme: The Convex Seascape Survey: This is pioneering collaboration of world-leading experts, working to quantify and understand blue carbon stored in the coastal ocean floor and seascape. The project aims to deliver new, reliable, open-source data and outreach, which will educate, inspire and enable informed decisions on ocean use, to harness the power of the sea in the fight against climate change.

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Work programme 1: The where, when, how and what of blue carbon in the seascape ($851, 883) | O.1.1 | New evidence compiled to support protection through publication of project papers | 1 | Scientific Papers | 1.4.1 | Research data and findings are available and accessible (open access) | Suitable collaborators identified in areas of interest Recruitment of high calibre research staff Fieldwork not impeded by hazards (weather etc.) | [6 empty] | 1 | Q2: Manuscript on ‘across shelf carbon flows’ is submitted.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Data mining and synthesis-mapping of seabed topography, carbon accommodation space and prior sampling effort (Task 1.1) |  |  | In Progress
|  |  | A.1.2 | Oceanographic modelling to predict carbon accumulation and hydrographic model development and application (Task 1.2) |  |  | In Progress | Areas of interest identified: Patagonian shelf, Argentina; Sunda Shelf, Indonesia; Indus shelf, Pakistan; Congo fan, Democratic Republic of Congo and the Celtic Deep, UK.
|  |  | A.1.3 | Oceanographic modelling to predict carbon accumulation-verification and refinement of hydrographic models of carbon burial based on field sample analyses (Task 1.2) |  |  | Not started | A manuscript describing the process that the oceanographic modelling team will follow and some model output as a proof of concept will be submitted for publication.
|  |  | A.1.4 | Oceanographic modelling to predict carbon accumulation-projection of changes in carbon burial under future sea level rise (Task 1.2) |  |  | Not started
|  |  | A.1.5 | Fieldwork – Identification of field sample sites and international project partners Task (1.3) |  |  | In Progress | Transfer budget to access sampling in certain regions via ships of opportunity aka research cruises rather than via formal partnerships with local institutions.
|  |  | A.1.6 | Fieldwork – Collection of fresh core samples to verify insights from models and data mining, and resampling of previously collected cores kept in collections worldwide (1.3) |  |  | Not started
|  |  | A.1.7 | Tracing the origins of blue carbon inputs to the seabed carbon sink. Analyses of samples for content and origin of buried carbon and testing (Task 1.4) |  |  | Not started
|  |  | A.1.8 | Placing sediment carbon into context of global carbon – data mining to identify three shelf seas to develop and apply an existing carbon budget model to (Task 1.5) |  |  | Complete | Carbon budget models to be produced for the European Shelf, Patagonian shelf, Tasmanian shelf and the mid/south Atlantic Bight.
|  |  | A.1.9 | Placing sediment carbon into context of global carbon-development of carbon budget models for the three identified shelf seas (Task 1.5) |  |  | Not started

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Work Programme 2: Human influences on seascape carbon ($1,550,048) | O.2.1 | New evidence compiled to support protection through publication of project papers | 1 | Scientific Papers | 1.4.1 | Research data and findings are available and accessible (open access) | Suitable collaborators identified in areas of interest Recruitment of high calibre research staff Fieldwork not impeded by hazards (weather etc.) | [7 empty] | Q1: Manuscript: "The world was our oyster: Records reveal the vast historical extent of European oyster reef ecosystems" submitted to npj Ocean Sustainability in April 2023.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Historical development and spread of human influences on the seabed. Scan of archives and other data sources for evidence of the spread of human influence on continental shelves (Task 2.1) |  |  | In Progress
|  |  | A.2.2 | Historical development and spread of human influences on the seabed-collation of eyewitness evidence of the unimpacted state of the seabed (Task 2.1) |  |  | Not started
|  |  | A.2.3 | Historical development and spread of human influences on the seabed-evidence synthesis and mapping (Task 2.1) |  |  | Not started
|  |  | A.2.4 | Contemporary intensity and distribution of bottom disturbance by human activities-mapping and analyses of satellite data to determine patterns and intensity of fishing gear use and other forms of disturbance (Task 2.2) |  |  | Not started
|  |  | A.2.5 | Contemporary intensity and distribution of bottom disturbance by human activities-analyses and mapping of overlap in hotspots of vulnerable buried carbon (from Tasks 1.3) and human disturbance of the seabed (Task 2.2) |  |  | Not started
|  |  | A.2.6 | Where are the world’s remaining areas of pristine/intact seabed habitat? Design and application of a citizen science programme (Comms/ Outreach) (Task 2.3) |  |  | In Progress
|  |  | A.2.7 | Where are the world’s remaining areas of pristine/intact seabed habitat? Identification and verification of seabed habitats in potentially unimpacted sites with Blue Marine Outreach (Task 2.3) |  |  | Not started
|  |  | A.2.8 | Viewing the impact of seascape disturbance from space – collation, analysis and mapping of satellite data on sediment disturbing human activities (Task 2.4) |  |  | In Progress | PML trawl experiment was originally planned for April 2023 but will most likely occur later in 2023.

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Work Programme 3: Life and biodiversity effects on blue carbon capture and burial and benefits of protection ($1,317,200) | O.3.1 | New evidence compiled to support protection through publication of project papers | 1 | Scientific Papers | 1.4.1 | Research data and findings are available and accessible (open access) | Suitable collaborators identified in areas of interest Recruitment of high calibre research staff Fieldwork not impeded by hazards (weather etc.) | [7 empty] | Q2: Manuscript examining the general issues around the carbon use in research projects has been completed by Dr Jamie Shutler and is in internal review. Q2: A literature "What evidence is there for biological burial of carbon by marine benthic invertebrate fauna and what are the implications for longterm sequestration?" will be submitted for review and publication shortly. |  | * Follow-up experiments are planned to be carried out in the Aquatic Research Centre, Exeter in Feb 2024. These experiments will focus on distribution of particulate organic carbon, building the link between bioturbation and carbon more strongly.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Monitoring and measuring uptake of carbon by seabed habitats and recovery of carbon stocks after protection. Identification of protected and control sites for field study, and of international research partners for collaboration (Task 3.1) |  |  | In Progress | An initial review of MPAs has been undertaken. The South African continental shelf is of interest and potential collaborators approached. Further agreements are in preperation with partners in Western Australia and Jersey.
|  |  | A.3.2 | Monitoring and measuring uptake of carbon by seabed habitats and recovery of carbon stocks after protection. Design of modular sampling programme to evaluate the effects of protection on biota (Task 3.1) |  |  | In Progress | Researchers have begun to design Baited Remote Underwater Video System field observations which will be carried out with our overseas partners or from Ships of Opportunity.
|  |  | A.3.3 | Monitoring and measuring uptake of carbon by seabed habitats and recovery of carbon stocks after protection (Task 3.1) |  |  | Not started
|  |  | A.3.4 | Laboratory mesocosm experiments. Laboratory mesocosm measurements of the effects of seabed biota on carbon capture and burial (Task 3.2) |  |  | In Progress | In May 2023 the team completed 2 days of ship sampling, 146 sediment grabs and ten days of lab experiments for the Great British Bioturbation-athon.
|  |  | A.3.5 | Laboratory mesocosm experiments. Laboratory mesocosm measurements of the effects of global change processes on seabed carbon capture and burial (Task 3.2) |  |  | Not started
|  |  | A.3.6 | Evaluating the co-benefits of seabed protection from human impacts on wildlife and ecosystem services (Task 3.3) |  |  | Not started | KAUST researchers will investigate the fate of suspended carbon as well as resolving the impact of whaling on Southern Ocean productivity and carbon sequestration
|  |  | A.3.7 | Economic values of protection – economic costbenefit analyses of change in ecosystem services under protected vs unprotected vs partially protected management regimes (Task 3.4) |  |  | Not started
|  |  | A.3.8 | Measuring, monitoring and minimising the project’s carbon and environmental footprint (Task 3.5) |  |  | In Progress

## Output 5 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 |  | O.5.1
O.5.2
0.5.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8

## Output 6 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 |  | O.6.1
O.6.2
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 |  | O.7.1
O.7.2
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 |  | O.8.1
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Target Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress achieved in 2021 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
9 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | 0.4 | Work Programme 4: Communicate and educate on the findings of the project ($2,250,000) | O.4.1 | Social media followers | 2500000 | Posts/Reels | Convex-specific | [9 empty] | 16 social media reels produced
|  |  | O.4.2 | Number of social media impressions | 11000000000 | Impressions | Convex-specific |  |  |  |  | 5290 | Instagram: 590, Facebook: 2.7k, Twitter: 7 engagement, 51 followers, LinkedIn: 2K impressions, Podcast: 163 downloads | 11 billion | The Project aims to get 11 billion impressions over 5 years | 325, 334 | End-June: Instagram - 19000 ¦ Facebook - 145000 ¦ Twitter - 23000 ¦ LinkedIn - 21000 ¦YouTube - 527 ¦ Website - 3600 ¦ UoE social media - 73207 ¦ BMF social media - 40000 *Emma to update Shared by Blue Marine ambassadors including Fi Drummond, Nick Hounsfield, Chris Packham, celebrity chef Hugh Fearnley-Whittingstall posted a reel rom River Cottage and Gentoo Sailing posted a reel live from their boat mid-sail! * Zandile Ndhlovu @Zandithemermaid re-posted the citizen science reel * Sussex Underwarer re-posted citizen science reel
|  |  | O.4.3 | Other media assets i.e. press, film, podcast, newsletter, website etc. |  | Outreach tools | 4.2.2 | URL links to films or posts |  |  | Nov 2021: Bloomberg Press article "Scientists Want to Find Out How Much Carbon the Oceans Can Absorb" |  | Jun: Website (phase 1) laucnhed on World Ocean Day Jun: Social media platforms launched on World Ocean Day Oct: Prof Callum Roberts Convex Conversation podcast |  |  | 9 | Jan: Film Intro to CSS launched on YouTube Jan: Film Deep Dive with Sarah Bradley launched on YouTube Jan: Film Meet Dr Ruth Thurstan launched on YouTube May: Wes Anderson style bioturbation film, views 8730 May: Article by A. Kemp published on the Divernet website Jun: Article by A. Kemp published in the SSI Dive blog Jun: Article by A. Kemp published on the AAUS website Jun: CSS digital asset WalkWithWhales augmented reality filter campaign 5-30 June. Reached 4.9 million people on social media and appeared on billboards in major UK cities. Opened 5,500 times, with 123,200 impressions across Meta. Lnading page viewed 22,500 times. Jun: Al Jazeera online coverage of Bioturbation-athon (2.5k YouTube views) and potential audience of 430 million Jul: Theresa's blogs on the Pacific Row website Sep: first edition of CSS newsletter circulated to 49 subscribers Sep: Article by Annabel Kemp published in BSAC magazine (28,000 members) Sep: CSS citizen science featured in UK Blue Carbon Forum's September Newsletter (madi to find stats) Oct: CSS Digital Experience new website laucnhed Dec: Arran Expedition film released Dec: CSS newsletter circulated to ** subscribers |  | * Chris Levine artwork release on World Ocean Day 8th June |  | Jan: Arran Expedition film released Jan: CSS newsletter circulated to ** subscribers
|  |  | O.4.4 | Outreach activities and events (workshops, conferences, presentations) |  | Outreach tools | 4.2.2 | Recordings, attendence records |  |  | Nov 2021: CSS announced at COP26, Glasgow | 4 | Nov: Presented at COP27 Nov: Fishmongers Hall Launch Event, London Nov: Blue Marine Parliamentary Reception, Downing Street Dec: UN Biodiversity Conference (COP15), Montreal |  |  | 5 | Feb: Presented at World Ocean Summit, Apr: George Duffield Convex Conversation podcast May: Presented at Convex Town Hall Meeting Jun: Presented at Brilliant Minds event, 20 attendees Jul: Urbanization, Water and Food Security Conference in Tuscany, 80 delegates Sep: Presented at Shakleton Conference, 30-40 attendees Sep: Presentation by Gabriella Gilkes in keynote for British Science Festival, Exeter - 30 attendees Sep: Sophie Ward presented a poster at the Shelf Sea Oceanography workshop (50 attendees). Sep: Mud and Mixology event for the British Science Festival, Exeter - 35 attendees Oct: Blue Carbon Fourm event, London, G. Fordham/B.Harris
|  |  | O.4.5 | Educational tools and activities produced by encounter Edu | Anna to update with new contract | Outreach tools | 4.2.2 | URL links to online resources, attendence records, presentation decks. | There is unmet demand for ocean-climate education in UK schools and globally. Science is adapted appropriately for a younger audience. Materials delivered are accurate and attractive. | NA | NA | NA | NA |  | Education year one contract - 5 live lessons, 1 animation, 4 lesson plans and a suite of teaching resources. | 26161 | Jan: Diagrams and Activities, Ocean carbon cycle Jan: Lesson Plan (KS2, KS3, KS4), Ocean and climate science Feb: Live Lesson Women on the frontiers of climate science - 2,040 viewers Mar: Live Lesson Seabed safari - 13,728 viewers Apr: Live Lesson How do we knoe about climate change? - 3,693 viewers May: Live Lesson Teaching ocean and climate PD - 2,500 viewers Jun: Live Lesson Whales, carbon and climate - 4,055 viewers Jul: Infographihc, Ocean, carbon and climate Jul: Infographics and Activities, Ocean life Jul: Lesson Plan (KS2, KS3), How is life adapted to ocean habitats? August: Meetng with Encounter Edu about Y2-5 plans September: Confirmation of upcoming lesson content from Encounter Edu, budget confirmed Dec: Live Lesson COP28 Review and Q&A
|  |  | O.4.6 | Number of schools and students engaged | 5.5 million students 1000 schools | Beneficiaries | 4.1.2 | Statistics provided by Encounter Edu | Statistics are accurate and evidenced. |  |  | 0 | NA |  |  | 26016 | 26,016 students reached, across 282 schools and 21 countries
|  |  | O.4.7 | Stakeholders reached directly through messaging |  | Stakeholders | 4.2.1 |  |  |  |  | 1150 | Nov: COP27, 1000 attendees Nov: Fishmongers Hall, 150 attendees Nov: Blue Marine Parliamentary Reception, 80 attendees Dec: UN Biodiversity Conference (COP15), 3,000 attendees Out of The Blue had, 80 attendees (what and when was this?) |  |  | 25261 | The World Ocean Summit, Lisbon, 200 attendees 'Human impacts on marine functional connectivity' 80 attendees Podcast with Dr Callum Robersts and George Duffield : 163 downloads Twitter engagement: 23000 impressions, 477 engagement and 134 followers. George Duffield presentation at Brilliant Minds event in Stockholm had 200 attendees Podcast: 163 downloads Twitter engagement: 7, 51 followers * Times Earth Summit, Bristol. G. Duffield spoke CSS on panel * COP28, Blue Economy Dinner at Jameel Residence Chris GB * COP28, Blue Marine/PML panel GG presented * COP28, Goals House round table, 35 attendees * COP28, GG presented in Blue Zone
|  |  | O.4.8 | Opportunities to see (OTS) i.e. frequency of media exposure | 33000000000 | OTS |  |  |  | 5000000000 |  |  |  | 7000000000 |  |  | OTS - *Gail to fill Specialist dive websites and magazines with reach of 20 million globally. BSAC has 23,000 members. World Ocean Summit, Lisbon, 18m sponsorship reach | 9000000000 |  |  |  | 7000000000 |  |  |  | 5000000000
|  |  | O.4.9 | Coalitions/working advisory groups etc formed - number of partner organisations | 11 | Partnerships | 4.3.1 | MoU |  |  |  | 11 | July: Project started, partnering with Exeter uni, |  |  | 2 | South african partner agreement signed KAUST agreement signed
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | A social media strategy is implemented across project channels (LinkedIn, Twitter, Facebook, Instagram, YouTube) and analystics data gathered |  |  | In Progress | Emma Nicol to guide. Hootsuite utilised for scheduling and metric tracking, progress achieved to be updated quarterly.
|  |  | A.4.2 | Other media content created e.g. articles, films, podcasts, newsletter |  |  | In Progress | Carbon mesocosm experiment filming completed in Nov '22, Exeter. Bioturbation filming completed in May '23 *awaiting output from Matt Jarvis
|  |  | A.4.3 | Project staff represent and present at events |  |  | In Progress
|  |  | A.4.4 | An education programme is developed and delivered, and engagement statistics monitored |  |  | In Progress | Anna Hughs and Hannah Le Broq to guide.
|  |  | A.4.5 | Communication and education metrics are compiled on a quarterly basis for reporting |  |  | In Progress
|  |  | A.4.6 | Relationships are built with external partners |  |  | In Progress
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest changing this to just schools/students/countries. How would we measure student knowledge increase? @Elyssa Quinton @Gabriella Gilkes @Gail Fordham Reply: Yes please, this is not clear
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Anna Hughes I'm changing this from 4.4.1 (Increase in knowledge) to 4.1.2 (Number of beneficiaries)! based on previous discussion
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there other further reaching impacts expected from this such as changes to policy/additional protected areas?
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do you have an aim for the number of people you're hoping to reach? Reply: We only have targets for OTS, but I don't think we have one for direct reach Reply: @Gail Fordham that's fine - I think this should here be considered things like number of people who have attended our events or presnetations on the project, rather than digital reach. this is a change from when this was first written so it is slightly confusing!
Note on R10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: OOTB I thought was in 2022? Or has there been one this year? @Gail Fordham Reply: Gabi said it was in February 2023....I'm not sure as it was before my time!
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have set this to zero as it's a contractual partnership which is slightly different from the intent of the impact indicator Reply: @Appin Williamson Understood, I'll remove these then, agreed it's not impact. Trying to think what would count towards this... capacity building with local partners? Reply: @Gail Fordham Looking at this, I actually wonder whether we keep it in and list all the partners we're working with on this project, so I might disagree with my original comment - shall we discuss on teams or a call maybe? Reply: Great, I've got some other questions anyway!
Note on R12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gail Fordham even though this says 6 it looks like just 3 so I am changing from 6 to 3 Reply: Hi Sorry, OceanX and Fugro dragging on and still not confirmed, but these two are firm. Reply: Thanks Gail - that makes sense - do you have the name of the south african partner listed here?

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025 |  | Progress Planned in 2026 |  | Progress achieved in 2026
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [13 empty] | Impact Indicator Tracking
[17 empty] | Defined in original outputs |  |  |  |  | Unplanned |  |  |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved in Y4 | Planned for Y5 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2024 | Progress achieved in 2025 | Progress achieved in 2026 | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2024 | Progress achieved in 2025 | Progress achieved in 2026 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected
Output 1 | 1 | 5 | O.1 | O.1.1 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 1 | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 1 | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 9 | 13 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 3 | 7 | O.2 | O.2.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 | O.3 | O.3.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0.4 | O.4.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.4 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
|  |  |  | O.4.5 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.6 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  |  | O.4.7 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.8 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.9 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.1.2 | 0 | 26016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26016 | 0 | 26016 | 0
[16 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.2.1 | 1150 | 25261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26411 | 0 | 26411 | 0
[16 empty] | 4.2.2 | 4 | 26175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26179 | 0 | 26179 | 0
[16 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.3.1 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 13 | 11
[16 empty] | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0