## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). |  | 1 | BLUE's M&E Guide.pdf
|  | 2 | Logframe Instructions and Examples
|  | 3 | Example logframe
|  | 4 | Impact Indicator List
Notes to the Solent team:
Outputs 1-5 relate to the are equivalent to the 5 ELSP SSP outcomes and include the short term outputs listed in table 2 of our ELSP logframe matrix and in being monitored in section 2 of our annual report that we are using to monitor project progress., coming out of Outcomes 1-5 in the monitoring framework (explained below). These Outputs are outlined in the Logical Framework Matrix, underneath the table out Outcomes. update to explain section in the Logical Framework Matrix | 00. Logical Framework Matrix 24AUG22.docx Add Annual report section 2
The 'Impact and Outcome' tab relates to the 5 Outcomes (and the respective 15 measurable indicators) we are using to monitor in our Monitoring framework, for which we are producing a baseline report in April 2024. | ELSP Guidance

## Key Updates
Month | Date | Activities | Comments/links
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01 | 6th - 10 June | ELP stage 3 projects workshop - Cambridge
2022-08-01
2022-09-01 |  | Plan Vivo accept project as a pilot study for biodiversity credits
2022-10-22 | 26th-30th Oct | ELP knowledge exchange visit - Nature Positive Enterprises - Gokova Bay, Turkey | Louise attended on behalf of partnership
2022-10-01 | 31st Oct | Partnership agreement signed by all partners
2022-11-01 | 30th Nov | ELP Annual Grantee meeting (Zoom) | Louise attended on behalf of partnership
2022-11-01 | 22nd-23rd Nov | Seascape Symposium - ZSL | Jo Preston announced Solent Seascape Project
2022-12-01 | 15th December | EA post blog about project on gov.uk website | https://environmentagency.blog.gov.uk/2022/12/15/restoring-sealife-in-the-solent-a-5-million-5-year-project/
2023-01-23 | 31st Jan | On-line meeting with MMO licensing CEO (Trudi Wakelin) | Blue Marine invited to join the "Step back project" - representing restoration practitioners in MMO project to reflect on current licensing regieme and how it could be improved.
2023-01-01 | 10th Jan | Project Kick off meeting - Eames Farm
2023-02-23 | 20th-24th Feb | BUDS trial - saltmarsh restoration - Itchenor | Led by CHAPRON in collaboration with Land & Water - funded by ELP / EHI
2023-02-01 |  | Eric (Oyster Officer) joined Blue Marine
2023-03-01 | 15th Mar | Solent Forum meeting (Royal Maritime Club - Portsmouth) | Louise presented project to Solent Forum members
2023-03-23 | 27th-30th Mar | Hamble Oyster Reef build | SSP_River Hamble Foundation_Coverage.xlsx
2023-04-01 | 12th-13 April | HRH Princess Eugenie visit | https://www.hellomagazine.com/royalty/490062/princess-eugenie-reveals-why-motherhood-inspired-passion-project/
2023-05-01 |  | Coupelles deployed | check date with Eric
2023-06-23 | 19th June | Dive survey on langstone reef unable to find any live oysters | Log of Langstone survey work and events.pptx
2023-06-01 | 19th Jun | Rosalie (Project Co-ordinator) joined Blue Marine
2023-06-01 | 14th June | Jo P (UoP) presented the project to Crown Estate at HQ in London to stakeholders
2023-06-23 | 21st June | Blue Marine formally invited to join Southern Water ICEG | Independent Climate and Environment Group - advise / scruitinise SW
2023-06-23 | 6th Jun | Louise presented project to national teams at EA in "Lunch & Learn" | 49 national EA staff attended
2023-07-01 | 6th-7th Jul | ELP Team (Sarah, Taylor and Tundi) visited Solent and met partners
2023-07-23 | 11th Jul | Rememare Conference - Scarborough | Louise presented lessons learned in project so far to 250 restoration practitioners
2023-07-23 |  | ELP Knowledge Exchange - Greater Coa Valley | Emily Stroud attended on behalf of partnership
2023-07-23 |  | BUDS film released on SSP YouTube channel
2023-08-23 | 3rd Aug | Secretary of State Therese Coffey visited BUDS trial in Itchenor
2023-09-23 | 14th Sept | Nature Recovery Network - Priority Place | NE informed us that the Solent has been chosen as a "priority place", empowering NE staff to choose how to make the biggest and best difference for nature in this region
2023-09-23 | 19th Sept | Inception meeting - R4C | Meeting to finalise details of stakeholder engagement plan
2023-09-01 | 26th Sept | Accessing carbon finance for nature restoration in Europe workshop (ELSP, UNEP-WCMC, F&F) | Rosalie, Maddie and Kaija (Blue Marine) attended this workshop in Cambridge
2023-09-23 | 28th Sept | NSNNR site visit | Louise visited NE team at site to discuss rafts/islands project change request
2023-09-01 | 29th Sept | Seabird nest site restoration begins - Farlington Marshes | Collaboration between HIWWT / RSPB - funded by LIFE
2023-09-01 |  | Proposal from ABPmer agreed by partners at SRP WG | Proposal to create data portal / SoN
2023-09-01 |  | Proposal from Wayforward agreed by partners at SRP WG | Proposal to create project comms strategy
2023-10-01 | 3rd Oct | Greater Solent Priority Place Team Day | Louise attended site visit on behalf of partnership
2023-10-01 | 11th Oct | Solent Forum meeting (NOC- Southampton) | Louise presented project to Solent Forum members, Rosalie Jenny and multiple partners in attendance
2023-10-01 | 17th Oct | Plan Vivo biodiversity credit webinar, Solent Seascape Project presented, survey released | Rosalie presented the Solent project to 70+ attendees of the live webinar, recording now available publically, survey released
2023-10-01 | 24th Oct | ELSP Knowledge Exchange - Cairngorms Connect | Rosalie and Zoe M attended this KE trip on behalf of partnership, focused on science and monitoring
2023-11-01 | 1st Nov | SORP extraordinary meeting | TWG convened to give advice on way forward with reefs following Langstone data
2023-11-01 | 13th Nov | Rivers Action event, Conduit Club London | Rosalie attended the event and spoke with Charles Watson, who is interested in teaming up with SSP
2023-11-01 | 17th Nov | Hayling Nature Reserve visit | Louise, Wez, Fay and others attended a trip to discuss the site in Langstone
2023-11-01 | 22nd Nov | EHI funders meet HIWWT, UoP and RSPB at IMS | Wez, Jenny B, Jo P, Louise and Sam F attend the meeting with EHI at IMS
2023-11-01 | 22nd Nov | Hampshire CC LNRS development meeting | Jenny Murray attended
2023-11-01 | 30th Nov | Year one celebration, all partners | Event at staggeringly good brewery in Portsmouth
2023-12-01 | 4th Dec | ELSP Annual Grantees meeting | Louise and Rosalie attended. SSP won the ELSP Recognition Award for biodiversity credits work
2023-12-01 | 19th Dec | EHI match funding confirmed
2023-12-01 | 6th Dec

## Impact and Outcome
Impact | Protect and restore at least 30% of the Solent seascape, based on historical records. At this level, we will tip the balance of the Solent seascape from a degraded state to a naturally expanding, connected and productive ecosystem.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | 1 | A long term seascape recovery plan has been co-created and implemented with key stakeholders supporting the better management of existing Solent habitats | 1.1 | 1.1 Number of partners/ policy/stakeholders engaged with the development and delivery of the seascape recovery plan. | 1 |  |  | Monitor number/ type of partners and stakeholders participating in working group meetings during co-design of seascape recovery plan. This will be monitored using existing ongoing Habitat mapping & monitoring where possilbe: Seagrass: Seagrass extent & shoot density Saltmarsh: extent Changes in total saltmarsh and intertidal seagrass area will be monitored using habitat mapping by drone with LiDAR via existing iniatives. Natural England condition assessments to monitor unfavourable – favourable condition within designated sites in the long term | Stakeholders are willing to engage and adopt a seascape plan. It is assumed that a seascape plan will allow anthropogenic pressures to be reduced or removed, slowing the rate of degradation of marine and coastal habitats.
|  |  | 1.2 | 1.2 Area of habitat with improved condition through passive restoration and reduction of pressures
| 2 | Key marine and coastal habitats are being actively restored, increasing habitat extent and catalysing recovery across the wider seascape, improving ecological connectivity. | 2.1 | 2.1 Area and condition of seagrass and saltmarsh habitat. | 2 |  |  | Area and density of oyster reef habitat will be assessed using sidescan sonar coupled with GPS and ground-truthed with drop down video surveys. Oyster recruitment will be assessed using benthic collectors during the spawning season to monitor spat settlement. Oyster size frequency will be assessed using grab sampling methods of oysters and cultch, where morphometric measuresments of oysters will be taken. Benthic spat collectors deployed for 15 – 21 days at intervals between June an September. 50 oysters, collected from each reef site, will be measured (height, length, width) annually. Presence, abundance and species of fish, mobile shellfish and birds across saltmarsh, seagrass, and oyster reefs will be quantified using relative abundance measure based on maximum number of given species in a single frame during a 30 min deployment. Biomass and life history stage assessed via length of key species calibrated from BRUVs. Small fish species and abundance will be monitored at selected sites across the seascape via seine nets surveys using TRaC methodology. eDNA analysis will monitor the fish species present in the Solent throughout the lifetime of the project. A large-scale network of acoustic receivers will be installed at key locations throughout the Solent. Commercial fish species at different life stages, and some species of shark and rays will be fitted with acoustic transmitter tags and their movements will be tracked throughout the area to understand which areas and habitats, and during what seasons, these waters provide refuge for these species | Area of habitat to be restored to depend on site suitability and marine licence/ consenting processes. The majority of the Solent is designated therefore considerations are needed to ensure any recovery of certain habitats / species do not pose detriment of other designated features. Restoring marine and coastal habitats across the seascape will improve the connectivity for marine species that utilise the habitats (e.g. fish and birds)
|  |  | 2.2 | 2.2 Oyster habitat area and oyster density
|  |  | 2.3 | 2.3 Oyster recruitment and size frequency
|  |  | 2.4 | 2.4 Habitat use by mobile fauna (fish & transient molluscs/crustaceans)
| 3 | Ecosystem service benefits from restoration are increasing across the landscape, creating an evidence base of the wider benefits of seascape restoration. | 3.1 | 3.1 Marine biodiversity associated with target habitats (sp. Richness and abundance) | 3 |  |  | Water samples and benthic sediment samples will be taken from reference, control, and restoration sites, before and after restoration activity for eDNA metabarcoding analyses. Breeding abundance and productivity monitoring conducted using Seabird monitoring handbook for Britain and Ireland 1995 on an annual basis TRaC surveys as outlined in NFPD: TraC (Transitional & Coastal waters) fish survey relational datasets - data.gov.uk using seine nets. Species will be identified, and measurements taken. Sediment and biomass samples collected using cores. Living biomass and sediment carbon stock content will be measured for seagrass and saltmarsh. Water clarity will be assessed using light sensors and water quality will be assessed using Ex02 sondes to measure chla concentration and TSS continuously within the 3 harbours across the Solent. Changes in N concentration will be monitored seasonally using sonde data. Sediment nitrogen content will be quantified using total organic nitrogen analyser. Water nutrient concentration will be determined by continuous segmented flow analyser. | Restoring marine and coastal habitats at seascape scale will have quantifiable ecological benefits - increase associated biodiversity, sequester and store carbon and mitigate nutrient inputs.
|  |  | 3.2 | 3.2 Seabird abundance and productivity
|  |  | 3.3 | 3.3 Diversity and biomass of juvenile fish
|  |  | 3.4 | 3.4 Carbon stock assessment
|  |  | 3.5 | 3.5 Water quality and clarity assessment
|  |  | 3.6 | 3.6 Nutrient fluxes (N & P)
| 4 | The potential to upscale seascape restoration is improved through policy advocacy and development of financial mechanisms | 4.1 | 4.1 Number of organisations which have bought into stacked credit scheme | 4 |  |  | Count the number of organisations, interested, committed, and paid into the scheme. | This indicator is partially reliant on the level of increase on biodiversity, carbon and nitrate indicators.
| 5 | Local communities are engaged with and involved in the project. Positive behaviors are adopted by key stakeholders to reduce pressures on seascape habitats | 5.1 | 5.1 Number of individuals and communities reached through project education and engagement activities. | 5 |  |  | Count of volunteer numbers, hours spent, training sessions attended, and activities supported. Count of individuals and communities engaged with. Before and after interviews conducted with key stakeholders. Standard questionnaire and interview questioned developed to allow comparisons between stakeholders. | Communities are interested in being involved/ engaging with the project from the beginning. Community involvement will increase positive behaviours.
|  |  | 5.2 | 5.2 Reported rates of different behaviours

## Output 1
Outputs |  |  | Indicators | [7 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Description | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024
6 | [10 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Outcome one outputs | O.1.1 | Existing data colated for the Solent and presented in GIS map, providing the evidence base for the Solent’s ‘status of health’. Data colation exercise to include habitat extent data, existing monitoring project data on species abundance, condition etc, information on pressures e.g. fishing, recreational disturbance etc, and landownership boundaries. Data mapping used to identify gaps and provide baseline for developing co-designed vision. | Number and range of stakeholders providing data to develop GIS map with layers including land ownership, pressures, habitat extent and condition |  | Map | NA | GIS map | Data is available for all elements and layers of the map | [9 empty] | Map completed |  | Data portal commissioned for 2024, data currently being collected |  | Published in September 2023
|  |  | O.1.2 | ‘State of Nature’ report for the Solent published following data mapping exercise published. | Report published | 1 | Report | 2.1.1 | ‘State of Nature’ report | .Report effectively illustrates the Solent habitats / wildlife are in a degraded state | [9 empty] | Report published |  | Blue Marine have commissioned ABPmer to create the report, anticipated to be completed in September 2024 | 1 | Published in September 2024
|  |  | O.1.3a | Public facing ‘restoration projects’ story map developed to showcase existing projects and initiatives addressing pressures in the Solent | Number of visits to the on-line story map |  | Stakeholders reached | 5.3.1 | On-line story map proof of visit numbers | Appropriate and accessible on-line host for the map can be found Number of visits to the map can be measured | [9 empty] | Story map published |  | Website and interactive map still in development |  | Story map published
|  |  | O.1.3b | Public facing ‘restoration projects’ story map developed to showcase existing projects and initiatives addressing pressures in the Solent | Story map released | 1 | Outreach tool | 5.3.2 | On-line story map | [10 empty] | Story map published |  | Website and interactive map still in development | 1 | Story map published
|  |  | O.1.4 | Cross-sectoral collaboration developed to co-design the Solent vision for recovery | Number and range of stakeholders engaged in co-designing the vision |  | Stakeholders reached | 5.3.1 | Vision document | All sectors in the Solent are willing to collaborate | [9 empty] | Completed collaborative Seascape Recover Plan vision development |  | Key stakeholder groups identified in partner mapping workshop, stakeholder engagement process to start in the New Year |  | Stakeholder engagement process for Seascape Recovery Plan vision completed
|  |  | O.1.5 | Co-designed vision and seascape recovery plan for the Solent developed | Number of recovery plan meetings and workshops Number and range of stakeholders that engage in the co-design and endorse the recovery plan for the Solent | 1 | Plan | 2.1.1 | Recovery plan document Meeting minutes | [10 empty] | Co-design process started |  | Blue Marine have commissioned Resources for Change to begin the stakeholder engagement and co-design workshops in 2024 |  | Co-design process continued, one-on-one held interviews with key stakeholders, group workshops/activities held once the State of Nature report and data portal is ready. Behavioural change work (led by HIWWT) feeds into the plan
Activities
| Activity Code |  | Indicator Code | Description |  |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pending update
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Louise MacCallum and @Rosalie Wright please note that I have added another line in here, turning this into 1..3a and 1.3b - one for the number of visits, one for the actual creation of the story map in the first place

## Output 2
Outputs |  |  | Indicators | [7 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Description | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024
4 | [10 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Outcome two outputs | O.2.1 | Priority areas within Solent suitable for active restoration identified, including each area’s potential to contribute to connectivity and recovery of areas away from the site of active restoration. | Appropriate restoration areas identified |  |  | NA | Priority restoration area document | Sites suitable and available for restoration exist | [9 empty] | Decide restoration sites, survey habitat extents and obtain consents for active restoration work |  | Sites identified for seagrass (Priory Bay and Thorness), saltmarsh (potential at Langstone, Medina, Western Yar), bird nesting sites (planned work at 14 sites by RSPB and North Solent NNR by NE). Oyster restoration sites awaiting confirmation. |  | Partners to confirm further saltmarsh restoration sites (Coastal Partners, IoWEP), managed realignment at Thorness. Blue Marine plan oyster reef restoration sites at Chichester RSPB confirm restoration methods at the 14 sites outlined in 2023. NE decide on restoration methods for North Solent NNR. Seagrass restoration precise sites confirmed.
|  |  | O.2.2 | Active restoration including seagrass/salt marsh planting, cultch relaying, oyster brood stock enhancement, and sea bird shingle habitat deployment over: 7ha (seagrass), 8ha (salt marsh), 4ha (oyster habitat), 2ha (seabird habitat). | Area of key habitat under active restoration | 0.21 | km2 | 2.2.1 | Maps Photos | The relative hectarage of habitat for each key habitat type is available for restoration | [9 empty] | Seabird, saltmarsh, oyster reef restoration takes place. Seagrass seed collected | 0.0049 | 0.0025 of oyster reef in the River Hamble (April 2023) 0.0024 of saltmarsh at Itchenor (February 2023) 2 shingle islands restored and 2 new islands created at Farlington (October 2023) |  | Active restoration of seabird habitat at multiple sites from early 2024 onwards. Active restoration trial of seagrass restoration at Calshot (HIWWT) using overwintered seed, Spring 2024 Active restoration trial at Priory Bay and Thorness using transplanted seagrass fragments (Project Seagrass), Spring 2024 Active restoration of saltmarsh at Langstone, Medina Partners, IoWEP), managed realignment at Thorness. Blue Marine restore further oyster reefs in the River Hamble and Langstone in late Spring
|  |  | O.2.3 | Multispectoral camera analysis technology will be tested as an innovative mechanism to map extent and changes in marine habitats (particularly seagrass, saltmarsh and algal mat coverage) at scale. | Habitat extent and change over time is mapped using camera |  |  | NA | Photos Reports |  |  | no longer happening
|  |  | O.2.4 | Salt marsh plant “plugs” will be added to sediment retention structures at trial sites to kick start colonisation. | Number of plugs “planted” in areas of restored sediment |  |  | NA | Photos of restored saltmarsh | Salt marsh plant plugs are available in required numbers | [9 empty] | Plugs planted |  | Not yet planted due to team capacity issues. |  | Start trial in early 2024.
Activities
| Activity Code |  | Indicator Code | Description |  |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1
A.2.2
Note on W5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Rosalie Wright this is great - could you list the months against when each of these were done?

## Output 3
Outputs |  |  | Indicators | [7 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Description | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024
4 | [10 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Outcome three outputs | O.3.1 | Quantitative assessment of the impact of protection/management and restoration initiatives on: habitat recovery, biodiversity enhancement, ecosystem service delivery including water quality, nutrient cycling, and blue carbon. | Assessment complete | 1 | Report | 2.1.1 | Assessment report | [10 empty] | Baseline data collection ongoing. Central monitoring system established. UoP and Blue Marine monitoring lead oversee partners monitoring efforts |  | Still collecting baseline data. Central Monitoring System completed |  | Continue collecting baseline data and monitoring of active restoration, control and protection sites Final baseline data report produced April 2024
|  |  | O.3.2a | Reporting and active outreach with the international restoration community on lessons learned regarding seascape scale, multi-habitat restoration and protection initiatives. | Number of participants attending the Seascape Scale Restoration Conference |  | Stakeholders reached | 5.3.1 | Conference report | [10 empty] | n/a |  | n/a |  | Conference will be hosted in Spring/Summer 2024
|  |  | O.3.2b | Reporting and active outreach with the international restoration community on lessons learned regarding seascape scale, multi-habitat restoration and protection initiatives. | Number of events | 1 | Outreach activities | 5.3.2 | Conference report | [10 empty] | Initial planning started |  | Planning started for a Seascape Conference | 1 | UoP and Blue Marine (with ZSL, WWF and CEH) organise a second Seascape Conference following on the ZSL London one, November 2022. Likely to be held in 2024
|  |  | O.3.3 | Peer reviewed publications outlining impact of habitat setting on delivery of ecosystem services. | Papers published in open access journals |  | Papers | 2.1.1 | Scientific community utilising published research | Research produces publishable work | [10 empty] | 2 | Publication plan and timeline are currently in development for primary data collected under SSP. Papers informed by the project and published in 2023 include: - zu Ermgassen, P.S.E., ... Colsoul, B. (2023). Overcoming Ostrea edulis seed production limitations to meet ecosystem restoration demands in the UN decade on restoration. Aquat. Living Resour., 36, 16. DOI: https://doi.org/10.1051/alr/2023012 - Hughes, A., Bonačić, K., … zu Ermgassen, P.S.E. (2023). Site selection for European native oyster (Ostrea edulis) habitat restoration projects: An expert-derived consensus. Aquatic Conservation: Marine and Freshwater Ecosystems. https://doi.org/10.1002/aqc.3917 |  | Seascape paper (Jo Preston lead author) submitted to Nature Ocean Sustainability journal special issue. Publication plan and timeline developed
Activities
| Activity Code |  | Indicator Code | Description |  |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1
A.3.2
A.3.3
A.3.4
A.3.5
A.3.6
z
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same here - split into number of events held and then people reached
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should this be number of events? Reply: @Rosalie Wright no this is correct, but actually the one below should be number of events so I will change now Reply: thank you!

## Output 4
Outputs |  |  | Indicators | [7 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Description | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024
5 | [10 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Outcome four outputs | O.4.1 | Case studies provided to policy makers on barriers to restoration | Number of case studies |  |  | 1.1.2 | Case study document | Policy makers are wiling to consider case studies | [10 empty] | 2 | Shared case study template with all partners in July. UoP returned two case studies in August 2023. |  | Collect licensing case studies from all partners conducting active restoration
|  |  | O.4.2 | Engagement with wider initiatives e.g. ReMeMaRe to support with developing restoration licensing processes that support restoration projects. | Number of meetings / conferences attended with wider UK restoration initiatives |  |  | 5.3.2 | Meeting reports | [11 empty] | 20 | Blue Marine Foundation team attended ReMeMaRe. (July) and Louise gave presentation on project. Project partners have attended numerous meetings/conferences, including: ReMeMaRe (Jul 2023); ELSP Accessing carbon financing for nature restoration (Sep 2023); Meeting with LIFE Recreation Remedies to look at possibility to join-up (Aug 2023); Seascape project presented at ZSL conference on ecological connectivity (Nov 2022); Coastal Futures (Jan 2023); Saltmarsh Specialist Forum (Jun 2023); FSBI: Fish Ecology in a Changing Climate Conference (Jul 2023); Estuarine & Coastal Sciences Association Conference 2023; Ocean Action Conference (Jun 2023). In addition, partners attend the following meetings/ groups on a regular basis: Solent Forum; Sea the Value; UK Seascape Restoration Research Network; Three Harbours Project, Interreg RaNTrans project; Hurst to Lymington coastal strategy; Thorney Island Conservation Committee; Langstone Harbour Advisory Committee; Habitat Compensation and Restoration Programme; Local Government Authority SIG; Noltii Forum |  | Coastal Futures, possibly the Ocean Decade conference in April, will continue planning the Seascape conference with CEH and ZSL
|  |  | O.4.3 | Solent seascape project joined up with Local Nature Recovery Strategies. | Number of meetings attended to develop the Solent LNRS |  |  | NA | Meeting reports | LA’s choose to include marine habitats in LNRS | [10 empty] | 27 | Blue Marine had five meetings with Hampshire County and Isle of Wight (IoW) councils to discuss incorporating marine elements into LNRS. Blue Marine is co-delivering Solent Marine workshops with the Solent Forum to embed marine ecosystems into IoW and Hampshire County councils LNRS. CHaPRoN attended regular meetings (a total of 12) with West Sussex Council about their LNRS and attended two meetings with Hampshire County Council. HIWWT attended eight monthly meetings as part of the Local Nature Partnership where Hampshire CC and IoW Council update on LNRS plans. Joined two steering meetings with Hampshire CC as members of the LNRS steering group. EA attended the Southeast Local Nature Partnership to discuss and support the inclusion of coast and marine into LNRS. IoWEP attended a discussion on the development of the Isle of Wight LNRS |  | First workshop will be in January with the Hampshire CC, draft shared in Spring.
|  |  | O.4.4 | Development of stacked credit schemes to enable local authorities, councils, communities or organisations in the UK to understand the potential benefits (in terms of carbon, biodiversity and nitrate removal) of any given seascape when restored. | Quantified model for stacked credit scheme produced | 3 |  | NA | Credit scheme documents | [11 empty] | 1 | Confirmed as one of seven pilot projects for a biodiversity credit scheme with Plan Vivo, started monitoring programme. Attended a workshop by ELP on accessing carbon financing for nature restoration in September. | 3 | Biodiversity credit monitoring and scheme established with Plan Vivo, develop stacked scheme with carbon and nitrate benefits
|  |  | O.4.5 | Publication of a report, including Blue Carbon that will feed into the development of carbon codes in the UK. | Report published | 1 |  | 1.1.2 | Report document | Blue carbon sequestration / storage is measurable in restored marine habitats | [11 empty] | n/a |  | Planned for 2026.
Activities
| Activity Code |  | Indicator Code | Description |  |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1
A.4.2
A.4.3
Note on W4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Rosalie Wright just to double check - are these new documents that have been created for this? Or were these some pre-existing docs? Reply: new documents created for this project
Note on W5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rosalie Wright if I could do a chefs kiss here I would Reply: hahaha I suggest the new logframe set up has that option

## Output 5
Outputs |  |  | Indicators | [7 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Description | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024
7 | [10 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Outcome five outputs | O.5.1 | Report on audience mapping, identifying the key barriers to participation and outlining key messages and interventions to promote engagement and behaviour change. | Report published |  | Reports | 5.1.1 | Report | Solent audience is able to be mapped | [10 empty] | 0 | First behavioural change workshop has been hosted. Resources for Change are leading the community engagement and behavioural change work. Consultant has been hired to complete a project communications strategy with the resulting key messaging/behavioural change information. | 1 | Report completed and published
|  |  | O.5.2 | Active and informed volunteer network participating in project initiatives and supporting education and outreach. | Number of volunteers actively engaging in the network |  | Stakeholders | 5.3.1 | Volunteer registers | [11 empty] | 162 | Volunteer steering group set up by HIWWT in September, 27 attendees so far. oyster volunteering numbers: 135 as of November 2023. | 500 | Volunteer strategies and roles developed. Space for 500 over the course of 5 years
|  |  | O.5.3a | Outreach and education materials developed and displays installed in educations hubs with project partners. | Number of schools using Education materials produced |  | Schools | 5.5.2 | List of schools | [11 empty] | 0 | Materials in development |  | Materials developed
|  |  | O.5.3b | Outreach and education materials developed and displays installed in educations hubs with project partners. | Number of students using Education materials produced |  | Students | 5.5.1 | Attendee lists? | [11 empty] | 0 | Materials in development |  | Materials developed
|  |  | O.5.3c | Outreach and education materials developed and displays installed in educations hubs with project partners. | Number of displays installed | 1 | Educational packages | 5.5.3 | Education materials | [11 empty] | 0 | Education materials (e.g. banners) have been created and more are in design to reach target audiences and convey key messages. HIWWT are developing learning materials for volunteers to upskill them, e.g. as Inspiring People Marine Champion, Citizen Science Marine Champion and Seagrass Leader. |  | Materials developed
|  |  | O.5.4a | Impact film showcasing the project and its impact. | Number of people who see the film(s) on-line is recorded |  | Stakeholders | 5.3.1 | Stakeholders reached | Volunteers are attracted to the project | [10 empty] | 2017 | Saltmarsh restoration film: 1.7k Seascape introduction film: 317
|  |  | O.5.4b | Impact film showcasing the project and its impact. | Number of people who see the film(s) at screenings is recorded |  | Outreach activities | 5.3.2 | Film(s) produced | Volunteers are attracted to the project | [10 empty] | 0
Activities
| Activity Code |  | Indicator Code | Description | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on W4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Rosalie Wright Is this behavioural change workshop something that we held? If so we can count it as an outreach activity somewhere ☺️ Reply: this was held by our partners HIWWT for SSP - would that count? our other community engagement activities are in this list too: 5.1. Number of individuals and communities reached through project education and engagement activities.xlsx
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: update indicator naming Reply: it is now: Number of displays installed using Education materials produced , condense the three related
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As I have added this in, it's not in the original plan - but this is more aligned to what you would use to verify the indicator outlined in the text
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As I have added this in, it's not in the original plan - but this is more aligned to what you would use to verify the indicator outlined in the text

## Output 6 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 |  | O.6.1
O.6.2
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 |  | O.7.1
O.7.2
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 |  | O.8.1
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Partners Funders
Outcome | Output | Partner | Funder
1 | O.1.1
O.1.2
O.1.3
O.1.4
O.1.5
2 | O.2.1
O.2.2
O.2.3
O.2.4
3 | O.3.1
O.3.2
O.3.3
4 | O.4.1
O.4.2
O.4.3
O.4.4
O.4.5
5 | O.5.1
O.5.2
O.5.3
O.5.4

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5.1. Number of individuals and communities reached through project education and engagement activities.xlsx

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected
Output 1 | 6 | 10 | O.1 | O.1.1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 4 | 8 |  | O.1.2 | 0% | 0% | 0% | 0% | #VALUE! | 0% | 0% | 0% | 0% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 4 | 8 |  | O.1.3a | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 5 | 9 |  | O.1.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 7 | 11 |  | O.1.5 |  | 0% |  | 0% |  | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | 0% | 2.333% | 2.333% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | O.2.2 | 0% | 0% | 0% | 0% | #VALUE! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | 0% | 0% | 0% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.2.4 |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 | O.3 | O.3.1 | 0% | 0% | 0% | 0% | #VALUE! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2a | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.4 |  | 0% |  | 0% |  | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  |  | O.4.5 |  | 0% |  | 0% |  | 0% | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.3a |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0