## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact | Ensure better protection of 444,916km2 of ocean (six per cent of the UK’s marine estate) and demonstrate how a local, small-scale fishery can work alongside marine protection to improve livelihoods while also improving conservation outcomes.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | Enhance the Category VI MPA to include highly protected zoned areas, build local capacity, increase ocean literacy and champion conservation action among the St Helena community. | OC.0.1 | Become one of the largest and most effectively managed sustainable use MPAs in the Atlantic | 1 | 1.4.1 | 1.4 | Reports outlining monitoring findings | St Helena Gvoernment, UK Foreign Office and UK Government Agencies are receptive to implementing policy changes Local community are receptive and engaged with project
|  |  | OC.0.2 | Continue to enhance the Category VI MPA to include highly protected zoned areas | 2, 4 | 1.1.1, 1.3.1, 1.4.1, 3.4.1, 3.4.3, 4.2.1, 4.2.2, 4.3.1 | 1.1, 1.3, 1.4, 3.4, 4.2, 4.3 | Written evidence of new highly protected zoned areas
|  |  | OC.0.3 | Continue to build local capacity, increase ocean literacy and champion conservation action among the St Helena community | 3 | 4.1.2, 4.2.1, 4.2.2 | 4.1, 4.2 | Written evidence of local engagement and ocean champion support
| 1 | Appropriate Fisheries regulations enacted by the St Helena Government.
| 2 | A new marine management plan is completed and published by the St Helena Government.
| 3 | Support the St Helena National Trust Marine Team.
| 4 | Whale Shark research complete, to inform the revision of the marine management plan.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please review all means of verification and Important Assumptions (throughout all outputs as well)
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note - this doesn't seem to be covered within the outputs, so suggest this wording is either changed (although it's part of the Barclays plan) OR some wording is incorporated into the outputs

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Appropriate Fisheries regulations enacted by the St Helena Government. | O.1.1 | Evidence of Government and stakeholder liason |  | (number of recommendations submitted; meetings…) | NA - progress | Written copies of correspondence and meeting minutes including attendees | St Helena Government is open to dialogue and updates to fisheries management practices Evidence compiled encourages improved fisheries regulations | [6 empty] | 1 | Consultation feedback provided by Blue Marine and SHNT team on: Fishing Licence Policy - Fisheries Bill for Ordinance - Developments in the Marine Environment - Tourism & Accreditation Policy - Compliance & Enforcement Policy - Marine Species Interaction Policies
|  |  | O.1.2 | Number of reports/other evidence documents submitted to the Government on TACs/quotas; long lining; observer coverage; human labour etc. |  | Reports/ evidence documents | 1.4.1 | Copies of reports | [7 empty] | 2 | Consultations on Fisheries Bill included formal recommendations on: prohibitions on transhipment, destructive fishing, the dumping of inorganic waste at sea, forced labour; the need to use sustainable gear in exploratory work; the need for 100% observer coverage and effective scientific reporting; the need for regular stakeholder input into reviewing the SHG Big eye tuna science monitoring programme. Blue Marine and SHNT team sent evidence and TAC calculations to SHG and Elected Members, demonstrating appropriate quota and TACs based on: Cefas recommendations, previous scientific tagging rates and the precautionary approach
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Continue to work with St Helena Government and local stakeholders to ensure fisheries legislation is appropriately revised. This may include responding to the public consultation, assisting with requests for involvement in drafting, submitting evidence to the St Helena Government if requested |  |  | Complete | Fisheries legislation updated and enacted
|  |  | A.1.2 | Provide continued support for the St Helena Commercial Fishermen’s Association by leading the secretariat and coordinating input to the fisheries regulation process. To include: |  |  | Complete
|  |  | A.1.3 | Providing evidence to the Government to help them make evidence-based decisions when determining sustainable quotas and Total Allowable Catches (TACs) |  |  | Complete | fed into fisheries reviews and provided feedback
|  |  | A.1.4 | Helping to highlight the need to ensure that no longlining or fishing activities that are adverse to the IUCN Cat VI MPA takes place in St Helena’s waters in the interim period prior to the revised Fisheries Legislation being enacted. |  |  | Complete | No longlining permitted in StH waters - now in legislation
|  |  | A.1.5 | Assisting the Government with evidence of the need to utilise suitable fishing gear within ‘exploratory work’ and of the merits of full observer coverage on the seamounts. |  |  | Complete | continued advocacy work and letters sent to Governor
|  |  | A.1.6 | Working with UK and St Helena governments to ensure that forced labour and human trafficking is explicitly prohibited under any revised Fisheries Legislation and relating policy documents.
"1"
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please input here a rough estimate of the total expected over the lifetime of the project

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
8 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | A new marine management plan is completed and published by the St Helena Government. | O.2.1 | Scientific analysis conducted, identifying biodiversity hot spots that will be used to propose zonation |  | Number of hotspots identified under protection | 1.1.1 |  | Monitoring adequately identifies hotspots Stakeholders are open to engagement Universities and research partners are engagemend and receptive to partnerships UK Foreign Office, Government Agencies and St Helena Government receptive to meetings and policy change Local community engaged and receptive | [6 empty] | 0 | Work ongoing to use historic scientific data, anecdotal evidence and stakeholder workshops to identify 'biodiversity hotspots' which can then be included in any proposed zoning to enhance targeted spatial and temporal protection of species and habitats in St Helena's waters
|  |  | O.2.2 | Number of stakeholder consultation meetings conducted |  | Number of consultation events | 4.2.2 | [8 empty] | 1 | Stakeholder consultation meetings will ensure community buy in to any measures proposed, however, Blue Marine and SHNT Team completed MMP questionnaire and attended MMP Workshop in September 2021.
|  |  | O.2.3 | Number of University/research partnerships established |  | Partnerships | 4.3.1 | [8 empty] | 0 | Blue Marine and SHNT team will work with ZSL on a marine debris and plastic programme.
|  |  | O.2.4 | Number of management plans influenced/created/improved |  | Management plans | 3.4.3 | [8 empty] | 0 | Blue Marine and SHNT attended MPA management plan workshop and completed questionnaire |  |  | 1 | Marine Management Plan Approved (maybe Dec 22?)
|  |  | O.2.5 | Amount of evidence compiled and provided for the removal of long lining |  | Pieces of evidence | 3.4.1 | [8 empty] | 1 | Ordinance now legally prohibits use of anything other than pole ad line, droppers and dip nets. Blue Marine and SHNT fed into stakeholder input that made this happen
|  |  | O.2.6 | Number of meetings with UK Foreign Office, UK Government Agencies and St Helena Government conducted on marine management implementation |  | Meetings | NA - progress | [8 empty] | 12 | Regular meetings with FCDO Belt belt programme team lead and also with SHG Marine team management staff
|  |  | O.2.7 | Amount of community engagement events completed [if applicable for this output?] |  | Events | 4.2.2 | [8 empty] | 1 | Whale shark festival
|  |  | O.2.8 | Engagement levels across educational activities [reach, attendence rates, changes in support/awareness of marine conservaiton activities] |  | Stakeholders reached | 4.2.1 | [8 empty] | 300 | Marine team continues to host outreach and educational programmes to all local schools. Hosted the 4th annual Bone (whale) shark festival in February 2022, (currently the Trust’s biggest local fundraiser). The Festival focuses on the celebration of this iconic marine species; as one of the Islands ‘7 Wonders’ and one of our most identifiable links to the outside world and celebrates ‘what’s on our doorstep’ in our pristine and sustainable Marine Protected Area which surrounds us. >1000 attendees but 300 expected to be not reached via output O.3.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Work with the St Helena Government and local stakeholders to build the case for enhancement of the spatial and temporal management of the current MPA. This will be achieved by: - Using historic scientific data, anecdotal evidence and stakeholder workshops to identify ‘biodiversity hot spots’, which can then be included in any proposed zoning to enhance targeted spatial and temporal protection of both species and habitats in St Helena’s waters; - Stakeholder consultation meetings will ensure community buy in to any measures proposed. |  |  | Complete | Updated MMP - includes ability for spatial management where science indicates. No take zones around wrekcs
|  |  | A.2.2 | By using the current Marine Management Plan as a roadmap, through expert advice help the Government to identify where focused research is needed for key coastal fauna.
|  |  | A.2.3 | Engage with external research bodies/universities and St Helena Research Institute to help deliver research objectives. |  |  | Complete | whale shark research as core of SHNT, also now working on BRUV surbeys and other monitoring
|  |  | A.2.4 | Once this research – and any Government stock assessments are complete – this exercise will culminate in BLUE assisting in the development of tailored management plans for coastal fauna. |  |  | Complete | Bluebelt programme producing individual species annual assessments
|  |  | A.2.5 | Continue to provide evidence for the complete removal of long lining (and any other unsustainable fishing gears) within the revised Marine Management Plan. |  |  | Complete | Longlining prohobitied in fisheries legislation and updated MMP
|  |  | A.2.6 | Continue collaboration with UK Foreign Office, UK Government Agencies (MMO and Cefas) and St Helena Government to ensure timely and effective implementation. This will entail meetings with the relevant officials to update them on the evidence we have of progress – or lack of – towards a marine management plan that is appropriately revised and effectively implemented |  |  | Complete | continued engagfement with FCDO and also through GBO weekly meetings
|  |  | A.2.7 | Continue engagement with St Helena community around the importance of the MPA and why zoning and enhanced management measures are being developed – this transparency and engagement will encourage adherence to new zoning/rules and demonstrate the long term benefits to the community. |  |  | Complete | supported SHNT in advocacy work
|  |  | A.2.8 | Engagement will be conducted through tailored educational materials, our marine life mobile App, outreach events, newspaper articles, radio shows, and on social media. |  |  | Complete | lots social media, engagement, whale shark festival yearly etc
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you input the total estimate of each of these across the lifetime of the project (except O.2.6 as it's more a mark of progress)
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has this happened or it's going to happen?
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Marked as zero because a new management plan wasn't created, but there was some progress done towards it

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Support the St Helena National Trust Marine Team. | O.3.1 | Number of island-wide cleanups/pollution reduction programmes conducted |  | Outreach activites delivered | 4.2.2 |  | St Helena National Trust Marine Team remain in partnership with Blue Marine Foundation Social Media and other outputs fosters engagement with local community |  |  | 1 | Whale shark festival |  |  | 2 | SHNT conducted one beach clean with work experience students to demonstrate the important of how single use plastics effects our marine environment. However, following funding from ZSL, a marine plastics and debris program will commence soon. Trust team conducted oil spill pollution response training following SHG’s procurement of oil spill equipment. Team will continue training within this field by training for the OPRC OSR level 2 oil spill pollution response
|  |  | O.3.2 | Reach/engagement and wider impact of education intiatives 4.2.1 (knowledge/awareness change compared to baseline levels) |  | Stakeholders reached | 4.2.1 |  |  |  |  | 500 | Students |  |  | 510 | All local schools, (three primaries and 1 secondary) reached in year one, maintained in years two. Continued to build outreach with other local youth groups, which includes school holiday clubs, church lad brigade , Girl Guides. SHNT collating feedback to measure outreach, and impact school student numbers: (90-120 students each so assuming average of 105), 1 secondary school (300 students
|  |  | O.3.3 | Number of ocean champions supported |  | Number of beneficiaries | 4.1.2 |  |  |  |  | 200 | 4 schools access to marine education content |  |  | 30 | Believe and Achieve St Helena, a youth group dedicated to mentoring, inspiring year 9 students, (14 -15 yr. old) and offering career guidance currently studying their IGCSE examination.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Continue to fund the locally staffed Marine Team, housed within the St Helena National Trust. Duties include: |  |  | Complete | secured JE funding for SHNT for 3 years. Darwin funded plastic programme funds core staff
|  |  | A.3.2 | Island-wide plastic clean-ups and pollution reduction programmes |  |  | Complete | As part of Darwin plastics bid
|  |  | A.3.3 | Developing tailored ocean literacy initiatives. |  |  | In Progress
|  |  | A.3.4 | Local media and community engagement on conservation (including whale shark festival, ocean education, sustainable marine tourism). |  |  | Complete
|  |  | A.3.5 | Providing training opportunities to build local capacity and develop a network of local ‘ocean champions’ |  |  | Complete | SHNT staff came to UK on training visit, continual virtual technical support from Blue UK team
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do any of these overlap with the students outlined in Y2 stats?
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are they supported monetarily or in others ways? I think other ways based on the comments provided for impact stats but please let me know if this isn't correct
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 schools but do we know how many students?
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What's our involvement in this?

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
6 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Whale Shark research complete, to inform the revision of the marine management plan. | O.4.1 | Number of whale shark hot spots identified |  | Number of hotspots | 1.3.1 |  | Weather conditions allow for fieldwork Planning application process takes due account of scientific findings | [6 empty] | 0 | Analysing data at end of Y2
|  |  | O.4.2 | Aerial and underwater footage of whale sharks collected |  | Pieces of evidence | NA - progress | [8 empty] | 405 | Amount of photos collected
|  |  | O.4.3 | Amount of evidence (report, campaigns etc.) used to lobby against proposed planning applications |  | Pieces of evidence | 1.4.1 | [8 empty] | 0
|  |  | O.4.4 | Number of recommendations provided to Government in regards to whale shark protection |  | Pieces of evidence | 1.4.1 | [8 empty] | 1 | A recommendation was given to SHG to consider zoning whale shark hotspots from divers around the island during local whale shark season. Previous activity of divers shows they have knowingly gone to hotspots to dive.
|  |  | O.4.5 | Number of surveys conducted |  | Surveys completed | NA - progress |  |  |  |  | 0 | 21 new whale sharks identified for zoning plans (not included in Y1 impact stats) |  |  | 0 | Between November 2021 and March 2022, the Trust successfully identified 42 different Bone sharks, of which 20 (47.62%) have never been identified previously in any global database. The research period covered 62 half-days, (avg. 0900hrs – 1300hrs) at sea, with 45 total sightings.
|  |  | O.4.6 | Number of reports produced |  | Reports produced | 1.4.1 | [8 empty] | 1 | As part of the licence permitted to conduct whale shark research and completion of the project a summary report featuring data and results of the research needed to be submitted to the St Helena research institute and those interested in the island biodiversity.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | Use a variety of technologies to identify key whale shark ‘hot spots’ from Dec-March, which will inform the revision of the MMP and the designation of zoning within the MPA.
|  |  | A.4.2 | Use CATS (Customized Animal Tracking Solutions) camera to obtain footage of whale sharks interacting with each other without human presence during their season in St Helena waters.
|  |  | A.4.3 | Use state of the art drones to capture aerial views of whale shark mass aggregation locations for the first time.
|  |  | A.4.4 | Use underwater Remotely Operated Vehicle to continue to document whale shark aggregation sites – this underwater footage will complement the aerial footage.
|  |  | A.4.5 | Use footage and data to actively lobby against any proposed planning applications (such as the subsea fibre optic cable) which would be adverse to known whale shark aggregation grounds. Environmentally sound alternatives to be provided to Government.
|  |  | A.4.6 | Collate the finding from the surveys – and previous – to inform zoning during the revision of the marine management plan.
|  |  | A.4.7 | Produce whale shark research summary report.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you insert how many you're expecting for each of these across the lifetime of the project?
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is more like an activity, and very similar to Activity A.4.2, A.4.3 and A.4.4, so if you're happy to remove suggest we do so? Can record progress in the activities notes section

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | St Helena Education Programme is established, in partnership with St Helena National Trust, Prince Andrew Secondary School and St Helena Dive Club | O.5.1 | Local high school students recieving and completing scuba diving scholarships (over 5 years) | 10 | Students | 4.1.2 | Attendence and completion records (PADI open water certificates) | There is unmet demand for marine education and marine career enhancement on island. Partners for delivery are available (teachers, scientists, fishers). Funding is secured for the programme. | [8 empty] | 3 | Provide 3 dive scholarships | 3 | Q1/2: NA, scholarships scheduled for Q3. Q3: Scholar positions advertised and candidates selected. Q4: 3 scholars are enrolled and training has begun. Equipment breifing and pool sessions completed, open water sessions in progress. Feedback from SCUBA teacher is very positive and the scholarship programme got an excellent response on island
|  |  | O.5.2 | Teachers supported on delivery of KS4 Marine Science | 1 | Teachers | 4.1.2 | Improved edcational materials and positive feedback from students | [9 empty] | 1 | Support Will, from Prince Andrew Secondary | 1 | Q1/2: Will is involved and supportive of the project. Q3: Adverts for dive scholarhsips advertised and recieved well at the GCSE Marine science cohort. Q4: No contact with Will in Q4 as he is no longer teaching. We will seek new school contacts in the New Year.
|  |  | O.5.3 | Educational matierials created for Bone Shark festival and other events | 5 | Outreach tools | 4.2.2 | Copy of infographics, posters, leaflets, activity sheets etc. Photos of them in use at events | [9 empty] | 0 | Outreach tools will be developed for Jan 2024 | 0 | Q1/2: Discusstion with SHNT team aboout gaps and current needs. Q3: Efforts made to secure funding for a visit during the festival to deliver the new materials. Q4: Concluded that Blue Education team will not be attending festival, but will be supporting from the UK. Communication with SHNT team to define gaps and needs. Connections made for getting VR headsets to St Helena.
|  |  | O.5.4 | Video footage captured of the St Helena underwater habitat | 10 | Assets (as outreach tools) | 4.2.2 | Copy of video assets (both online in UK and on hard drive in St H) | [9 empty] | 5 | From Danny Copeland's 2023 trip | 0 | Q2:Meeting with Danny Copeland to discuss oppurtunities. Q3: Danny Copeland confirmed for Jan-Feb 2024 trip. Q4. Funding secured for Danny Copelands time to create film on the dive scholars. Louis from SHNT is breifing the scholars.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Local partners are contacted and secured, and partnership expectations laid out |  |  | Complete
|  |  | A.5.2 | Blue Marine Produce a concept note for review by partners |  |  | Complete
|  |  | A.5.3 | Funding applications and proposals are completed |  |  | In Progress
|  |  | A.5.4 | Teachers, Blue Marine Team and partners plan and produce educational materials |  |  | Not started
|  |  | A.5.5 | Programmes advertised and participants sign up / are selected |  |  | Complete
|  |  | A.5.6 | Timetable of delivery is created |  |  | Not started
|  |  | A.5.7 | Venues booked for teaching where necessary |  |  | Complete
|  |  | A.5.8 | Materials for teaching/fieldtrips/fieldwork sourced and distributed |  |  | In Progress
|  |  | A.5.9 | Lessons and trips delivered |  |  | In Progress
|  |  | A.5.10 | Distribution of post-course questioniare to knowledge gain, transfer and behaviour change |  |  | Not started
|  |  | A.5.11 | Participants provide feedback |  |  | Not started
A.5.12

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Number of beneficiaries | 1 | Beneficiaries | [13 empty] | 3 | 3 staff members attained free dive level 1 certification this past season
U.2 | Number of beneficiaries | 1 | Beneficiaries | [13 empty] | 1 | One youth staff member is ready to start Advanced certification now and will be finished before she completes her SHNT contract in July and goes to uni
U.3 | Number of beneficiaries | 1 | Beneficiaries | [13 empty] | 2 | 2 of the already Advanced certified divers have had a refresher and are currently working with the 2 staff mentioned above on improving skills for working underwater.
U.4 | Outreach activity | 1 | Outreach activities/tools deployed | [13 empty] | 1 | The Plastics team members have been using the dive training already so that they can organise community dive clean-ups using local divers and freedivers. They organized a clean-up in March on the EMD Ocean Awareness day, another in April during Ocean month, and a 3rd in June on world oceans day. To date they have removed 392kg of trash from James Bay.
U.5 | Litter removed | 100 | kg litter removed | [13 empty] | 392 | To date they have removed 392kg of trash from James Bay.
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
Note on S7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jude to confirm whether these can be reported under our own stats

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 2 | 6 | O.1 | O.1.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 8 | 12 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 3 | 7 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 6 | 10 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.6 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 1.4.1 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 4 | [9 empty] | #REF! | #REF! | #REF! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 200 | 30 | 0 | 0 | 0 | 0 | 230 | 0 | 230 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 500 | 810 | 0 | 0 | 0 | 0 | 1310 | 0 | 1310 | 0 | 0 | 0 | 0
[14 empty] | 4.2.2 | 1 | 4 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0