## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links | Project logframe contributions | Included in project logframe? | Link to logframe
2021-10-01 |  |  | Jersey Snorkel Trail | Y - Freddie to update | P4 Jersey M&E Logframe.xlsx
2021-11-01 |  |  | Maldives Fisher Platform | Y - Anna to update | 20_MaldivesProgramme M&E Logframe.xlsx
2021-12-01 |  |  | Berwickshire Ocean Observatory | Y - Anna/Joe to update | P5 Berwickshire M&E Logframe.xlsx
2022-01-01 |  |  | Aeolians Education Programme | Y - Anna/Giulia to update | 62_Italy M&E Logframe.xlsx
2022-02-01 |  |  | St Helena | Y - Anna to update | P2 StHelena M&E Logframe.xlsx
2022-03-01 |  |  | Convex | Y - Anna to update | 21_Namibia M&E Logframe.xlsx
2022-04-01 |  |  | Namibia | Y - Anna to update | 94_ConvexSeascape M&E Logframe.xlsx
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01 | Establising partnership with Ocean Race for SWB translation | GC5761_BMF_TSWB_Multilingual_Setup_161122.pdf
Maldives fisher platform deadline extended
| Aeolian Makerzine final text confirmed | Makerzine - Nov 17 2022.pdf - Google Drive
| Report sent to Nico and Rob (makerzine funding) | Summary for Nico and Rob.docx
Content sent to DK and new timeline proposed with Eugenie
2022-12-01 | CFOF presentation
SWB --> schools in Sheffield and Birmingham, feedback recieved
Swarovski annual impact report
Makerzines sent to print
2023-01-01 | Contact made with school around SH
Launch of TSWB in Spanish and Portuguese
Ocean Observatory site completed
Scoping and meeting with ArtExplora project
TSWB exhibited in Alicante
Edu x comms strategy confirmed
1244888 = reach of TSWB to date (8th Jan)
Partnership with York Splash of Colour
2023-02-01 | TSWB VR proposals submitted (DP world and Tech for Nature)
Fed back on Junior Marine Biology Courses, Maldives
St Helena education programme scoping
WWW first draft recieved
Planning for Jersey Snorkel Trail education 2023
Visit to Bringtlingsea Harbour EA oysters
Funding secured for Climate Change and Nitrogen Modules of Masmahaa Veshi
Social media plan and assets for Mashahaa Veshi started
Social media plan and assets for Ocean Observatory completed
Meeting with Dragon School
BLUEprint for MPAs education case study completed
TSWB exhibited in Cape town
Final meeting with Swarovski
Plans made for BMYC education package
Sign-up partnership established
2023-03-01 | First pass of WWW recieved and fed back on
Sail GP partnership proposal
Partnership established with the Iris Prize
First Adopt a Beach in the Aeolians
Ocean Observatory launched 10th March
2023-04-01 | Funding oppurtunities explored to support Cerys, St Helena Marine student
Berwickshire Ocean Observatory exhibited at Eyemouth Hippodrome for two weeks
TSWB reaches Brazil
Masahaa Veshi is launched
Snorkel Trail Booklet completed
Big Give funding secured
2023-05-01 | VR project kicks off
Turkish TSWB translations finalised
Filming in the Solent for WOD live lesson
Invited to Wales WT Youth Ocean Summit
Darwin + application submitted for St Helena
Interns interviewed and selected
2023-06-01 | Trip to Jersey for Snorkel Trail delivery
First visuals created for TSWB VR
Connections made with MCS education team about curriculum campaign
Connections made with UNESCO about resource endorsement
Hannah joined the team
Fishing gear animation series pitched to BMT giveback
WOD for Schools live lesson went live
2023-07-01 | Ocean Race concludes global tour
Berwickshire Ocean Observatory is delivered at the Scottish Seabird centre
Illustrations finalised for the Aeolians illustration
Content finalised for climate change and nitrogen modules of Masmahaa Veshi
Funding secured for St Helena dive scholarships
2 interns onboarded
Slow Food event, Aeolians
Daughters of Earth appliacation submitted for the Aeolians
Convex education passed to Education Unit
French TSWB translations begun
Namibia ocean literacy workshop is delivered
WWW published
2023-08-01
2023-09-01 | TSWB on CNN interview, Monaco Yacht Show.
Zandile teaches kinds in Sao Tome to free dive with Mission William
Helena BC records TSWB VO
2023-10-01 | Arabic TSWB completed
Sign Up captions completed
Makerzines reach schools in Aeolians
Aeolian animation VO recorded and animation completed
Note on A84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Hannah Le Brocq I'm not very good at remembering to fill this section out, maybe we could both input here and it could double as edu newsletter plans?

## Impact and Outcome
Impact | To educate and inspire all ages to become ocean advocates with free, accessible and imaginative resources, through hands-on education programmes and career enhancement oppurtunities.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | 1.5 million people engage with Blue Marine's educational initiatives | OC.0.1 | Number of students taking part in Blue Marine's on-the-ground education programmes, which enhance ocean literacy by filling gaps in current curriculums | 1, 2, 3, 4, 5 | 4.1.2, 4.2.1, 4.2.2, 4.2.3, 4.3.1 | 4.1, 4.2, 4.3 | Attendance records and teacher/student questionaire responses | There is unmet demand for marine education within schools and local comunities globally. Schools are accepting of and willing to integrate Blue Marine's materials. There is capacity for the Blue Marine team to travel and visit schools, or there is teacher capacity to deliver materials.
|  |  | OC.0.2 | Number of people using Blue Marine's online education materials | 1, 3, 4, 7, 8, 10 | 4.1.2, 4.2.1, 4.2.2, 4.2.3, 4.3.1 | 4.1, 4.2, 4.3 | Digital impact metrics (views, clicks, downloads etc.) | Digital education resources are free of charge and easy to access and navigate. Appropriate impact metric tracking is in place for all projects.
|  |  | OC.0.3 | Number of young people and community members benefitting from Blue Marine's career enhancement or training programmes | 3, 5, 6, 9 | 4.1.1, 4.1.2, 4.2.1, 4.2.2, 4.2.3, 4.3.1, 1.4.1 | 4.1, 4.2, 4.3 | Attendance records and student/community questionaire responses | There is enough demand from young people for career enhancement experiences. Local communities are accepting of Blue Marine's wider work and their local education programme.
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.4.1 added (new evidence to support protection) - evidence gathered in seagrass summer school through surveys

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
6 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | The Sea We Breathe online experience and associated classroom materials | O.1.1 | Number of people around the world engaging with The Sea We Breathe online experience | 500000 | Individual views | 4.2.1 | Digital impact metrics (individual views) | Appropriate impact metric tracking is in place. | 0 | Soph to help | [6 empty] | 500000 | Reach 500,000 views to date | 1000000 | Exceeded 1m views to date, and won a Webby award | 1500000 | Reach 1.5m | 500000 | Q1: 1.4m views April 2023, Q2: 1.5m views June 2023. Q3: Total in Sept 2023, 1,635,700 page views, 1,215,802 users. Total in Dec 2023, 1,689,203 page views, 1222297 users.
|  |  | O.1.2 | Number of schools / conservation / community groups contacted to encourage use of the classroom materials | 200 | Number groups | 4.2.1 | Tracker of emails sent | Admin staff are reading emails and passing onto teacher, who then pass the learning onto students. | 0 | [7 empty] | 200 | Classroom materials launched and distributed to 200 schools | 235 | 235 schools contacted | 30 | Directly engage with and see evidence of use in 30 schools | 1 | Q1: No progress this quarter. Q2: ~50 schools in Edinburgh contacted. Resource promoted through WOD4S. Q3: Used in 3 schools in Istanbul. Used at an "Ocean School" in Mozmbique. Q4. No progress this quarter.
|  |  | O.1.3 | Users display increased knowledge on ocean-climate topics after interacting with The Sea We Breathe | 75% | % | 4.4.1 | Student surveys | Questionaires are fit for purpose and answered truthfully | 0 | [7 empty] | 75% | Surveys and interviews conducted, planned for December 2022 | 0 | Not enough surveys completed to calculate | 75% | At least 75% of survey respondents self-reporting increased knowledge | 83% | Q1: 83% of 12 respondents. Q2: No additional respondents. Q3: No additional respondents, funding secured from Monica Vinader for TSWB education pack to promote use in schools. Q4. NA
|  |  | O.1.4 | Users display intent to share new ocean-climate knowledge with families and friends | 60% | % | 4.4.2 | Student surveys | Questionaires are fit for purpose and answered truthfully | 0 | [7 empty] | 60% | Surveys and interviews conducted, planned for December 2022 | 0 | Not enough surveys completed to calculate | 60% | At least 60% of survey respondents showing intent to share new knowledge | 25% | Q1: only 25% stated that they had shared new knowledge with others. Q2: No additional respondents. Q3: No additional respondents, funding secured from Monica Vinader for TSWB education pack to promote use in schools. Q4: NA.
|  |  | O.1.5 | Users show indications of pro-environmental behaviour change after interacting with The Sea We Breathe | 60% | % | 4.2.3 | Student surveys | Questionaires are fit for purpose and answered truthfully | 0 | [7 empty] | 60% | Surveys and interviews conducted, planned for December 2022 | 0 | Not enough surveys completed to calculate | 60% | At least 60% of survey respondents showing indications of behaviour change | 58% | Q1: 58% of respondents took action for the ocean (eating sustaibale fish, reading/watching something or talking to others). Q2: No additional respondents. Q3: No additional respondents, funding secured from Monica Vinader for TSWB education pack to promote use in schools. Q4. NA
|  |  | O.1.6 | Translate TSWB into multiple languages | 10 | Languages | 4.2.2 | Multilingual website URLs | Translations can be sourced and design time funded | 0 | [5 empty] | 1 | First launch of TSWB launched in english | 0 | NA | 0 | NA | 5 | Spanish, Portuguese, Italian plus two | 6 | Q1: Spanish, Portuguese, Italian. Q2: Turkish and French in progress. Q3: Turkish live, French and Arabic in progress. Q4: French and Arabic completed.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Compile existing background information on target audience, performance within the digital space and existing ocean/climate educational content |  |  | Complete
|  |  | A.1.2 | Select digital design agency, create roadmap and onboard (GC) |  |  | Complete
|  |  | A.1.3 | Gather content on key ocean-climate topics, selected and designed based on its ability to inspire behaviour change and increase awareness. |  |  | Complete
|  |  | A.1.4 | Work with agency and BLUE Media to define strategy and build the platform |  |  | Complete
|  |  | A.1.5 | Receive a handover from the digital agency to ensure BLUE can confidently distribute the product and address any product issues. |  |  | Complete
|  |  | A.1.6 | Work with Comms team to determine target audiences and a social media/distribution strategy. |  |  | In Progress
"1" |  |  | A.1.7 | Connect with schools both in the UK and abroad to integrate product as a science classroom tool. |  |  | In Progress
|  |  | A.1.8 | Develop evaluation tools (e.g. surveys and interviews) to distribute to schools or other institutions/user groups to collect additional data |  |  | Complete
|  |  | A.1.9 | Onboard education consultant to produce classroom materials |  |  | Complete
|  |  | A.1.10 | Deploy technology that will create compatible media types for the platform e.g reef cams |  |  | In Progress | Perhaps not possible within the final platform. Explored oppurtunities with Naturebytes and StreamOcean
|  |  | A.1.11 | Develop conservation goals of the programme with project managers and launch associated citizen science |  |  | Not started | May be conducted in other elements of Blue Education's work (i.e. ocean observatory)
|  |  | A.1.12 | Translate the site into multilpe languages |  |  | In Progress | In partnership with the Ocean Race, and independently
|  |  | A.1.13 | Continuously monitor engagement analytics and collect impact data (e.g. behaviour change, awareness, attitudes) |  |  | In Progress
|  |  | A.1.14 | Exhibition of TSWB around the world in partnership with the ocean race |  |  | Complete
A.1.14
A.1.14
A.1.14
Note on Z4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hey @Anna Hughes, two questions: 1. Are the two values in this cell total for the quarter? So is the total 2.9m? Or is it that it is 1.4mil in Q1 and 100,000 in Q2? 2. Depending on the answer to the above, should the cell next to this not read either 1.5mil or 2.9 mil? Reply: These are all time stats. We are at just over 1.5m since launch (cumulative). I can get stats for the quarters if you want? Reply: that's ok - if it was 1mil last year and it's 1.5 mil this year we can just call it 500,000. But that brings me back to my second question about the value that's in there now Reply: Changed to 1.5m. This is not just this year, its since launch (2021) - is that okay? Reply: @Appin Williamson we have a new google analytics system that I don't yet understand, so I can't update. I probably wont be able to until past the deadline - sorry! Reply: No probs - thanks for letting me know!
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson should this 'Value' column be a % or a number (ie. number of surveys to be conducted in 2022) Reply: I would make this he percentage, perhaps this is where the other spreadsheet will come in handy to calculate it for you. I have made an empty file here: Connection_ImpactStatistics.xlsx if you would find it useful to start populating it Reply: hmmm link isn't working - I'll teams it to you!
Note on W6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson should this 'Value' column be a % or a number (ie. number of surveys to be conducted in 2022) Reply: I would make this he percentage, perhaps this is where the other spreadsheet will come in handy to calculate it for you. I have made an empty file here: Connection_ImpactStatistics.xlsx if you would find it useful to start populating it Reply: hmmm link isn't working - I'll teams it to you!

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Multiple editions of the Blue Marine Makerzine are produced, with bespoke content for different regions in which we work | O.2.1 | Editions of Makerzine produced | 2 | Books (as an outreach tool) | 4.2.2 | Physical printed books | Education unit has capacity to deliver this, and wider relevent project managers are available to provide locational context and local knowledge | 0 | Soph to help | [6 empty] | 1 | Create Aeolian Islands edition of the Makerzine | 1 | Aeolians edition nears completion | 0 | Complete and distribute Aeolian Makerzine | 1 | Q1: Aeoloian Makerzine finalised and printed. Q2: No update, complete. Q3: No update, complete. Q4: No update, complete.
|  |  | O.2.2 | Makerzines distributed to children around the world | 10000 | Children reached | 4.2.1 | Tracking of distribution, proof of postage and reciept from schools | Funding for shipping can be secured. Schools want to recive the Makerzines. | 0 | [6 empty] | Find pre-2022 numbers | 2000 | Ship remaining copies of St Helena edition (~2000) | 1800 | Most of the remaining copies were shipped | 2000 | Ship 2000 Aeolian Makerzines | 2000 | Q1: Remaining edition 1 copies shipped. Aeolian copies yet to be shipped. Q2: 1900 copies shipped to schools and NGOs in Italy. 100 to Greece. 500 in reserve at Somerset House. Q3: All Italian copies distributed to school children in Italy in late September. Q4: No update, complete.
|  |  | O.2.3 | Children display increased knowledge and awareness of ocean topics after reading the Makerzine | 50 | Number of children | 4.4.1 | Student quotes and ad-hoc feedback | Teachers are willing and able to collect quotes and photos | 0 | [7 empty] | 50 | Recieve feedback from schools shipped to this year | 5 | Only 5 schools gave feedback and it was not in a formal survey. Must push for this next year | 50 | Recieve detailed survey feedback from secondary schools in Milazzo and the Aeolian Islands | 0 | Q1: Feedback yet to be collected. Q2: Feedback will be collected in Q3 (new school year). Q3: Feedback and photos will be collected from trachers and students this quarter. Q4. Problems recieving feedback as our schools contact is no longer working for Blue Marine. Photos recieved.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Conduct research to gather content and themes for the book, consulting relevent project teams |  |  | Complete
|  |  | A.2.2 | Onboard Planetari as a production partner |  |  | Complete
|  |  | A.2.3 | Draft and refine educational content, ensuring it is age appropriate and curriculum linked in the target country |  |  | Complete
|  |  | A.2.4 | Source images and comission illustrations to make the book eye-catching |  |  | Complete
|  |  | A.2.5 | Work with Misfits to design laser cut sections |  |  | Complete
|  |  | A.2.6 | Research and select printing compangy, based both and cost and emissions of shipping |  |  | Complete
|  |  | A.2.7 | Secure funders for distribution |  |  | Complete
|  |  | A.2.8 | Build up schools database and liase with schools for distribution |  |  | In Progress | Connected with all primary and middle schools in the Aeolian Islands
|  |  | A.2.9 | Print and ship makerzines |  |  | Complete
|  |  | A.2.10 | Conduct surveys, ask for quotes and photos and gather feedback to inform effectiveness of the book |  |  | In Progress
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson these three rows will feature in most outputs I think - is that okay? Reply: Yes that's totally fine - happy for you to have it however works best for you :)

## Output 3
Outputs |  |  | Indicators
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | An includive and diverse three-tier internship programme is developed and launched | O.3.1 | Internship programme formally established | 1 | Programme | 4.2.2 | Existence of programme within Blue Marine's HR operations, copy of internship documentation | Internship programme is integrated effectively into Blue Marine operations and is accepted and encouraged bythe wider team. Funding is secured to support inter salary and training needs | [8 empty] | 1 | 1 internship propgramme developed | 1 | Programme developed and launched with Ocean Bottle in summer 2022 | 1 | Internship programme continually improved | 1 | Q1: Programme updated and launched accross team. Q2: NA. Q3: Programme document for managers completed and designed. Q4: Document to managers not yet circulated.
|  |  | O.3.2 | Interns enrolled in the programme (with representation from diverse backgrounds) | 3 | Number of interns | 4.1.1 | Payroll evidence | Interns complete the programme and engage with activities provided. Team provide sufficient support and facilitate integration | [8 empty] | 3 | Host 3 interns | 3 | Elina Doumer, Emily Bulled, Kathryn Smith | 3 | Hire 3 interns, at least one in partnerhsip with Creative Access | 2 | Q1: Job Advertisement Launched with Creative Access. Q2: Intern application reviewed, interviews conducted and interns selected. Start dates are 24th July and 1st Aug 2023. Q3: Two interns sucessfully employed. Q4: Job ad for Economics intern completed and Creative Access hired again.
|  |  | O.3.3 | Interns gain valuable skills and career oppurtunites are enhanced | 3 | Number of interns | 4.1.2 | Self reported through intern surveys | Questionaires are fit for purpose and answered truthfully | [8 empty] | 3 | All 3 interns show development of new skills and feel more confident in securing employment in the sector | NA | Decided that interns haven't been with us long enough to condict surveys | 3 | Conduct surveys at the end of Elina, Emily and Kathryns internships | 0 | Q1:Informal feedback collected from Kathryn, Elina and Emily, Q2: Pre-internship surveys shared with the two new interns. Q3: Pre-internship survey completed x 2. Q4: Post internship survey completed x1.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Research conducted into DIE in the workplace |  |  | In Progress | Research will be continuous to ensure we stay up to date as an organisation
|  |  | A.3.2 | Internship programme and policies drafted with input from HR |  |  | Complete | This should be a continually evolving document, updated regularly
|  |  | A.3.3 | Hiring process defined with input from HR |  |  | In Progress | This is still not compleatly clear, there are still multiple avenues
|  |  | A.3.4 | Interns onboarded by dedicated mentor and activities initiated |  |  | Complete
|  |  | A.3.5 | Interns continuously supported by wider Blue Marine team and designated mentor |  |  | In Progress
|  |  | A.3.6 | Appraisals conducted annd future oppurtunities explored |  |  | Not started
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Anna Hughes should this be 2020 or 2022?
Note on Z6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI @Anna Hughes I think we might have to choose that they are either classed as monetary or non-monetary beneficiaries otherwise it almost looks like we're benefitting four people when it's two - do you have a preference? Reply: Ah yes okay, I think probably monetary? Reply: Yeah you're probably right - realistically they're both but in the immediate term they are monetary ☺️ - thanks!

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Blue Marine's educational resource bank is built and refined | O.4.1 | World's Wildest Waters is written, illustrated and published | 1 | Books | 4.2.2 | Copies of published book, photos of book in bookshops | Foreword and other content is provided on time to DK, book is accepted in bookshops | [12 empty] | 1 | Book Published | 1 | Q1: Final version signed off, going to print April 2023. Q2: Published and available in book shops 3rd Aug 2023. Q3: Book seen in Waterstones accross the country. Copies purchased for Blue Marine to use in school visits. Q4: Copies taken to Namibia.
|  |  | O.4.2 | Animation series is created explaining fishing gear types | 5 | Animations | 4.2.2 | Animations complete and uploaded to Vimeo | Blue Marine team continue working together to disentangle and solidify messaging on low-impact fisheries | [12 empty] | 0 | By end of 2023, want to have plans finalised and animators onboarded | 0 | Q1: No progress this quarter. Q2: Entered this project into BMT Giveback programme, potential funding oppurtunity. Q3. Application rejected by BMT at final stage. Other funding oppurtunities will be explored. Q4: No progress.
|  |  | O.4.3 | BMYC education pack is developed and distributed | 1 | Education pack | 4.2.2 | Digital and hard copies of pack, photos of it being used on yachts | Knowledge of teahcing on yachts is sufficient within education unit, packs are suitable for audience | [12 empty] | 1 | Due to launch at BMYC event in Sept 2023 | 1 | Q1: Planning underway, contacts made with superyachts. Q2: Increased resourcing allowed for more planning and content development. Q3: content developed and booklet produced and printed, taken to Monaco late September. Q4: Booklet recieved well at MYS and used in various fundraising activities.
|  |  | O.4.4 | Education hub is integrated into the Blue Marine website | 1 | Website subdomain | 4.2.2 | URL of education hub subdomain | Media unit redevelop website and integrate this functionality | [12 empty] | 1 | Planned to allign with new BMF website | 0 | Q1: No progress this quarter. Q2: Quote secured from Jory&Co, brainstorming hub design. Q3. Meetings with SII team to discuss joint fundraising and design, delays due to delays in main website redesign. Q4: Project on hold while media team decide on how to approach website redesign.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  |  | WWW
|  |  | A.4.1 | Sign partnership agreement with DK books |  |  | Complete
|  |  | A.4.2 | Provide written and visual content |  |  | Complete
|  |  | A.4.3 | Approve illustrations and copy |  |  | Complete
|  |  | A.4.4 | Write 'Who Are We' |  |  | Complete
|  |  | A.4.5 | Secure HRH Princess Eugenie's foreword, image and signature |  |  | Complete
|  |  | A.4.6 | Sign off final version |  |  | Complete
Fisher Animation Series
|  |  | A.4.7 | Collate team knowledge |  |  | Not started
|  |  | A.4.8 | Onboard animator and comission first one (potting) |  |  | Not started
|  |  | A.4.9 | Provide script, referecne images, storyboard and other guidence |  |  | Not started
|  |  | A.4.10 | Review drafts |  |  | Not started
|  |  | A.4.11 | Approve final version |  |  | Not started
BMYC
|  |  | A.4.12 | Plan content for activities, case studies and booklet |  |  | In Progress
|  |  | A.4.13 | Create educational content |  |  | In Progress
|  |  | A.4.14 | Have content designed |  |  | Not started
|  |  | A.4.15 | Purchase science kits |  |  | Not started
|  |  | A.4.16 | Distribute to families |  |  | Not started
Education hub
|  |  | A.4.17 | Create breif with media team |  |  | Not started
|  |  | A.4.18 | Onboard web design agency |  |  | In Progress
|  |  | A.4.19 | Review and approve |  |  | Not started
A.4.20
A.4.21
A.4.22
A.4.23
A.4.24

## Output 5
Outputs |  |  | Indicators
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Oyster outreach programme is delivered in Brightlingsea, Essex | O.5.1 | Essex oyster education programme is developed | 1 | Programme | 4.2.2 | Copies of lesson plans, powerpoints and required kit | Education programme is age appropriate, curriculum linked and supported by teachers | [12 empty] | 1 | Programme should be complete | 1 | Q1: Programme materials finalised April 2023. Q2: Complete. Q3: NA. Q4: NA.
|  |  | O.5.2 | Number of primary school children attending classroom and outdoor sessions are delivered | 120 | Children | 4.1.2 | Attendence records and photos | Attendance records are accurate and permission is cleared to photograph children | [12 empty] | 120 | Teaching planned for May 2023 | 112 | Q1: teaching not yet happened. Q2: All sessions delivered sucessfully, eight children not in attendence, 112 Y4/Y5s. Q3: NA. Q4: NA.
|  |  | 0.5.3 | Children display increased knowledge and awareness of ocean topics after participating in the sessions | 75% | Percentage increase | 4.4.1 | Student surveys | Questionaires are fit for purpose and answered truthfully | [12 empty] | 75% | Surveys to be conducted after teaching | NA | Q1: teaching not yet happened. Q2: Decided to ask for teacher feedback due to age of children. Teachers indicated that students talked knowledagably about marine issues since attending and even showed positive behaviour change https://docs.google.com/forms/d/1T2mTR7xGE88vhrUK3j7tqVOglLlQxfyS-zaAE-3sxbY/edit#responses. Q3 NA. Q4: NA.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Location of cage installation is approved, licences cleared and equipment purchased |  |  | Complete
|  |  | A.5.2 | Lesson plans and powerpoints are researched, produced and designed |  |  | Complete
|  |  | A.5.3 | Classroom and outdoor sessions are delivered |  |  | Complete
|  |  | A.5.4 | Partnership is established with Essex Wildlife Trust and Bringtlingsea Marina |  |  | Complete
|  |  | A.5.5 | EWT team are briefed on delivery |  |  | Complete
|  |  | A.5.6 | EWT team deliver the classroom sessions |  |  | Complete
|  |  | A.5.7 | Anna and Matt to attend one trip for asset capture and feedback surveys |  |  | Complete
A.5.8
A.5.9

## Output 6
Outputs |  |  | Indicators
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Scoping is conducted in the field of Ed-Tech (specifically Minecraft) | O.6.1 | Produce scoping report for the use of Ed-Tech in marine education | 1 | Report | 4.2.2 | Copy of report and associated reading lists / research database | Appropriate/sufficient/up-to-date information is gathered | [8 empty] | 1 | Report to be started by the end of 2022 | 0 | Report not yet started | 1 | Report complete | 0 | Q1: Report not yet started, may be pushed to late 2023. Q2: No progress this quarter. Q3: No progress this quarter. Q4: No progress this quarter.
|  |  | O.6.2 | Relationships with Microsoft, Mojang/Minecraft, and YouTubers established | 5 | Contacts | 4.3.1 | Correspondence to support informal/formal relationships | Desired partners are willing to work with Blue Marine | [8 empty] | 0 | Partners to be explored and confirmed in 2022 | 0 | Partners explored (Naturebytes) but not confirmed | 3 | Production partners established | 0 | Q1: No progress this quarter. Q2: No progress this quarter. Q3: No progress this quarter. Q4: No progress this quarter.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Background reading on Ed-Tech conducted |  |  | In Progress
|  |  | A.6.2 | Background reading on innovative ocean education conducted |  |  | In Progress
|  |  | A.6.3 | Evidence compiled into an interal report |  |  | Not started
|  |  | A.6.4 | Report shared with partnerships and media teams |  |  | Not started
|  |  | A.6.5 | Existing contacts contacted (e.g. Arlo's contact at Microsoft) |  |  | Not started
|  |  | A.6.6 | New contacts in the inductry researched and contacted |  |  | In Progress
|  |  | A.6.7 | Meetings held with potential partners for production and distributoin |  |  | In Progress | Naturebytes

## Output 7
Outputs |  |  | Indicators
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 | A skills-sharing group is created for all of Blue Marine's educators and education partners | O.7.1 | Skills-sharing group is developed and formalised | 1 | Working group | NA | Correspondence, meeting minutes and emails | There is appitite among educators to form this group | [8 empty] | 0 | Working group to be established in 2023 | 0 | Working group to be established in 2023 | 1 | Contacts brought together and working group established | 0 | Q1: No progress this quarter. Q2: No progress this quarter. Q3: No progress this quarter. Q4: No progress this quarter.
|  |  | O.7.2 | Conduct meetings bi-annually | 2 | Meeting | 4.2.2 | Meeting minutes and records of attendance | Educators have the time and capacity to attend meetings | [8 empty] | 0 | Working group to be established in 2023 | 0 | Working group to be established in 2023 | 2 | 2 meetings held | 0 | Q1: No progress this quarter. Q2: No progress this quarter. Q3: No progress this quarter. Q4: No progress this quarter.
|  |  | O.7.3 | Summary reports produced and shared | 2 | Report | 4.2.2 | Copy of report and evidence of sharing via email | Report is produced in an effective and timely manner, and is utilised by workshop participants | [8 empty] | 0 | Working group to be established in 2023 | 0 | Working group to be established in 2023 | 2 | 2 reports produced | 0 | Q1: No progress this quarter. Q2: No progress this quarter. Q3: No progress this quarter. Q4: No progress this quarter.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1 | Contact database created of all Blue Marine's educational partners, supporters and teachers, and other NGO education professionals |  |  | Not started
|  |  | A.7.2 | Create mailing list |  |  | Not started
|  |  | A.7.3 | Plan first workshop, introductions and questions |  |  | Not started
|  |  | A.7.4 | Host workshop online with support from Hannah |  |  | Not started
|  |  | A.7.5 | Write up report for first workshop |  |  | Not started

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Output 8
Outputs |  |  | Indicators
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 | The Sea We Breathe Virtual Reality experience | O.8.1 | People around the world engage with The Sea We Breathe VR experience | 500000 | Individual uses | 4.2.1 | Google Analytics (or equivelent) tracking stats | Digital experience is freely available and uder friendly, trakcing is set up | [12 empty] | 2000 | VR experience will launch October 2023 | 2153 | Q1: No users yet. Q2: No public users yet, Blue Marine staff have seen demos. Q4: Tracking not quite functioning, but the VR reached 2153 people during COP28.
|  |  | O.8.2 | VR experience is deployed at COP28 in Autumn 2023 | 1 | Number of events | 4.2.2 | Experience accepted into COP28 programme/"green zone", Blue staff to attend and capture photo evidence | COP28 is open and receptive to hosting the VR experience | [12 empty] | 1 | VR experience will launch October 2023 | 1 | Q1: VR not launched yet. Q2: On track to launch October 2023. Q3: Voiceover recorded with Helena Bonham Carter, animation in final stages, headsets purchased. Q4: VR launched 29/11/23, hosted at COP28 but the Ocean Pavillion, Resilience Hub, Goals House and and DP world.
|  |  | O.8.3 | Number of schools (and students) reached through rollout using google cardboard | 600 (20 classes) | Number of school students | 4.1.2 | Attendence records for classes using the product | Schools are keen and able to use this technology | [12 empty] | 30 | VR experience will launch October 2023 (30 students = 1 class) | 0 | Q1: No rollout yet. Q2: No rollout yet. Q3. No rollout yet. Q4: No progress this quarter.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1 | Research and summarise ocean VR |  |  | Complete
|  |  | A.8.2 | Onboard Unseen Studio |  |  | Complete
|  |  | A.8.3 | Narratives and themes decided |  |  | Complete
|  |  | A.8.4 | VR experience is designed and developed by Unseen |  |  | In Progress
|  |  | A.8.5 | Blue Education and Media teams feedback and finalise |  |  | Not started
A.8.6
A.8.7
Note on Z4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Anna Hughes I thought the VR had launched at COP? Reply: It has! That's the Q4 bit. The analytics is causing some problems so I'm not totally confident in that 700... will update if we get clarity Reply: Ok great - for now I will include 700 and we can update if we need to
Note on Z6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Anna Hughes did it get rolled out to students in COP? If so I'll put 30 in here Reply: I don't think any students saw it, wouldn't be confident in saying that anyways! Reply: OK no worries - is the 'planned in 2023' text correct in that case? Perhaps not Reply: oh I see, yes you're right!

## Output 9
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 | Ocean Observatories | O.9.1 | Berwickshire Ocean Observatory website produced | 1 | Website | 4.2.2 | Website url is live | [13 empty] | 1 | Website is live, distributed, promoted and evaluated effectively. | 1 | Q1: Observatory went live in March, social media promotion and schools outreach conducted. Q2: Meetings held with local partners, support gathered, sessions delivered at the Scottish Seabird Centre. Q3: Meeting with COAST, Restoration Forth and Edinburgh Shoreline. Science pack in developent with BMR. Q4: Pack completed with BMR, due to launch in januar. Updated made to website to improve navigation based on user feedback.
|  |  | O.9.2 | Jersey Ocean Observatory website produced | 1 | Website | 4.2.3 | Website url is live | [13 empty] | 1 | Website is developed and pushed live online | 0 | Q1: NA, funding not yet secured. Q2: Background research begun. Q3: Jory & Co onboarded and contract signed. Timeline determined to support Jersey's Marine Spatial Plan, ideas formalised with Jersey team. Q4: No progress this quarter.
|  |  | O.9.3 | Greece Ocean Observatory website produced | 1 | Website | 4.2.4 | Website url is live | [13 empty] | 1 | Website is in development | 0 | Q1: NA, funding not yet secured. Q2: Background research begun. Q3: Jory & Co onboarded and contract signed. Meetings held and partnership established with Cycladed Conservation Collective to support on local knowledge provision and content development. Q4: No progress this quarter.
|  |  | O.9.4 | Caribbean Ocean Observatory website produced | 1 | Website | 4.2.5 | Website url is live | [13 empty] | 1 | Website is in development | 0 | Q1: NA, funding not yet secured. Q2: No progress this quarter. Q3: Jory & Co onboarded and contract signed. Meetings held with Jude and Fiona, scoping plan discussed for their trip in Nov. Discussing possiblity of partnering with all 6 parks authorities in the Dutch Carribean. Q4: Observatory discussed with partners during project site to Dutch Carribean.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1 | Secure finding (Big Give) |  |  | Complete
|  |  | A.9.2 | Compile background information on target audience, location details, potential themes and categories, main aims and uses, links to project goals |  |  | In Progress
|  |  | A.9.3 | Onboard Jory&Co for web development |  |  | In Progress
|  |  | A.9.4 | Gather video footage, comissioning where needed |  |  | Not started
|  |  | A.9.5 | Gather additional facts and background information for the website |  |  | Not started
|  |  | A.9.6 | New landing page and three seperate microsites developed by Jory&Co |  |  | Not started
|  |  | A.9.7 | CMS handover |  |  | Not started
|  |  | A.9.8 | Connect with schools both in the UK and abroad |  |  | Not started
|  |  | A.9.9 | Develop evaluation tools (e.g. surveys and interviews) to distribute to schools or other institutions/user groups to collect additional data |  |  | Not started
|  |  | A.9.10 | Establish partnerships with local organisations for delivery and rollout |  |  | Not started
|  |  | A.9.11 | Translate site where necessary |  |  | Not started
|  |  | A.9.12 | Continuously monitor engagement analytics and collect impact data |  |  | Not started

## Unplanned Outputs
Outputs
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Virtual live lesson with Encounter Edu for World Oceans Day for Schools | 1 | Live lesson | 4.2.2 | 7864 schools registered | Recording of the live lesson | [10 empty] | 1 | Lesson delivered 8th June 2022
U.2 | Classroom presentation and Makerzine distribution with Y2 at Wetherby School, London. | 1 | Presentation | 4.2.2 |  | Photos and presentation slides | [10 empty] | 1 | Visit on 9th June 2022
U.3 | Installation of The Sea We Breathe at Ocean Race 'race villages' around the world | 9 | Installations | 4.2.2 |  | Feedback and photos from OR team | [10 empty] | 0 | NA | 9 | Race occuring in 2023 | 4 | Q1: Alicante, Cabo Verde, Cape Town, Itajai
U.4 | GSL Leadership talk | 1 | Presentation | 4.2.2 |  | Social media posts and presentation slides | [10 empty] | 1 | Presentation delivered 11th Nov 2022
U.5 | Edinburgh University Dissertation Mixer | 1 | In-person event | 4.2.2 |  | Attendence record | [10 empty] | 1 | Attended 22nd Nov 2022
U.8 | Dragon School Partnership | 1 | Partnership | 4.2.3 |  | Meeting notes and partnership agreement | [14 empty] | 1 | Secured February 2023
U.9 | SVG concept note April 2023 | 1 | Written concept note | 4.2.2 |  | Copy of concept note | [14 empty] | 1 | Delivered on 4th April 2023
U.10 | Little Justice Leaders pack produced | 1 | Learning resource | 4.2.2 |  | Physical resource packs | [14 empty] | 1 | Pack finalised 10th April 2023
U.11 | Presentation to Tech4Nature | 1 | Presentation | 4.2.2 |  | Slides and attendence | [14 empty] | 1 | Presentation on 18th April 2023 - estimated reach 30 people
U.12 | Live lesson in the Solent for WOD for Schools | 1 | Live lesson | 4.2.2 |  | Recording of the live lesson | [14 empty] | 1 | Lesson delivered 8th June 2023 - estimated reach 4280 students
U.13 | BLUEPrint for MPAs Education Case Study | 1 | Document | 4.2.2 |  | Copy of document | [14 empty] | 1 | Case study document completed Q1
U.14 | Partnership established with SignUp captions, for BSL interpretation on our videos | 10 | Videos captioned | 4.2.2 |  | Url to YouTube videos | [14 empty] | 0 | Q1: Partnership established. Q2: Video list provided and interpreter hired.
U. 15 | Invited to prosent workshops at Wales Wildlife Trust Ocean Youth Summit | 1 | In-person event | 4.2.2 |  | Attendence record | [14 empty] | 0 | Event planned for Q3
U.16 | Stakeholders reached through in-person events and with materials | 1 | Stakeholders reached | 4.2.1 |  | Attendence record | [14 empty] | 4310 | Number of attendees to presentations (attendees at 18th April 2023 and students receiving lesson 8 June 2023)
U.17 | TSWB at Burgess stand, Monaco Yacht Show | 1 | Event | 4.2.2 |  | Meetings, planning and content outputs (video and print) | [14 empty] | 1 | Burgess held a bespoke Blue Marine stall at the Monaco Yacht Show. Featuring Blue Marine assets (video and photo) and having TSWB on Ipads for visitors
U.18 | Support of freediving for 24 children in Sao Tome with Zandile Ndhlovu | 24 | Beneficiaries | 4.2.1 |  | Images and attendance record | [14 empty] | 24 | Coordinated through Mission William, Blue Marine funded Zandile's travel which allowed her to teach outside of South Africa for the first time. Taught lesson of 24 students
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson did you add these number for 2020/21 or have I done this by accident? Reply: hmmm I don't think I put these in
Note on W12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Anna Hughes do we know the number of attendees for this line and the line below? It's possible that the line below is being captured in the solent logframe but not sure if you know the answer to that too? Reply: Added numbers. The 4280 is high confidence, 30 for tech4nature I'm not as sure. Will tell Louise that I have included this :) Reply: Awesome ok - I'm going to put in a line below for number of stakeholders reached and chuck those numbers into there
Note on W19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Anna Hughes is this 24 representative of the students taught? I think if this line is counting beneficiaries I'm more inclined to count as 1 Reply: This is children. Happy to count as 1 (ie Zandi) Reply: Ok great thanks for confirming, unfortunately I think we need to count as 1 - but I'm going to include the 24 students in the main text

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking | [11 empty] | Final Barclays Reporting
[15 empty] | Defined in original outputs |  |  |  | Unplanned |  |  |  | Totals |  |  |  |  | Defined in original outputs
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Progress achieved in 2020 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2020 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | Impact Indicator | Progress achieved in Y1 (2020+2021) | Progress achieved in Y2 (2022) | Progress achieved in Y3
Output 1 | 6 | 10 | O.1 | O.1.1 | 0% | 0% | 0% | 0% | 200% | 0% | 100% | 200% | 200% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | 0% | 0% | 0% | 0% | 117.5% | 0% | 100% | 117.5% | 117.5% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1 | 0 | 0 | 0
Output 3 | 3 | 7 |  | O.1.3 | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2 | 0 | 0 | 0
Output 4 | 4 | 8 |  | O.1.4 | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3 | 0 | 0 | 0
Output 5 | 3 | 7 | O.2 | O.2.1 | 0% | 0% | 0% | 0% | 50% | 0% | 50% | 50% | 50% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0
Output 6 | 2 | 6 |  | O.2.2 | 0% | 0% | 0% | 0% | 18% | 0% | 20% | 18% | 18% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1 | 0 | 0 | 0
Output 7 | 3 | 7 |  | O.2.2 | #REF! | 0% | 0% | 0% | 10% | 0% | #REF! | #REF! | #REF! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2 | 0 | 0 | 0
Output 8 | 3 | 7 | O.3 | O.3.1 | #REF! | 0% | 0% | 0% | 100% | 0% | #REF! | #VALUE! | #VALUE! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3 | 0 | 0 | 0
Output 9 | 4 | 8 |  | O.3.2 | #REF! | 0% | 0% | 0% | 100% | 0% | #REF! | #REF! | #REF! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 0
Output 10 | 1 | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2 | 0 | 0 | 0
|  |  |  | O.4.2 | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3 | 0 | 0 | 0
|  |  |  | O.4.3 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1 | 0 | 0 | 0
|  |  |  | O.5.2 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2 | 0 | 0 | 0
|  |  |  | 0.5.3 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3 | 0 | 0 | 0
Outputs: | 10 |  | O.6 | O.6.1 | #REF! | 0% | 0% | 0% | 0 | 0% | 100% | 0% | 0% | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 0 | 0
|  |  |  | O.6.2 | #REF! | 0% | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1.1 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1.2 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 0 | 0
|  |  |  | O.7.2 | #REF! | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.1 | 0 | 0 | 0
|  |  |  | O.7.3 | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #REF! | 0.4306% | 0% | 0% | 0% | 0.4306% | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.3 | 0 | 0 | 0
|  |  |  | O.2.2 | #REF! | 100% | 0% | 0% | 0% | 100% | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3.1 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3.2 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3.3 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4.1 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4.2 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4.3 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1.1 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1.2 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1.3 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.1 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.2 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3.1 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3.2 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3.3 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4.1 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4.2 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4.3 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 4.1.1 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 4.1.2 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 0 | 1002035 | 504154 | 0 | 0 | 0 | 4334 | 1002035 | 0 | 1002035 | 10200 | 4.2.1 | 0 | 1000235 | 500001
[14 empty] | 4.2.2 | 0 | 1 | 2 | 13 | 0 | 0 | 4 | 10 | 3 | 4 | 7 | 12 | 4.2.2 | 1 | 0 | 6
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0.58 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1.6 | 4.2.3 | 0 | 0 | 0.58
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4.3.1 | 0 | 0 | 0
[14 empty] | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 0 | 0
[14 empty] | 4.4.1 | 0 | 0 | 5 | 0.83 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 51.5 | 5.1.1 | 0 | 0 | 0
[14 empty] | 4.4.2 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 5.1.2 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1.3 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2.1 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2.2 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3.1 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3.2 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3.3 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1.1 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1.2 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1.3 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1.5 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4.1 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4.2 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4.3 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0