## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01 | Lyme Bay Reserve Consultative Committee meeting
2022-04-01
2022-05-01
2022-06-01
2022-07-01 | Monitoring surveys by UoP
2022-08-01 | Lyme Bay Fishermens CIC registered
2022-09-01
2022-10-01 | Lyme Bay Reserve Consultative Committee meeting
2022-11-01 | Lyme Bay Fishermens CIC bid to MMO approved
2022-12-01
2023-01-01
2023-02-01 | Lyme Bay Reserve case study published as part of BLUEprint for MPAs
2023-03-01 | Lyme Bay Reserve Consultative Committee meeting
2023-04-01
2023-05-01
2023-06-01 | Lyme Bay Reserve Consultative Committee meeting
2023-07-01
2023-08-01 | Lyme Bay Impact paper submitted to ICES Journal of Marine Science
2023-09-01 | Dorset Seafood Festival
2023-10-01 | Revised MoU agreed with fishermen
2023-11-01 | Lyme Bay Reserve Consultative Committee meeting
2023-12-01 | Lyme Bay Impact paper published?
2024-01-01

## Impact and Outcome
Impact | Develop the Lyme Bay model from its current, successful example of voluntary fisheries management into a demonstrator of best-practice fisheries management with national uptake.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | The principles of the Lyme Bay model are adopted by Defra based on scientific evidence and management across IFCA boundaries are harmonised. Reserve Seafood is an adoptable business model and the voluntary codes for the Lyme Bay Reserve are legally adopted by the IFCA. | OC.0.1 | Defra adopts key fisheries management and conservation principles, based on convincing scientific evidence that demonstrates the benefits of marine conservation - no longer valid post-Barclays | 1, 2, 3, 4 | 3.4.1 | 3
|  |  | OC.0.2 | The local IFCA incorporates the principles from the voluntary code of conduct into regulation based on the evidence that demonstrates the efficacy of the code of conduct - no longer valid post-Barclays | 5, 6
|  |  | OC.0.3 | The Lyme Bay Reserve Seafood label is a self-sustaining business model, with the local fishery under a recognised national certification the incorporates biodiversity and conservation considerations - no longer valid - Reserve Seafood assets handed over to fishermen | 7
|  |  | 1 | Biodiversity benefits of the Reserve continue to be quantified.
|  |  | 2 | Publication of a scientific, peer-reviewed paper and accompanying public-facing document, on the ecological and socio-economic impacts of the Lyme Bay Reserve management model.
|  |  | 3 | Publication of a Lyme Bay Reserve management ‘How to’ guide to help other communities and fishermen apply the Lyme Bay model.
|  |  | 4 | Five-year Reserve management plan published.
|  |  | 5 | IFCAs enshrine part of the codes of conduct in law to strengthen best-practice management.
|  |  | 6 | The Government moves to an inshore fisheries management regime that reflects some of the principles of the Lyme Bay model. This work is now being progressed through the SARF and national fisheries programme.
|  |  | 7 | Reserve Seafood infrastructure and transport scheme becomes self-sufficient initiative managed by Lyme Bay fishermen - Project completed and handed over to LBFCIC in January 2023. No further action to be taken.

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Biodiversity benefits of the Reserve continue to be quantified. | O.1.1 | Ecology monitoring conducted, with X number of surveys completed inside/outside reserve |  | Number of surveys | 3.4.1 |  |  |  |  | 2 | 1 scientific paper (potting study) 1 consultation response |  |  | 0 | 60 sites surveyed in July/August 2021 by University of Plymouth. | 60 | Ecological surveys carried out by UoP in July/August 2022 | 0 | Q1: 65 towed video transects and 24 BRUV surveys in July/August 2022 by University of Plymouth. | 0 | Q1: 65 towed video transects and 24 BRUV surveys in July/August 2022 by University of Plymouth.
|  |  | O.1.2 | Results summarised [quantification of biodiversity benefits from the Reserve; number of reports] |  | Number of reports | 3.4.1 | [8 empty] | 0 | Waiting for receipt of report from UoP – report on In Yr 3. | 2 | 2021 and 2022 monitoring reports submitted by UoP | 2 | Q3: 2021 monitoring report submitted to Blue Marine by University of Plymouth (March 2023). Q4: 2022 monitoring report submitted to Blue Marine by University of Plymouth (June 2023). | 2 | Q3: 2021 monitoring report submitted to Blue Marine by University of Plymouth (March 2023). Q4: 2022 monitoring report submitted to Blue Marine by University of Plymouth (June 2023).
|  |  | O.1.3 | NEW JULY 2022 Number of pieces of evidence provided outlining biodiversity benefits of the reserve |  | Number of pieces of evidence | 3.4.1 | [8 empty] | 2 | 2 Scientific papers published, 1 in Aug 2021 (resilience to extreme climatic events Sheehan et al), 1 in Sept 2021 (Impact of banning mobile gear on fished and non-fished species Davies et al). | 1 | Presentations to IMPAC5 (Feb 2023) on Lyme Bay Recovery by Emma Sheehan, Bede Davis and Adam Rees / Publication of Lyme Bay Reserve Impact paper (June 2023) | 0 | Q3: Presentation at IMPAC5 by Dr Bede Davies on 14 years of monitoring in Lyme Bay Reserve (Feb 2023)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Towed-video surveys inside and outside the Reserve completed and analysis of species and habitat health. This research is part of a 12-year ecological dataset by Plymouth University. |  |  | Complete
|  |  | A.1.2 | Summary of results from annual monitoring provided to BLUE. |  |  | Complete
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sam Fanshawe am I right in thinking that we will then disseminate this report to a wider audience? If so, it might be best to include this as 'done' once we have released the report Reply: @Sam Fanshawe - me again 😉 are these reports that get disseminated publicly? Reply: They will be uploaded to the Lyme Bay Reserve website in spring 2024 Reply: great thanks Sam
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have changed this from 1 to 0 because this wasn't us presenting (but still good to be aware of). Unless we paid for this we can't report it in here

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Publication of a scientific, peer-reviewed paper and accompanying public-facing document, on the ecological and socio-economic impacts of the Lyme Bay Reserve management model. | O.2.1 | Academic paper published [number of, in what journal and it's reach] |  | Papers published | 3.4.1 | [8 empty] | 0 | Not complete yet | 1 | Due to be published September 2023 | 1 | Draft manuscript submitted for publication in ICES Journal of Marine Science in August 2023: "Functional MPAs for fishers, fish, and essential fish habitats. Lessons from Lyme Bay to inform policy, management, and monitoring worldwide". Manuscript accepted for publication in December 2023. Date of publication not yet known.
|  |  | O.2.2 | External facing 'Gold Standard' document is published [number of, reach/downloads/distrbution] |  | Number of documents released | 3.4.1 | [8 empty] | 0 | Not complete yet | 1 | Due to be published September 2023 | 1 | The MPA Blueprint Lyme Bay Case Study effectively completed this action - published February 2023.
|  |  | O.2.3 | Number of press/article features |  | Number of press articles | 1.4.2 | [8 empty] | 0 | Not complete yet |  | To be reported on in September 2023 |  | This seems to be a very difficult metric to track as I'm not sure the Comms team have any way of doing this - we should ask Jo if they can set up an agency to track Blue in the media along with key words like Lyme Bay, Solent Seascape, etc
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Collation of information and data gathered since the Reserve was created in 2008 by Plymouth University for the creation of an academic paper. This will include data on ecological, economic and social impact of the MPA itself and BLUE project. |  |  | Complete
|  |  | A.2.2 | Writing of accompanying public-facing document by BLUE highlighting Lyme as a ‘Gold-Standard’ MPA. |  |  | Complete
|  |  | A.2.3 | Submission of the academic paper. |  |  | Complete
|  |  | A.2.4 | Press release creation and media to accompany publication. The aim is to change perceptions of fisheries and conservation management within MPAs. |  |  | In Progress

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Publication of a Lyme Bay Reserve management ‘How to’ guide to help other communities and fishermen apply the Lyme Bay model. | O.3.1 | Number of public-facing guides published and available online |  | Number of assets released | 3.4.1 | [8 empty] | 0 | In final prep – being launched in Feb 2023 |  | Lyme Bay 'guide' designed and ready to be published in Feb 2023 along with MPA BLUEPrint | 0 | Q3: Lyme Bay Case Study published in Feb 2023 as one of several project case studies to support the MPA BLUEPrint |  | Lyme Bay 'guide' designed and ready to be published in Feb 2023 along with MPA BLUEPrint
|  |  | O.3.2 | Number of people reached through media assets produced and their impact (social media report stats) |  | Reach | 4.2.1 | [8 empty] | 0 | As above, dependent on release. |  | As above, dependent on release. | 2300 | Views on social media the day of the launch of the MPA BLUEPrint
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Collection of information and data to create a ‘How to’ guide for the Lyme Bay model as a case study. This will form one of several project case studies published as part of the BLUEprint for MPAs |  |  | Complete
|  |  | A.3.2 | Creation of media assets (infographics and short clips) to promote the guide. |  |  | Complete
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have put to 0 because has been counted in another tab

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Five-year Reserve management plan published. | O.4.1 | Number of Committee meetings |  | Number of meetings | NA - progress | Meeting minutes |  |  |  | 2 | Completed in November 2020, February 2021 |  |  | 2 | Completed in Nov 2021, March 2022, due for one on y3 | 2 | Committee meetings in Oct 2022 and March 2023 | 3 | Committee meeting Oct 2022, March 2023 and June 2023 complete | 4 | Oct 22 and March 22
|  |  | O.4.2 | New management plan produced with Committee sign off - no longer being progressed post-Barclays |  | Number of plans produced | 3.2.1 | Management plan |  |  |  | 0 | One-year management plan drafted |  |  | 0 | Will be handed over to the fishermen. Refusing to talk for 18 months. One has been drafted by BLUE but putting at zero until management plan is in better place.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | Meetings with Committee to develop five-year management plan to include governance, fisheries and conservation management and long-term sustainability plan for Reserve Seafood.
|  |  | A.4.2 | Writing of the management plan by BLUE.
|  |  | A.4.3 | Sign off of final version by Committee.

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
5 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | IFCAs enshrine part of the codes of conduct in law to strengthen best-practice management. | O.5.1 | Envrionmental and economic data compiled (number of datasets) - not feasible or funded - remove |  | Number of pieces of evidence | 3.4.1 | [8 empty] | 0 | Haven’t collected data specific to this |  |  |  | No work planned for Y3
|  |  | O.5.2 | Number of meetings with fishermen and Committee |  | Number of meetings | NA - progress | [8 empty] | 1 | Management committee meeting (Oct 2021) – dedicated fishermen IFCA management meeting. | 3 | Hold 3 Lyme Bay Committee meetings with fishermen and IFCAs | 3 | Committee meeting Oct 2022, March 2023 and June 2023 complete
|  |  | O.5.3 | Amount of evidence submitted |  | Number of pieces of evidence | 3.4.1 | [8 empty] | 0 | About to respond to byelaw extending trawling ban – will submit in July – consider for reporting in Y3. |  | Respond to Consultation on Bottom Towed Fishing Gear Closed Areas in August 2022 | 1 | Response submitted to Consultation on Bottom Towed Fishing Gear Closed Areas in August 2022
|  |  | O.5.4 | Number of presentations/workshops conducted to IFCA |  | Number of outreach activities | 4.2.2 | [8 empty] | 0 | Letter sent to southern IFCA and Devon and Severn IFCA in May 2022, calling for legal underwriting of voluntary code. Meeting set for Aug 4th following letter. |  | Lyme Bay Fisherman's CIC are now holding meetings directly. No further action to be taken. |  | No work planned for Y3 | 0 | Letter sent to southern IFCA and Devon and Severn IFCA in May 2022, calling for legal underwriting of voluntary code. Meeting set for Aug 4th following letter.
|  |  | O.5.5 | Changes in regulation/legislation following engagement with IFCA (number of policies influenced etc.) |  | Number of legislative changes | 3.4.3 | [8 empty] | 0 | Still to come. Whelk pot limit (previously not statutory) has been proposed close to voluntary CoC in a Byelaw, not yet signed off by Secretary of State soon. Due to be finalised in Y3. |  | Influence outcome of Potting Byelaw. |  | Whelk pot limit (previously not statutory) has been proposed close to voluntary CoC in a Byelaw. As at July 2023 the Byelaw had not yet been signed off by Secretary of State.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Collation of all data carried out over the past 10 years that underpin the value of the codes for fisheries and biodiversity. This will include any economic evidence indicating rewards from Reserve Seafood and dedication to the codes by fishermen. BLUE will also analyse spatial data of fishing patterns from the iVMS monitoring app on board each vessel.
|  |  | A.5.2 | Meetings with fishermen and the Committee to build consensus for enshrining codes.
|  |  | A.5.3 | Submission of evidence via formal bylaw consultations for both IFCAs as and when they occur highlighting the benefits of the codes for fisheries and conservation. This will include evidence in support of harmonising regulations for certain species across the Reserve. This will include presentations and/ or workshops to IFCA committees with Reserve fishermen, MMO and Defra. |  |  | Complete
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson Not sure where this text came from, there wasnt any plan to do this as far as a I was aware Reply: Hi Sam - this was taken from the Barclays report - it's based on the first version that went to print (i.e. before the projects started) so is it possible this migh thave been dropped since then?

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
5 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | The Government moves to an inshore fisheries management regime that reflects some of the principles of the Lyme Bay model. This work is now being progressed through the SARF and national fisheries programme. | O.6.1 | Number of meetings with Defra/Government officials |  | Number of meetings | NA - progress | [8 empty] | 2 | Fisheries Minister visited Lyme Bay fishermen in Nov 2021. Fishermen and Blue Marine met Defra in ~Apr 2022. |  | This work is now being progressed through the SARF programme |  |  | 1 | apr 2022 meeting with fishermen and Defra
|  |  | O.6.2 | Number of meetings, presentaions, workshops etc. provided to key decision makers |  | Number of outreach activities | 4.2.2 | [8 empty] | 0 | Accounted for above – consider |  | See above
|  |  | O.6.3 | Number of wider stakeholder meetings |  | Number of outreach activities | 4.2.2 | [8 empty] | 0 |  |  | See above
|  |  | O.6.4 | Adoption of management regime that reflects Lyme Bay principles by Government (changes to regulation/management plan improvements etc.) |  | Number of fshing agreements amended | 3.2.3 | [8 empty] | 0 | Working up to in outputs above |  | See above
|  |  | O.6.5 | NEW IN JULY 2022 Number of new pieces of evidence to support move to better fisheries management regime |  | Number of pieces of evidence | 3.4.1 | [8 empty] | 1 | Letter submitted to MMO to change sole quota allocation in Lyme Bay linking to national policy (May 2022). |  | See above |  |  | 1 | Letter submitted to MMO to change sole quota allocation in Lyme Bay linking to national policy (May 2022).
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Use of Lyme and BLUE’s network of projects to showcase the principles of the Lyme model. This will involve engagement with policy makers within Defra and feed into the Government’s review of inshore fisheries management. |  |  | In Progress
|  |  | A.6.2 | Assistance and advice to Government, IFCAs and regional marine regulators to help understanding of Lyme Bay style governance systems and applicability to other MPAs.This could include presentations and/or workshops with interested IFCAs and other fisheries bodies across the UK. |  |  | In Progress
|  |  | A.6.3 | Meetings with other communities who want to adopt the system/model for their MPA and use of the published paper and ‘How to’ guide to promote the benefits of the model.

## Output 7
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 | Reserve Seafood infrastructure and transport scheme becomes self-sufficient initiative managed by Lyme Bay fishermen - Project completed and handed over to LBFCIC in January 2023. No further action to be taken. | O.7.1 | Number of fish boxes transported for fishermen | 0 | Boxes | NA - progress | [13 empty] | Transport scheme handed over to Lyme Bay Fisherman's CIC. Project complete.
|  |  | O.7.2 | Reserve Seafood van gifted to the Lyme Bay fishermen in July 2022 - project complete | 15 | Non-monetary beneficiaries | 4.1.2 | [8 empty] | 15 | 15-20 local fishermen using the van provided by Blue Marine for seafood deliveries. |  | Van gifted to the Lyme Bay Fisherman's CIC |  | Van gifted to the Lyme Bay Fisherman's CIC in July 2022. Project complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1 | Provide a support programme for logistics and brand licensing to fishermen’s associations around the coast. This will allow fisheries to adopt the brand for their landings and benefit from premium prices to support their responsible fishing activities. |  |  | Not started | No longer valid - Reserve Seafood model not sustainable so not being promoted
|  |  | A.7.2 | Establish an appropriate auditing process to ensure that the codes for low-impact fishing methods and vessel traceability are being adhered to as essential for Reserve Seafood brand reputation. |  |  | Not started | No longer valid - Blue Marine is funding Lyme Bay Fishermens CIC to market their catch locally
|  |  | A.7.3 | Provide brand marketing support through communications and existing distribution and customer networks. |  |  | Not started | No longer valid - Blue Marine is funding Lyme Bay Fishermens CIC to market their catch locally
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sam Fanshawe do you know roughly how many fishermen are using this van? I think we can say that they are beneficiaries from our work here Reply: not exactly but probably 15-20

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Hosted Danish NGO visit to Lyme Bay showcasing voluntary code of conduct and collaborative management with fishermen (June 2022) – Five participants including President and CEO. – 1 x outreach activity (4.2.2), 5 x stakeholders reached (4.2.2) | 1 | Number of outreach activities | 4.2.2 | [8 empty] | 1 | Hosted Danish NGO visit to Lyme Bay showcasing voluntary code of conduct and collaborative management with fishermen (June 2022) – Five participants including President and CEO.
U.2 | Stakeholders reached by U.1 | 5 |  | 4.2.1 | [8 empty] | 5 | Hosted Danish NGO visit to Lyme Bay showcasing voluntary code of conduct and collaborative management with fishermen (June 2022) – Five participants including President and CEO.
U.3 | Presentations to Sussex Bay webinar (November 2021), All Party Parliamentary Group (February 2022), Local Government Association Coastal Special Interest Group (March 2022) on Lyme Bay model | 3 | Number of outreach activities | 4.2.2 | [8 empty] | 2 | Presentations to * Sussex Bay webinar (November 2021), Display at: Dorset Seafood Festival (Sept 2022) |  | Display at: Dorset Seafood Festival (Sept 2022) / West Bay Discovery Centre (Mar-Oct 2023) Presentations to: Charmouth Heritage Coast (Feb 2023) / West Bay Discovery Centre (April 2023) | 3 | Display at: / West Bay Discovery Centre (Mar-Oct 2023) Presentations to: Charmouth Heritage Coast (Feb 2023) | 2 | * All Party Parliamentary Group (February 2022), * Local Government Association Coastal Special Interest Group (March 2022) on Lyme Bay model
U.4 | Project engagement (over lifetime of project) | 10000 | Reach of outreach activities + tools | 4.2.1 | [8 empty] | 17094 | 2499: Twitter following 1916: Facebook likes 12679: Website views |  |  |  |  | 17094 | 2499: Twitter following 1916: Facebook likes 12679: Website views
U.5 | Film release | 1 | Number of outreach activities | 4.2.2 |  |  |  |  | 1 | Film released in Y1
U.6 | Reach (general events reach of outreach activities) |  | Number of stakeholders reached | 4.2.1 |  |  |  |  | 7500 | Number of views to end of y1 |  |  | 8700 | Display at: Dorset Seafood Festival (Sept 2022) seen by 8700 people |  | Display at Seafeast Dorset Seafood Festival (Sept 2023) | 10000 | Display at Seafeast Dorset Seafood Festival (Sept 2023)
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sam Fanshawe these are great, is there anyway we can find out how many people have seen these displays? Reply: @Appin Williamson 8,700 people saw the displays at the Seafood Festival last year - not sure where to put this figure though Reply: Wow - amazing. OK great I will add this to the U.6 line as that is stakeholders reached (we can use it across multiple events). I am going to put it in last year's column
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Picked a number at random here!

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 3 | 7 | O.1 | O.1.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 2 | 6 |  | O.1.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 5 | 9 | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 5 | 9 |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 2 | 6 |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | #DIV/0! | #DIV/0! | #REF! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 7 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | 0% | 0% | 0% | #REF! | #DIV/0! | #REF! | #REF! | 100% | #REF! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 2 | 3 | 5 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 3 | 3 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 0 | 2300 | 7500 | 25799 | 10000 | 2300 | 43299 | 45599 | 0 | 17094 | 0 | 17094
[14 empty] | 4.2.2 | 0 | 0 | 0 | 1 | 3 | 3 | 0 | 7 | 7 | 0 | 2 | 0 | 2
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0