## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | BLUE's M&E Guide.pdf
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 |  | OC.0.1
OC.0.2
OC.0.3

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | MPAs/Offshore MPAs | O.1.1 | Newly proposed marine protected areas/NTZs | 4 | km2 | 1.1.1 | Legislation documentation | [12 empty] | Government consultation on five proposed HPMAs in English waters | 3 | Implementation of four HPMAs | 0 | Three HPMAs in England confirmed. This was a little worse than what we hoped for given the governemnt had said they wanted to do five. However, they have decided to extend the HPMA programme - which was a key request of ours.
|  |  | O.1.2 | Marine protected areas with management plans |  | management plans | 1.2.1 | Management plan | [11 empty] | 0 | Four offshore MPAs (the Dogger Bank, South Dorset MCZ, the Canyons MCZ & Inner Dowswing, Race Bank and North Ridge SAC) which has doubled the amount of UK waters where trawling is banned. The sites are 12,300, 191, 663, 845 square kilometre respectivly. These all came into force in June | 13 | The next 13 offshore sites will have managmenet measures introduced | 0 | The MMO has consulted on measures across the remaining 13 sites for some gear types with the others to come. Management measures will be fone for trawling by end of 2023
|  |  | O.1.3 | Number of important habitats under increased protection |  | Species | 1.3.3 | Reports outlining areas now under protection | [11 empty] | 0 | N/A - I don't think we will do this |  | N/A - all species within sites | 0 | N/A - all species within sites
|  |  | O.1.4 | New evidence compiled to support protection |  | Reports/investigations/field surveys etc | 1.4.1 | Reports/survey reports etc | [11 empty] | 5 | A consultation response that supported teh designation of HPMAs in principle and relating to the five specific sites beign consulted on as part of the HPMA trial (Dolphin Head, Lindisfarne, Northeast of Farnes Deep, Allonby Bay and the Inner Silver Pit) was submitted. Furthermore in MArch 2023 we submitted a response to the stages 2 & 3 of the offshore MPA consultaiton - which concenred proposed measures for specific gear types in 13 sites and a call to evidence for the remaining sites. |  | Stage two and three of MMO process completed- all reamining offshore MPAs have management mesures in place. Stage 3 and four consultation will be done by Blue | 0 | As expected this is coming along reasonably well.
|  |  | O.1.5 | Number of stakeholders reached with marine conservation messaging |  | Stakeholders | 4.2.1 | Social media & other stats, workshop attendee lists | [12 empty] | N/A |  | N/A | 0 | N/A
|  |  | O.1.6 | Number of outreach tools/activities developed |  | Activities (workshops, media outputs etc) | 4.2.2 | Screenshots of media outputs, emails sent around ot workshop attendees etc | [12 empty] | N/A |  |  | 0 | N/A
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on Z4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jonny Hughes unless we are the cause that these were designated we don't include here
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not management plans, just management measures, consider changing impact indicator
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jonny Hughes this impact indicator specifically is to determine whether a new management plan is in place because of our work - is this the case here? Reply: @Jonny Hughes assuming no?
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jonny Hughes please provide details of how this 5 has been calculated Reply: I looked at the site descriptions and took them from there Reply: I'm referring to when these consultations were submitted and for which sites Reply: @Jonny Hughes please provide more details - when were these done and which sites did we campaign for

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Increase understanding of and promote a just transition to lower impact fisheries | O.2.1 | New pieces of evidence (in the form of five case studies, prawns, scallops, Sussex (post closure), transition from commercial fishing to other jobs at sea, Turkey possible collab with FFI) | 5 | Pieces of evidence | 3.4.1 | [12 empty] | 0 | Scottish draft underway, other two at early stages. | 5 | Confirm Agreemeent with EFTECH to commissioning them to do the conduct case studies or help set up a framewok | 0 | 3 UK transition case studies underway with a farmwork and outputs and report scheduled December 2023 will have 3 pieces of evidence in November 2023
|  |  | O.2.2 | Number of stakeholders [members of the public/govt/NGOs etc.] reached with marine conservation messaging through in-person and/or digital engagement work (disaggregated by gender, if possible) | 100 | Stakeholders | 4.2.1 | [12 empty] | 0 | Drafts not finished so no outreach |  | An NGO workshop is planned for March to try and develop joint positions and see where different organsiations are focusing Scottish tansition case study workshop | 42 | NGO workshop was consdcuted in March both in person and onlien atendess (29 people). A folow up online meetign was conducted in June 2023 (15 people) Scottish transition case study workshop was condcuted on March 23 (13 people)
|  |  | O.2.3 | Number of outreach tools or activities delivered (including workshops, reports, media outputs, app development etc.) | 1 | Outreach tools/activities | 4.2.2 | [12 empty] | 0 | Drafts not finished so no outreach | 1 | Transition Symposium planned for Oct 23 | 0 | n/a
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1
A.2.2
Note on Y5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson Should the value be the numbers of attendees at each workshop and online event? So the numbers ive included in brackets in column next to it?>

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
6 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Our Seas Campaign | O.3.1 | New evidence compiled and distributed to policy makers to support protection |  | Quantity of reports/investigations/field surveys | 1.4.1 | Copies of reports or other evidence, reports, consultation responses | [11 empty] | 5 | FCP - Respnse submitted REM response submitted cod consultation resposne quota allocation resposn e Scottish fisheries and climate change consultation response | 3 | HPMA consultation reposne Submit coaliton evidence to RAINE petition committee letter to minister cod COnustlation | 5 | Hpma consutaltion submitted 20th April 2023 evidecne submitted to RAINE committee sep 2022 Cod consultation Scottish Biodiversity consultation response Decemeber VMS <12M consultation response submitted
|  |  | O.3.2 | Area of habitat across which mobile gear has been banned |  | km2 | 3.1.3 | Map/documentation | [13 empty] | 13 | Offshore MPA trawling bans completed | 0 | Consultaitons for banning bottom towed fishign in MPAs has been delayed by Government . Expected to publish January 2024
|  |  | O.3.3 | Number of stakeholders reached with marine conservation messaging |  | Stakeholders | 4.2.1 | Social media & other stats, workshop attendee lists | [14 empty] | social post using wild isle asset to increase petition signatures Social media pack prodcued MSP E-ACTION for inshore cap | 3801 | 800 petition signatories between March and April 2023 3000 emails sent to MSPs following creation of social media pack Social media pack created MSP eaction created and share with signatory base resultingin over 3000 emials to MSPs being sent from Scottish residents.
|  |  | O.3.4 | Number of outreach tools/activities developed |  | Activities (workshops, media outputs etc) | 4.2.2 | Screenshots of media outputs, emails sent around to workshop attendees etc | [11 empty] | 2 | Our seas campaign song produced Nov 22 Our Seas film time limit public premier (March 2022) | 4 | Coastal video testimonies project Film screenig road trips | 1 | CTP completed November 2023(Over 50 testimonies and photographic portraits of people from all over Scotland) and ready to be distributed in Q1 of 2024 Launched at a parliamentary event in 2024
|  |  | O.3.5 | Coalitions/working advisory groups etc formed (number of coalitions/working groups) | 1 | Coalition | 5.4.2 | [14 empty] | 1 |  | 0 | n/a
|  |  | O.3.6 | Coalitions/working advisory groups etc formed (number of member organisations/representatives) |  | Number of member organisations | 5.4.3 | [12 empty] | 120 | 120 member organisations part of our seas coalition | 120 | Increase member organisation - started year at 120 member orgs | 16 | As of of Decemebr 2023 there 136 Our Sea member organsiations
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1
A.3.2
A.3.3
A.3.4
A.3.5
A.3.6
Note on Y6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson can I add in increased number of petition signatures here? Also there was one social media pack created so should that be added with value of 1 too? Reply: Yes correct - I've added them together so it now says 801 (the value of this cell needs to just be a number as it gets added up later) - when you say increased number of petition sigantures, what do you mean?
Note on Z6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson is the MSP e action in the right place here and how do i report value if 3000 emails were sent to msp off the back of that ?
Note on V7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joe Richards please provide months here Reply: Also - do we have reach of the film/campaign song? Reply: The Time lLmit public premier was held in glasgow in March 2022 and has been viewed over 1k times (Pretty lame but hasn't properly bee promotes / launched yet) Reply: The Song hasn't actually be released yet due to final approvals needed. but song and music video was produced / finalised November 2022 Reply: Ok fab - would you be happy to add those in? The views etc will need to go in a new line specifically for reach. Let me know if you have any questions about it!
Note on Y9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joe Richards I have changed this to 120 and 14 from percentages, is that correct? Reply: @Joe Richards

## Output 5 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 |  | O.5.1
O.5.2
0.5.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8

## Output 6 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 |  | O.6.1
O.6.2
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 |  | O.7.1
O.7.2
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 |  | O.8.1
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–June 2023) |  | Progress achieved in Y3 (July 2022–June 2023)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
9 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Offshore Marine Reserves | O.4.1 | Newly proposed marine protected areas/no-take zones (km2) |  | km2 | 1.1.1 | [16 empty] | 0 | n/a
|  |  | O.4.2 | Newly created/gazetted marine protected areas/no-take areas created |  |  | 1.1.3 | [12 empty] | 0 | Four offshore MPAs were targetted through a legal campaign by BLUE (also boulders dropped by Greenpeace) to achieve protection of. Achieved the below byelaws but they are not new MPAs so this is zero. Instead, recorded under the impact indicator 3.1.3 (bellow) The Dogger Bank: 12300km2 (all protected) South Dorset MCZ: 191km2 (all protected) Canyons MCZ: 663km2 (of which 574km2 protected) Inner Dowsing, Race Bank and North Ridge SAC: 845km2 SAC, (of which 351km2 protected by new byelaw) This has doubled the amount of UK waters where trawling is banned. These all came into force in June 2022 | 13 | Thirteen new offshore MPAs will be implemented. We will campaign to ensure that managment measures are actually effective | 0 | Consultations completed. Logging of MPs done. Waiting for DEFRA outcomes.
|  |  | O.4.3 | Biodiversity hotspots under proposed/desginated/created protection (quantity) |  |  | 1.3.1 | [12 empty] | 4 | Four identified offshore MPAs are key biodiversity areas | 13 | Same as above | 0 | Same as above
|  |  | O.4.4 | Number of important habitats [nursery grounds/areas of nutrient-rich upwelling etc] under [proposed/designated/created] protection (quantity) |  |  | 1.3.3 | [16 empty] | 0 | n/a
|  |  | O.4.5 | [UK/Global] Uptake of new evidence to support protection (quantity of policy instruments/MOUs etc) |  |  | 1.4.3 | [16 empty] | 0 | n/a
|  |  | O.4.6 | Number of regional, national and international legal agreements which have been influenced (e.g. harvest management rules, RFMOs) | 2 |  | 3.2.3 | [12 empty] | 2 | NEAFC and IOTC work |  |  | 4 | Coastal states, UK-EU, Trilateral BBNJ
|  |  | O.4.7 | Number of outreach tools or activities delivered (including workshops, reports, media outputs, app development etc.) |  |  | 4.2.2 | [16 empty] | 0 | n/a
|  |  | O.4.8 | Percentage of individuals reached with public engagement work who took action/donated/changed their seafood buying behaviour |  |  | 4.2.3 | [16 empty] | 0 | n/a
|  |  | O.4.9 | Area of habitat across which mobile gear, harmful or illegal fishing practices have been banned |  |  | 3.1.3 | [12 empty] | 13416 | Four offshore MPAs were targetted through a legal campaign by BLUE (also boulders dropped by Greenpeace) to achieve protection of: The Dogger Bank: 12300km2 (all protected) South Dorset MCZ: 191km2 (all protected) Canyons MCZ: 663km2 (of which 574km2 protected) Inner Dowsing, Race Bank and North Ridge SAC: 845km2 SAC, (of which 351km2 protected by new byelaw) This has doubled the amount of UK waters where trawling is banned. These all came into force in June 2022 |  |  | 0 | 466, 27.6, 491.8 (HPMA area total) - new areas
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1
A.4.2
A.4.3
Note on V5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These areas were gained by downloading the byelaw shapefiles into ArcGIS and measuring the area of the shapefile. I can't find these figures anywhere online
Note on Z9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jasmine Finbow @Jonny Hughes have these been influenced due to our work? The number here says 4 but 3 are listed in the description Reply: Sorry, forgot to put a comma between Trilateral and BBNJ Reply: Thanks @Jasmine Finbow - would it be possible to include a bit more detail on what these agreements are and what we influenced in them please?
Note on V12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These areas were gained by downloading the byelaw shapefiles into ArcGIS and measuring the area of the shapefile. I can't find these figures anywhere online
Note on Y12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This said 985.4 - however have changed to zero as this was not just due to us

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  |  | Unplanned |  |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Progress achieved in 2020 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2020 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected
Output 1 | 4 | 8 | O.1 | O.1.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 6 | 10 |  | O.1.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 9 | 13 |  | O.1.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 3 | 7 | O.2 | O.2.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | O.2.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | O.2.3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.3.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 |  | O.3.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 13416 | 0 | 0 | 0 | 0 | 0 | 13416 | 0 | 13416 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 0 | 0 | 3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
[14 empty] | 4.2.2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[14 empty] | 5.4.3 | 0 | 0 | 120 | 16 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0