## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01 | Presented at Sturgeon Irish WT Webinar to 40 participants
2023-07-01
2023-08-01
2023-09-01
2023-11-23 | Input into structured decision making process for sturgeon re-introductions

## Impact and Outcome
Impact | Build the case to restore critically endangered European sturgeon and use this as a flagship species to encourage further rewilding of lost marine species.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | European sturgeon is effectively protected in UK waters, with a template developed for rewilding lost marine species in the UK. UK rivers and estuaries have suitable conditions to enable successful sturgeon spawning and egg development. | OC.0.1 | Defra and other key agencies/authorities (e.g. Cefas) adopt regulation measures that effectively protect native sturgeon. | 4, 8
|  |  | OC.0.2 | BLUE produces a publicly available template on rewilding lost marine species, based on IUCN guidelines and project research findings. | 6
|  |  | OC.0.3 | BLUE has provided evidence and recommendations to improve UK rivers and estuaries to suitable conditions that support sturgeon spawning/egg development. | 1, 2, 3, 5, 7
|  |  | OC.0.4 | Sturgeon have access to critical habitat following BLUE's recommendations/actions to remove or alter river/estuary barriers | 8
|  |  | 1 | Complete a multilevel GIS map of the Severn Estuary River System, specific to sturgeon.
|  |  | 2 | Complete a comprehensive database of European sturgeon records.
|  |  | 3 | Complete a document evidencing that European sturgeon is native to the UK.
|  |  | 4 | The European sturgeon is recognised as a native species in the UK by JNCC, and subsequently DEFRA.
|  |  | 5 | Complete a media campaign to raise awareness of sturgeon conservation.
|  |  | 6 | Complete a series of local and regional stakeholder meetings, events and workshops.
|  |  | 7 | Complete and present evidence reports (including the sturgeon records database) and scientific papers to inform authorities on the abundance of and threats arising from non-native sturgeon in UK waters.
|  |  | 8 | Cefas begins to highly regulate non-native sturgeon in the UK.
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These don't tie in exactly, but I have approximated them

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Complete a multilevel GIS map of the Severn Estuary River System, specific to sturgeon. | O.1.1 | Relevant information relating to sturgeon in the project area has been collated and formatted for input into ArcGISpro. NA - progress |  |  | NA - Progress | Material is usable and sharable and is useful for future projects | Information is available and transferrable to GIS |  |  | 30 | 30 surveys completed | [6 empty] | 0 | Complete
|  |  | O.1.2 | Created GIS map is clear and can lead to further analysis in future documents [number of maps created] |  |  | NA progress | [12 empty] | 0 | Complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson need to add in when the GIS map of the sturgeon sightings were added. @Sophie Locke I think this may have been completed in August 2021 before I joined and believe you may have done this with Alex? Please can you confirm and I will add to the log frame.

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Complete a comprehensive database of European sturgeon records. | O.2.1 | All known sources of information have been sorted through and collated into a spreadsheet. | 1 |  | 2.4.1 | Database is created | Records of native sturgeon are accessible. Whole database relies on outside party to complete, and be willing to share. |  |  | 1 | research database produced | [6 empty] | 0 | Complete
[20 empty] | 0 | Complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1
A.2.2
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson I have put this as 1 to match with the above as I imagine the spreadsheet above is referring to the same one here so to me this is a duplication - do we need this here? Reply: mmm yeah I think this is a hangover of transferring this across to our current logframe template, I will delete the text as it's not required

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Complete a document evidencing that European sturgeon is native to the UK. | O.3.1 | Historical information, life-history and database data will be collated into a document to outline the presence of European sturgeon in the UK throughout history |  |  | NA - progress | Evidence report and summary report produced | Main document is produced by outside party and circulated so summary document can be created. |  |  | 1 | Report providing evidence on restoration released | [6 empty] | 0 | Complete
|  |  | O.3.2 | A shorter summary document is also produced to be more public facing [document produced]. |  |  | 2.4.1 |  |  |  |  | 1 | Report providing evidence on restoration released | [6 empty] | 0 | Complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1
A.3.2
A.3.3
A.3.4
A.3.5
A.3.6
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson I have added this to match with the above - longer version report of the shorter evidence report highlighted below. Reply: Great - thank you! Do you know the months these were released and if so please could you include?

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | The European sturgeon is recognised as a native species in the UK by JNCC, and subsequently DEFRA. | O.4.1 | After meetings with JNCC, they clarify their position on the native status of European sturgeon |  |  | NA - progress | Policy change leading to European sturgeon clarified as UK native species | Relies on JNCC being willing to clarify position based on evidence presented. | [10 empty] | 1 | Sturgeon now confirmed as native species - Oct 22. Confirmation provided verbally. | 1 | Sturgeon now confirmed as native species - Oct 22. Confirmation provided verbally.
|  |  | O.4.2 | Future documents and the JNCC website display that European sturgeon are native to the UK |  |  | 2.4.3 |  |  |  | UK Government agencies have not taken this forward |  | UK Government agencies have not taken this forward |  | UK Government agencies have not taken this forward |  | UK Government agencies have not taken this forward |  | UK Government agencies have not taken this forward | 0 | UK Government agencies have not taken this forward
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1
A.4.2
A.4.3
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray did this happen because of work involving BLUE? This is big news! Reply: Yes partly. It was more because of the evidence that was collected and submitted to regulators (from Steve Colclough) but also because of the continued engagement we have been having with them, for example through the Favourable Conservation Status report we were commissioned to do by NE.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson UK Gov agencies have not taken this forward so have left blank. Reply: OK, have just added text to the progress section to reflect that

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Complete a media campaign to raise awareness of sturgeon conservation. | O.5.1 | A digital landing page is created, which can be linked in all social media posts, which will display information on European sturgeon and the UK Sturgeon Project. | 1 |  | 4.2.2 | Media campaign has many interactions (Impact stats) | Assets on European sturgeon are available or able to be created/collected. |  |  |  |  | 1 | Website launched March 2022 | 1 | Website launched March 2022 |  |  |  |  | 1 | Website launched March 2022
|  |  | O.5.2 | Social media posts of assets are shared leading to greater interest in the project. | 2000 |  | 4.2.1 | [6 empty] | 304000 | has had over 4,000 visits since its launch in March 2022. #SaveTheSturgeon Campaign reached 300,000 people online. | 304000 | has had over 4,000 visits since its launch in March 2022. #SaveTheSturgeon Campaign reached 300,000 people online. |  |  | 5670 | Savethesturgeon website has 5,348 views (an extra 1348 from Y2) and 4322 users as of Nov 22 | 309670 | has had over 4,000 visits since its launch in March 2022. #SaveTheSturgeon Campaign reached 300,000 people online. Savethesturgeon website has 5,348 views (an extra 1348 from Y2) and 4322 users as of Nov 22
|  |  | O.5.3 | Videos are created to support this campaign |  |  | 4.2.2 | [12 empty] | 1 | Sturgeon life cycle animation video - July 22 | 1 | Sturgeon life cycle animation video - July 22
|  |  | O.5.4 | Media campaign engages with a large number of people |  |  | 4.2.1 |  |  |  | Media campaign took form of website outlined in rows above |  | Media campaign took form of website outlined in rows above |  | Media campaign took form of website outlined in rows above |  | Media campaign took form of website outlined in rows above |  | Media campaign took form of website outlined in rows above | 0 | Media campaign took form of website outlined in rows above
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just put a number in here at random Reply: Ah yeah that is quite difficult to answer but I think Emma might have an idea of how many posts we shared if that;s helpful?
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson the only media campaign we released was with the save the sturgeon website and this has been covered above. Reply: ok great - I will add some text in the progress achieved section to reflect that

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Complete a series of local and regional stakeholder meetings, events and workshops. | O.6.1 | Different interest groups including anglers and government bodies are met with and spoken to about the project |  |  | 4.2.2 | Number of meetings and events are created and attended by stakeholders | Covid restrictions are relaxed to allow for in person events, or else internet connections are available to all involved. | [6 empty] | 1 | The last UK Sturgeon Alliance working group meeting was held in March 2022 and was attended by over 30 people from different organisations including DEFRA, Natural England, NRW, EA etc. BLUE was a founding member of the group |  |  | 3 | 1- UK action plan for sturgeon conservation - attended by 20 individuals - Oct 22 2 - HELCOM meeting (Estonia) to discuss Baltic re-introduction programmes - Nov 22 3 - Presented at Sturgeon Irish WT Webinar to 40 participants - June 23 | 4 | The last UK Sturgeon Alliance working group meeting was held in March 2022 and was attended by over 30 people from different organisations including DEFRA, Natural England, NRW, EA etc. BLUE was a founding member of the group1- UK action plan for sturgeon conservation - attended by 20 individuals - Oct 22 2 - HELCOM meeting (Estonia) to discuss Baltic re-introduction programmes - Nov 22 3 - Presented at Sturgeon Irish WT Webinar to 40 participants - June 23
|  |  | O.6.2 | Any issues or concerns are spoken about and dealt with either in explanations or changes to delivery of project |  |  | NA - progress
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray I have removed the second one from being counted because it's wasn't run by us but please le tme know if that's not correct Reply: Ah yeah okay that makes sense - it wasn't run by us, I just attended on behalf of the Sturgeon Alliance Reply: @Appin Williamson I have added this presentation (no.3) but not sure it's in the right place/ it'll be filtered through to the impact stats as no.1&2 were already in there. Reply: Hmm I'm not sure I understand this comment now I have read it again, what do you mean? I have also just added 30 stakeholders reached into the unplanned tab

## Output 7
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 | Complete and present evidence reports (including the sturgeon records database) and scientific papers to inform authorities on the abundance of and threats arising from non-native sturgeon in UK waters. | O.7.1 | Extent of presence of non-native sturgeon in the project area and wider UK is understood. |  |  | 2.4.1 | Number of reports on non-native sturgeon are produced | Information is available and numbers of non-native sturgeon present are accessible. | [10 empty] | 0 | Output now removed
|  |  | O.7.2 | Impacts non-native sturgeon have on the environment is understood based on wider literature and presented in a report [reports produced]. |  |  | 2.4.1 | [12 empty] | 0 | Output now removed
|  |  | O.7.3 | Reports suggest recommendations for alleviating the issue of non-native sturgeon in the UK. |  |  | 2.4.1 | [12 empty] | 0 | Output now removed
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson all of these refer to non-native species which we are no longer taking forward through Barclays. We have however highlighted that non-natives are a threat within the Action Plan - should we include this anywhere? Reply: I think that we have released the action plan is probably output enough. This maybe comes back to whether this adequately reflects the scope of the sturgeon project - if the milestones are changed then we can change them here to reflect what we're really doing

## Output 8
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 | Cefas begins to highly regulate non-native sturgeon in the UK. | O.8.1 | Reports are presented to Cefas along with a meeting/discussion [number of]. |  |  | NA - progress | Policy and regulation changes | Reliant on Cefas regulating non-native trade more based on evidence presented. | [10 empty] | 0 | Output now removed
|  |  | O.8.2 | Policy change/stricter regulations on non-native sturgeon in the pet trade [number of policy/regulation amendments]. |  |  | 2.4.3 | [12 empty] | 0 | Output now removed
|  |  | O.8.3 | Fewer accidental/illegal releases into the wild [dataset evidence to reflect this]. |  |  | 2.4.3 | [12 empty] | 0 | Output now removed
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson again we aren't taking this forward through Barclays but we have actions in the UK action plan for it.

## Output 9
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 | Produce a report that lays the foundation for the subsequent restoration of spawning grounds and fingerling release in order to actively restore European sturgeon to UK rivers. | O.9.1 | A combination of fieldwork, data collection and literature reviewing will collate into a feasibility study [paper produced] |  |  | 2.4.1 | Number of surveys, datasets etc. produced | Fieldwork is not restricted by covid. Data and literature are available. |  |  | 0 | July 2021 - field survey completed, 2 weeks of river surveys - eDNA samples collected | [6 empty] | 1 | Feasibility study report on Severn produced draft - Sept 22 Restoring Sturgeon to Irish Waters report released May 23 (https://www.bluemarinefoundation.com/wp-content/uploads/2023/05/Sturgeon_Report_2023-Final.pdf)
|  |  | O.9.2 | Feasibility study clearly determines whether active resotration of European sturgeon is necessary. |  |  | NA - progress | Feasibility study produced
|  |  | O.9.3 | Feasibility report leads to the creation of a rewilding template for lost marine species [paper produced] |  |  | 2.4.1 | [12 empty] | 0
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jenny Murray please could you check the number of samples collected as part of this fieldwork? Reply: @Appin Williamson 26
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jenny Murray if this is in draft and not yet published, I might just leave this as zero for now. But please shout if you think this is wrongh Reply: Yes happy with that - I wasn't sure whether to include it as it hasn't been published yet so happy to capture it in the next round. Reply: I have added in the Irish report into this line as it still seems appropriate
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson this is now being taken forward through the UK action plan - how would you like to capture this? Reply: I have included the action plan in the unplanned outputs section. Reply: @Jenny Murray so is this something that we're no longer directly doing ourselves? If so we could put further along in the row that this is now being completed by others so we don't need to report on it

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Sturgeon sightings | 3 | sightings | 2.4.1 | 3 sightings of sturgeon logged in website | Website information collected | [6 empty] | 0 | 3 sightings of sturgeon logged in website |  |  | 0 | 4 sightings of non native sturgeon logged in website (2 in Dec, 1 in Jan, 1 in Feb)
U.2 | UK action plan for sturgeon conservation being developed | 1 | Number reports | 2.4.1 | [10 empty] | 1 | Action plan expected to be published in May 2023 | 1 | Sturgeon action plan produced (May)
U.3 | Favourable conservation status document being developed by NE and UK Sturgeon Alliance | 1 | Number reports | 2.4.1 | [10 empty] | 1 | FCS document expected to be published in June 2023 | 0
U.4 | MsC Students | 1 | Number of students | 4.1.2 | Number of students benefitting from Blue project resource |  |  |  | 1 | Report outlined below
U.5 | Msc student reports | 1 | Number of Msc reports | 2.4.1 |  |  |  |  | 1 | Msc report on feasibility of sturgeon recovery in the Bristol Channel. Sept 2021.
U.6 | Stakeholders reached with marine conservation messaging | 1 | Number of stakehodlers | 4.2.1 | [12 empty] | 40 | 3 - Presented at Sturgeon Irish WT Webinar to 40 participants - June 23
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Appin Williamson this has still not been published so have set to 0.

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 2 | 6 | O.1 | O.1.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 1 | 5 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 2 | 6 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 4 | 8 | O.2 | O.2.1 | 0% | 100% | 0% | 0% | #DIV/0! | 100% | 0% | 0% | 100% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 2 | 6 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 3 | 7 | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.3.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | 0% | 0% | 100% | 100% | #DIV/0! | 100% | 0% | 0% | 100% | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.2 | 0% | 0% | 15200% | 15200% | #DIV/0! | 15200% | 0% | 283.5% | 15484% | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 9 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 2 | 0 | 1 | 1 | 0 | 1 | 3 | 2 | 5 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 304000 | 5670 | 0 | 0 | 40 | 309670 | 40 | 309710 | 2000 | 309670 | 309670 | 0
[14 empty] | 4.2.2 | 0 | 2 | 4 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0