## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01 | Key stakeholder workshop: tool presentation and feedback.
2023-04-01 | 1:1 workshops held with key stakeholders.
2023-05-01 | 1:1 workshops held with key stakeholders.
2023-06-01 | MRAG presented at SIME, Glasgow. OFW tool distributed to four companies. | Potential links with Defra.
2023-07-01 | Presented to TCE - 50 participants on the call.
2023-08-01 | Aberdeen OWF visit - informal partnership with Floatation Energy Phase 2 MRAG proposal submitted
2023-09-01 | Meeting with DEFRA to confirm support for progressing phase 2 proposal.

## Impact and Outcome
Impact | Illustrate that ocean conservation and offshore wind can have a symbiotic and mutually beneficial relationship and highlight new opportunities for environmentally focused investment.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | Establish the scale for offshore wind sites to be used for habitat creation, multi-function and coexistence in UK seas, while identifying specific wind farm locations for habitat creation projects. | OC.0.1 | Establish the scale of the potential for offshore wind sites to be used for habitat creation | 1, 2 |  |  | Reports/datasets/evidence produced and shared externally | 0.1 Offshore wind farm operators and other key stakeholders are willing to participate in feasibility studies 0.2 Data is available to make a strong case for habitat creation, multi-function and coexistence in UK seas. 0.3 Numerous wind farms are suitable for the above. 0.4 The Government, Crown Estate and other key decision/policy makers are supportive of the project
|  |  | OC.0.2 | Illustrate the possibility for multi-function and co-existence of industry and conservation in UK seas | 3, 4 |  |  | Feasibility studies conducted by tehcnical experts
|  |  | OC.0.3 | Identify specific wind farm locations for habitat creation projects | 5, 6 |  |  | Partnerships with operators/research organisations participating in restoration activites/research activities to support restoration
Significant reach and support generated across key UK/EU stakeholder groups, informal partnerships formed
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These were as outlined in the older version of this logframe - updated to the goals Reply: Key goals: Establish the scale of the potential for offshore wind sites to be used for habitat creation Illustrate the possibility for multi-function and co-existance of industry and conservation in UK seas Identify specific wind farm locations for habitat creation projects
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These don't fit exactly, I have tried to roughly align but please change as you see fit

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Decision made on Gunfleet Sands wind farm made. Complete initial scoping study of all Orsted UK wind farm sites | O.1.1 | Pilot project for oystered cages within Gunfleet Sands Wind Farm is/is not advised |  |  | NA | Communication with Orsted on agreed outcome | Spatial and ecological data is available | [9 empty] | Completed in Y1 |  | Completed in Y1
|  |  | O.1.2 | GIS analysis of [number of wind farms] Orsted wind farms completed; analysis of nearshore and offshore wind farm site attributes and ecological requirements of native oysters and other species assessed |  | number of studies/investigations | 2.4.1 | Database (site selection matrix) shows results of analysis |  |  | This was done by Sophie's matrix, by BLUE, Ofsted and ENORI - output needs inclusion in this logframe? | [7 empty] | Completed in Y1 |  | Completed in Y1
|  |  | O.1.3 | Analysis repeated for potential future wind farms (i.e. consented sites, areas of exploration, expansions...) |  |  | NA | GIS map outputs demonstrate spatial mapping and analysis of Orsted wind farms, plus potential future sites | [10 empty] | Completed in Y1 |  | Completed in Y1
[8 empty] | Rationale explains analysis of attributes/ecological requirements of native oysters | [10 empty] | Completed in Y1 |  | Completed in Y1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sophie Locke do you know when this was completed? Reply: @Sophie Locke
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This was flagged as 1.4 but it didn't look like there was an output indicator 1.4 - have left in this new row for now

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Complete scoping study of all UK wind farm sites and establish relationships with relevant stakeholders. | O.2.1 | GIS analysis of [number of wind farms] completed; analysis of nearshore and offshore wind far site attributes and ecological requirements [number of] species assessed |  | number of studies/investigations | 2.4.1 | GIS map outputs, site selection matrix completed | Spatial and ecological data is available Stakeholders are willing to engage with BLUE on the project in the UK |  | Covered in Output 1 |  | Covered in Output 1 |  | Covered in Output 1 |  | Covered in Output 1 |  | Covered in Output 1 |  | Covered in Output 1
|  |  | O.2.2 | [Number of] offshore wind farm operators in contact/in relationship/partnership with BLUE |  |  | NA | Correspondence with operators and other key stakeholders | [6 empty] | Completed |  | Completed |  | Completed |  | Completed
|  |  | O.2.3 | [Number of] meetings/events where results are presented |  | Number of presentations | 4.2.2 | Meetings/presentations attended by BLUE with work presented | [5 empty] | 1 | Feb 2022 - OWF conference |  | Completed |  | Completed |  | Completed
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have included this info already in Outcome 1 - not sure I should be duplicating Reply: OK grea thanks, yes don't want to duplicate so that's good to know - here we can leave blank with a comment explaining it's already in output 1
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sophie Locke should we be including the site selection matrix that's listed in here? It's not currently covered in output 1
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sophie Locke same question here - do you know when this was completed?

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Commitments from UK government and agencies to be involved with UK wide detailed feasibility study confirmed | O.3.1 | [Number of] informal/formal partnerships/relationships formed with UK government and agencies |  |  | NA | Correspondence with government and agencies outlining broad support/expressions of commitment to be involved with feasibility studies | Government/agency capacity allows for involvement/commitment Government/agencies are supportive of colocation projects | [10 empty] | 3 | Relationships established during Blue/ MRAG March 2023 feedback workshop with Defra, Natural England and The Crown Estate who were supportive of the decision tool and would like to continue discussions and develop potential partnerships for phase 2 iterations.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Agreement from several offshore developers to participate in a detailed feasibility study and network built of supportive organisations. | O.4.1 | [Number of] informal/formal agreements received from offshore wind farm operators/developers to participate in detailed feaisbility study |  |  | NA | Correspondence with offshore wind farm operators/developers | [11 empty] | 4 | Informal partnerships agreed to take forward testing of the OWF tool. Informal agreement recieved from Floatation Energy, Ocean Winds, Orsted and Arc Marine.
|  |  | O.4.2 | [Number of] organisations supporting the development of the project and feasibility study work [collaborative working group] |  |  |  | Correspondence with key organisations
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | UK-wide feasibility study completed and report distributed. | O.5.1 | Feasibility study produced, assessing [number of] offshore wind farms and habitat enhancement opportunities for [number of native UK species] |  | Number of reports/investigations | 2.4.1 | Comprehensive feasibility report produced by chosen consultant
|  |  | O.5.2 | Public-facing report on findings is produced |  | Number of reports/investigations | 2.4.1 | Report published and available online |  |  |  | 2 | 1 report on offshore wind restoration completed 1 research project [matrix, spatial analysis completed] |  |  | 0 | MRAG study assessing suitability of OWFs across the UK for NID options comissioned Feb 2022. | 1 | Publish MRAG study online in a public-facing format | 1 | MRAG report completed in April 2023 and shared with gov bodies and OWF developers and industry representative groups.
|  |  | O.5.3 | [Number of] presentations/conferences completed that showcase results of UK-wise feasibility study |  | Number of presentations/conferences/outreach activities | 4.2.2 | Significant representation at presentations/conferences | [7 empty] | 1 | Offshore wind event feb 2022 |  |  |  |  | 1 | Offshore wind event feb 2022
|  |  | O.5.4 | Stakeholders reached through public facing reports and outreach acitivites |  | Stakeholders | 4.2.1 | Attendance records, copy of correspondence | [7 empty] | 330 | Stakeholder engagement event, 330 attendees from 20 countries |  |  |  |  | 330 | Stakeholder engagement event, 330 attendees from 20 countries
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sophie Locke - is this referring to each individual feasibility study now being completed outside of MRAG study?
Note on Q5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I'm not sure if this should count as 1 study - or if this should be all OWF's assessed which Soph did which I think was about 50. @Sophie Locke which year was this done?

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
| O.6 | Produce an in-depth study at one (or more) wind farm sites. No longer relevant. | O.6.1 | Scope of work for in-depth site investigation and feasibility study is produced. No longer relevant. |  |  | NA | Outline for scope of work defined by consultant/BLUE/operators | [11 empty] | 0 | This output is no longer relevant. Instead of producing a report that outlines the steps of nature enhancement in within windfarms, Blue Marine will publish the Phase I report on nature-inclusive design in a public-facing format (as mentioned above). This report not only covers the development of the decision-tree tool, but also provides evidence for why nature-inclusive design is needed within the offshore wind industry and the steps that all stakeholders should investigate when considering their introduction.
|  |  | O.6.2 | In-depth study at [number of] wind farm sites [total km2] produced, analysing [number of species] and [number of] habitat enhancement/restoration opportunities. No longer relevant. |  |  | 2.4.1 | Report produced | [11 empty] | 0 | MRAG’s Phase I report will be published online by the end of September 2023. It has already been widely circulated with numerous government representatives, industry members, offshore wind companies and NGOs. These stakeholder relationships have been built since the inception of the project and reflect Blue Marine’s integration into this sector (both within the UK and Europe) over the past three years.
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How does this link with output 5 feasibility studies. @Sophie Locke as per my other comment, if the one in output 5 is referring to each individual feasibility study then this would be a duplication?

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | PhD Student | 1 | No. of Students | 4.1.2 |  |  |  |  | 1 | PhD student
U.2 | Media Feature | 1 | No. outreach tools/activities | 4.2.2 |  |  |  |  | 1 | 1 x media feature
U.3 | Offshore wind event | 330 | No. event attendees | 4.2.1 | 330 event users from over 20 countries | Attendance report from MW |  |  | 0 | Covered in output tab
U.4 | Offshore wind event | 1 | No. of outreach tools/activities | 4.2.2
U.5 | Outreach activity | 1 | No. of outreach activities | 4.2.2 | [12 empty] | 2 | CE talk given online (July 23) SIME conference (June 23)
U.6 | Stakeholders reached | 50 | No. stakeholders reached | 4.2.1 | [12 empty] | 150 | Number of attendees at CE online workshop - 50 (July 23) No. attendees at SIME conference - 100 (June 23)
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 3 | 7 | O.1 | O.1.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 1 | 5 |  | O.1.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 4 | 8 | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 2 | 6 |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | #REF! | #REF! |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | #REF! | #REF! | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | #REF! | #REF! |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | #REF! | #REF! |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 10 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | O.2.1 | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.4.1 | 2 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 330 | 0 | 0 | 0 | 150 | 330 | 150 | 480 | 0 | 330 | 330 | 0
[14 empty] | 4.2.2 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 3 | 4 | 0 | 1 | 1 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0