## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | BLUE's M&E Guide.pdf
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2023-12-22 | Presentation of the project in front of representatives of the authorities (SBAAs, DFMR) and NGOs | During a two-day workshop (AKROTIRI PENINSULA - BIOTIC & ABIOTIC MONITORING, STATUS & TRENDS at the Akrotiri Environmental Education Centre) we presented the project to the attendees (representatives from the DFMR, the Envrionmental Department of the SBAAs, local NGOs like Terra Cypria, BirdLife Cyprus, Enalia-Physis, and others)
| Presentation of the short documentary to the authorities (SBAAs, DFMR) and other NGOs | During a two-day workshop (AKROTIRI PENINSULA - BIOTIC & ABIOTIC MONITORING, STATUS & TRENDS at the Akrotiri Environmental Education Centre) we presented the short documentary of the project
| Dissemination of videos to increase awareness, resulting in a strong social impact | Dissemination of a short documentary (in GR and EN), highlighting the significance of the marine area of Akrotiri, shedding light on the potential threats it faces, with a mention to the objectives and scope of the Akrotiri project. | https://www.youtube.com/watch?v=ypYwA8cgLqw
| Awareness actions | Promotion of the short documentary and description of the project on MER's social media (Facebook, Instagram, Linkedin, Twitter) and MER's website
| Communication actions and support assurance from fishers | Informal discussions with individual small-scale fishers, recreational fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received. | https://www.youtube.com/watch?v=bg63Gbw3E-0
2023-01-23 | Communication actions and support assurance from fishers | Informal discussions with individual small-scale fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received. | https://www.merresearch.com/projects/
2023-02-23 | Submission of an initial proposal suggesting an MPA model for the marine area of Akrotiri | Developing management protocols and structure to ensure effective enforcement of regulations.
2023-03-23 | Communication actions and support assurance from fishers | Informal discussions with individual small-scale fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received.
| Draft proposal for the establishment of a fishery co-management model for Akrotiri Peninsula | Information collation, literature review, analysis. Proposal to be submitted and presented to the authorities.
2023-04-23 | Draft proposal for the establishment of a fishery co-management model for Akrotiri Peninsula | Information collation, literature review, analysis. Proposal to be submitted and presented to the authorities.
| Draft proposal for the establishment of a fishery co-management model for Akrotiri Peninsula | Information collation, literature review, analysis. Proposal to be submitted and presented to the authorities.
| Questionnaire surveys for fishers at key locations | Questions for key activities at the areas of interest
2023-05-23 | Informal discussions with representatives from the SBAA | During a two-day workshop at Akrotiri (SBAAs Biodiversity Strategy Workshop), our discussions revolved around Akrotiri. We also engaged in informal communications with individuals from the Environmental Department to ensure continuous communication and maintain their support regarding our project.
| Awareness actions | During a two-day festival held at Akrotiri (Akrotiri Spring Festival 13-14 May 2023), we informed the public about the importance of the marine area of Akrotiri and showed the short documentary we prepared for the area http://visitakrotiri.cy/plan-your-visit/festivals/
| Communication actions and support from small-scale and recreational fishers | Informal discussions with individual small-scale fishers, recreational fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received.
2023-06-23 | Communication actions and support from small-scale and recreational fishers | Informal discussions with individual small-scale fishers, recreational fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received.
| Submission and presentation of the proposal for the establishment of a fishery co-management model for Akrotiri Peninsula to DFMR | Presentation of the proposal and discussion with the Director of the DFMR (Marina Argyrou). We extensively discussed the possibilities, opportunities, risks, and the way forward. Positive outlook was received.
| Communication actions and support from small-scale and recreational fishers | Informal discussions with individual small-scale fishers, recreational fishers and representatives of fishery associations regarding the project, the importance of Akrotiri, and the need for adoption of management measures. Written support was received.
2023-07-23 | Drafting a more detailed technical proposal for our model, which will include information about the Committee's functioning, its members, their roles, and its legal status, as well as additional info such as how the results will be monitored. | Following the discussions with the Director of the DFMR, a more detailed proposal (written in the format of a management plan for the area of interest) is required, in order to be reviewed again by the DFMR, and then if approved, to be sent to the legislative scrunity of the Republic of Cyprus for further approval
| Finalising a big report including all information collected for Akrotiri, inclusing data from preliminary field surveys at the area of interest | To be reviewed and submitted to BMF
2023-08-01 | Refining big report including all information collected for Akrotiri, inclusing data from preliminary field surveys at the area of interest | To be reviewed and submitted to BMF
2023-09-01 | One tournament for invasive species at Akrotiri | Lionfish removal with spearfishers
Please find below some rough estimates. Let me know if you think adjustments are needed.
Raising awareness and engaging the groups together (30,000 EU)
Two tournaments
Two workshops
Eight consultation events
Meetings with stakeholders จC at least 20
Network dissemination and awareness actions
Communication material and dissemination
Environmental monitoring & visualization of risks/activities (50,000 EU)
Visual census
Posidonia monitoring
Questionnaires to delineate activities
Fishery sensitivity assessment studies of fisheries on habitats
Cartography/Risk maps
Legal status (8,000 EU)
Establishing a legal form
MoU with stakeholders etc.
Management proposals & negotiations (8,000 EU)
Proposals visualized in maps & negotiations with stakeholders and authorities

## Impact and Outcome
Impact
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | Effective designation of the marine area of Akrotiri as an MPA following a fishery co-management model with strong stakeholders' engagement | OC.0.1 | Successful designation of an Akrotiri MPA | 1,2,3 | 1.1.1, 1.2.1, 1.3.1, 2.1.1, 2.2.1, 2.4.1, 3.4.1 | 1.1, 1.2, 1.3, 2.1, 2.2, 2.4, 3.4 | Formation of a management plan including a long-term monitoring plan, Governmental Approval and Official Documentation followed by pubic announcement, Stakeholder Consultations | Consistent commitment from project partners, Governmental and Regulatory Support, endorsement of the proposal by local authorities - political will, legal framework, collaboration,Financial Resources, public support
|  |  | OC.0.2 | Effective management of the Akrotiri MPA | 1,2, 3, 4, 5 | 1.1.2, 1.2.2, 1.3.2, 1.4.2, 2.1.2, 2.2.2, 3.1.3, 3.2.2, 3.2.4, 3.3.1, 3.3.2, 3.3.3, 3.4.2, 4.3.1, 4.2.2, 4.1.2, 4.2.1, 4.2.2, 4.1.1, 4.4.1, 5.1.2, 5.3.1, 5.3.2, 5.3.3 | 1.1, 1.2, 1.3, 1.4, 2.1, 2.2, 3.1, 3.2, 3.3, 3.4, 4.1, 4.2, 4.3, 4.4, 5.1, 5.3 | Implementation of the MPA management plan, collaborative governance, regular ecological monitoring, Long-term Support and Funding | Stakeholders are willing to participate in workshops/ consultation events - commitment to co-management, Political and Regulatory Support
|  |  | OC.0.3 | Developing sustainable fisheries that provide employment for local communities and secure ongoing on the ground support for the MPA | 4 | 4.2.1, 4.2.2, 4.4.1, 4.1.2 | 4.1, 4.2, 4.4. | Events, questionnaires, change in public's perspective, community engagement and support, codes of conduct, fish stock assessments | Community engagement throughout the lifespan of the project, effective governance and enforcement, community acceptance, scientific data accuracy,

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024 |  | Progress planned in 2025 |  | Progress achieved in 2025 |  | Progress planned in 2026 |  | Progress achieved in 2026
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Stakeholders and public engagement | O.1.1 | Raising awareness and concern of stakeholders and community groups | 150 | Number of people informed | 4.2.1 | More than 150 people (general public and stakeholders) | Accurate, relevant, and impactful disseminated information, stakeholders are receptive and willing to engage in awareness actions | 100 | At least 100 people to attend events promoting Akrotiri, and the project | 100 | At least 100 people attended events promoting Akrotiri, and the project
|  |  | O.1.2 | Targeted workshops/events organised | 8 | Number of workshops | 4.2.2 | More than 8 workshops | Sufficient interest and participation from the target stakeholders in attending the workshops or events, logistical arrangements and resources are available to organize the workshops/events | 4 | Four workshops organised | 0 | No workshops were organised, however there were commincation actions with individual stakeholders | 4 | Four workshops organised
|  |  | O.1.3 | Number of partnerships developed | 10 | Partnerships | 4.3.1 | More than 10 partnerships | Benefits and incentives for partners to collaborate are clear and mutually beneficial. | 9 | Collaboration with relevant stakeholders to participate in the co-management committe - including individual commercial and recreational fishers, fishers associations, the Sovereign Base Areas of Akrotiri and Dhekelia (SBAA), Pantelis Charilaou (Environment and Conservation officer), Kostas Aristeidou (Environmental Engineer), Enalia Physis Environmental Research Centre, BirdLife Cyprus, AQUADEMIA, Cyprus Environmental Foundation, and University of Cyprus. | 9 | Support and motivation to participate in the Committee has already been received by most relevant stakeholders including individual commercial and recreational fishers, fishers associations, the Sovereign Base Areas of Akrotiri and Dhekelia (SBAA), Pantelis Charilaou (Environment and Conservation officer), Kostas Aristeidou (Environmental Engineer), Enalia Physis Environmental Research Centre, BirdLife Cyprus, AQUADEMIA, Cyprus Environmental Foundation, and University of Cyprus.
|  |  | O.1.4 | Outreach activities/tools are held/released | 4 | Number of tools/activities | 4.2.2 | 2 tournaments for invasive species removal, videos, dissemination material, photos | Outreach activities and tools are designed to be accessible and engaging for the target audience | 2 | 1 tournament for invasive species removal, 1 short documentary for the importance of Akrotiri/ threats | 2 | 1 short documentary for the importance of Akrotiri/threats; 1 tournament for invasive species (lionfish)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1
A.1.2
A.1.3
A.1.4
A.1.5
A.1.6
"1"

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024 |  | Progress planned in 2025 |  | Progress achieved in 2025 |  | Progress planned in 2026 |  | Progress achieved in 2026
7 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Environmental monitoring and risk assessment/visualisation | O.2.1 | Comprehensive literature review completed | 1 | Quantity of literature reviews | 1.4.1 | Literature review report | Reliable scientific data collection using scientific standards and consistent techniques (e.g., to prevent the collection of inaccurate seasonal data due to short-term natural or human- induced changes in environmental conditions) | 1 | Complete literature review and compile data into a big report | 1 | Final draft of the literature review was completed, pending refining and final editing before submission
|  |  | O.2.2 | Comprehensive baseline protocol developed | 1 | Number of protocols | 1.4.2 | Protocol developed and implemented | Data availability, scientific expertise, access to monitoring sites | 1 | Protocol developed | 1 | Protocol developed
|  |  | O.2.3 | Visual fish census surveys | 6 | Number of visual fish census surveys | 1.4.1 | Data sheets and field notes from the visual surveys, documenting species observed, abundance, and location. Photo or video documentation of key species or habitats during the surveys. At least at three locations, at two habitats (n=6) | Survey methodology remains consistent over time | 1 | Visual fish census at three locations (Cape Zeugari, Avdimou, Bahames) at two habitat types
|  |  | O.2.4 | Posidonia oceanica monitoring | 3 | Number of field surveys at P.oceanica | 1.4.1 | At least three locations with P.oceanica meadows to be monitored | Survey methodology remains consistent over time | 1 | Monitoring of P.oceanica meadows at three locations (Cape Zeugari, Avdimou, Bahames)
|  |  | O.2.5 | Fishery Sensitivity Assessment Studies of Fisheries on Habitats | 1 | Reports | 1.4.1 | Detailed sensitivity assessment reports, including methodology, data sources, and results. | Stakeholders are willing to collaborate and provide data for the assessment, necessary expertise to conduct a robust sensitivity assessment. | 1 | Collection of data (field data from 2021-2023), landing surveys | 1 | Collection of data (field data from 2021-2023), landing surveys was initiated
|  |  | O.2.6 | Cartography/Risk Maps: | 1 | Number of maps | 1.4.1 | At least one map of the area showing high risk areas to be produced | Accurate and up-to-date spatial data are available | 1 | Identification of high-risk areas
|  |  | O.2.7 | Interviews conducted with local fishers | 80 | Number of fishers participating in surveys | 1.4.3 | More than 80 fishers interviewed - Analysis and reporting of questionnaire responses | Willingness of fishers to participate, reliability of information | 50 | 50 fishers to be interviewed | 21 | 21 fishers were interviewed | 30 | More than 30 fishers to be interviewed (mainly recreational fishers, were data islimited).
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1
A.2.2

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024 |  | Progress planned in 2025 |  | Progress achieved in 2025 |  | Progress planned in 2026 |  | Progress achieved in 2026
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Establishing a legal status | O.3.1 | Legal form of the committee established | 1 | Documentation | 1.4.1 | Legal Form of the Committee Established, official certificates, permits, or documentation confirming the committee's legal status, minutes of meetings | Clear legal framework or regulatory process in place, committee members and stakeholders are committed to complying with the legal requirements and formalities for the establishment of the committee's legal form,access to legal expertise or consultation to navigate the process and ensure compliance with all necessary legal procedures | 10 | Consultations with stakeholders and lawyers
|  |  | O.3.2 | Memorandum of understanding (MoU) signed | 1 | MoU |  | Copy of the signed and dated Memorandum of Understanding (MoU), Records of meetings, negotiations, or consultations leading to the development and finalization of the MoU | All involved stakeholders are willing to collaborate and engage in the process of drafting and signing the MoU,mutual understanding and agreement among stakeholders | 1 | First draft of MoU and discussions with stakeholders
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1
A.3.2
A.3.3
A.3.4
A.3.5
A.3.6

## Output 5 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 |  | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Akrotiri proposed as an MPA | O.5.1 | Number of km2 proposed for protection |  | km2 | 1.1.1
O.5.2
0.5.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Found this link online - consider including https://www.merresearch.com/portfolio/co-management-of-fisheries/ Reply: Also this: https://www.merresearch.com/portfolio/acoustic-telemetry-for-the-critically-endangered-guitarfish-species/

## Output 6 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 |  | O.6.1
O.6.2
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1
A.6.2
A.6.3

## Output 7 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 |  | O.7.1
O.7.2
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1
A.7.2
A.7.3

## Output 8 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 | Progress achieved in 2023
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 |  | O.8.1
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1
A.8.2

## Output 9 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 | Progress achieved in 2023
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 9 | O.9 |  | O.9.1
O.9.2
O.9.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 9 Activities | A.9 |  | A.9.1
A.9.2
A.9.3
A.9.4
A.9.5

## Output 10 (hidden)
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022 |  | Progress planned in 2023 | Progress achieved in 2023
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 10 | O.10 |  | O.10.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 10 Activities | A.10 |  | A.10.1
A.10.2
A.10.3

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress planned in 2024 |  | Progress achieved in 2024 |  | Progress planned in 2025 |  | Progress achieved in 2025 |  | Progress planned in 2026 |  | Progress achieved in 2026
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Management changes | O.4.1 | Number of km2 proposed for protection | 195 | km2 | 1.1.1 | Proposed protected area documentation - management plan including a long-term monitoring plan public | Government Support, availability of funding, expertise and capacity, minimal opposition or conflict | 1 | Proposal Development and Documentation to be submitted and presented to the authorities (DFMR, SBAA) | 1 | Proposal Development and Documentation to be submitted and presented to the authorities (DFMR)
|  |  | O.4.2 | A new management plan is developed | 1 | Management plans | 1.2.1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1
A.4.2
A.4.3

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in 2020 |  | Progress achieved in 2020 |  | Progress planned in 2021 |  | Progress achieved in 2021 |  | Progress planned in 2022 |  | Progress achieved in 2022
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected
Output 1 | 4 | 8 | O.1 | O.1.1 | 66.67% | 66.67% | 0% | 0% | 0% | 66.67% | 0% | 0% | 66.67% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 7 | 11 |  | O.1.2 | 50% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 1.1.1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Output 3 | 2 | 6 |  | O.1.3 | 90% | 90% | 0% | 0% | 0% | 90% | 0% | 0% | 90% | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | O.1.4 | 50% | 50% | 0% | 0% | 0% | 50% | 0% | 0% | 50% | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 3 | 7 | O.2 | O.2.1 | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | O.2.2 | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Output 7 | 3 | 7 |  | O.2.3 | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 | O.3 | O.3.1 | 1000% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 9 | 3 | 7 |  | O.3.2 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 10 | 1 | 5 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | 0.5128% | 0.5128% | 0% | 0% | 0% | 0.5128% | 0% | 0% | 0.5128% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 11
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
|  |  |  | 0.5.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 80
Outputs: | 10 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.9 | O.9.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.9.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.10 | O.10.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 0
[14 empty] | 4.2.2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 12
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 10
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0