## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact | Prove the carbon sequestration value of marine restoration and protection, encouraging a government shift in policy to formally recognised the value of blue carbon habitats to mitigate the effects of climate change.
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | Produce a scientific case that marine conservation and restoration actions will lead to greater sequestration of carbon and provide numerous co-benefits, underpinning the design of investable blue carbon and promoting inclusion into conservation/GHG policy. | OC.0.1 | Carbon sequestration potential quantified and valued for conservation and/or restoration projects (CO2 eq and £/T C) | 1 | 5.1.1 | 5.1
|  |  | OC.0.2 | Cobenefits/ecosystem services quantified and valued (£) | 1 | 5.1.1 | 5.1
|  |  | OC.0.3 | Evidence provided that forms a proposition that unlocks investment into blue carbon capture (reports/datasets/number of financial mechanisms..) | 2, 4, 5 | 4.3.1, 5.4.2, 5.1.1 | 4.3, 5.1, 5.4
|  |  | OC.0.4 | Successful stakeholder engagement that helps catalyse policy change (conferences/reach/engagement/working groups) | 3, 6, 7 | 4.2.1, 4.2.2, 5.1.1 | 4.2, 5.1
|  |  | OC.0.5 | Evidence presented to policy/decision makers for including blue carbon into NDCs | 8 | 5.1.3 | 5.1
|  |  | 1 | Blue carbon value and co benefits/ecosystem services of key habitats and BLUE project sites are quantified.
|  |  | 2 | A coalition of world leading experts is convened by BLUE to shape the research findings and outputs.
|  |  | 3 | Initial findings are showcased at UNFCCC COP26 (at project sites in the Solent and Sussex) at UNFCCC COP26.
|  |  | 4 | Research findings are incorporated into a review of potential financial mechanisms that can support blue carbon restoration / conservation projects.
|  |  | 5 | A proposition that unlocks investment into blue carbon capture is created (linked to BLUE Economics – Connection 5).
|  |  | 6 | Publicly available report is produced, presenting key findings and recommendations
|  |  | 7 | Findings and recommendations are presented to key stakeholders and BLUE’s wider conservation network through a workshop event.
|  |  | 8 | The profile of blue carbon is raised as a climate change mitigation strategy, encouraging inclusion within the government’s Nationally Determined Contributions (NDCs).

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Blue carbon value and co benefits/ecosystem services of key habitats and BLUE project sites are quantified. | O.1.1 | Analysis completed, outlining carbon value (£/T C/CO2 eq) for X km2 blue carbon habitat/s through desktop/field studies | 3 | Pieces of new evidence | 5.1.1 | Calculations verified, showing monetary value of blue carbon conservation/restoration (carbon, cobenefits) | Data available to calculate carbon value Data available to quantify cobenefits and determine monetary value | [6 empty] | 0 | Ongoing work in Sussex, Jersey, Maldives, Solent |  | This is going to be captured by the report from PML that is mentioned below. | 0
|  |  | O.1.2 | Analysis completed, quantifying and valuing cobenefits/ecosystem services (£) for X km2 of blue carbon habitat/s through desktop/field studies | 1 | Pieces of evidence | 5.1.1 | Document/file recording analysis and results | [7 empty] | 0 | Not started | 1 | PML contracted to complete work, completion date of June 2023 | 0 | We are still waiting on the delivery of PML report
|  |  | O.1.3 | Analysis completed on gaps in scientific understanding within blue carbon conservation/restoration | 3 | Pieces of evidence | 5.1.1 | Analysis report |  |  |  | 0 | Previously included report on Seabed carbon and all aspects in Y1 - now included all in Y2 |  |  | 4 | 1: report: seabed carbon (Feb 2022) 1: report: all aspects blue carbon (March 22) 1: Data-led study on North Sea (Nov 21) 1: report on gaps in UK blue carbon audits (June 2022) | 1 |  | 3 | 1: Identifying priority aras bottom towed fishing uk (Sept 22) 1: Does biodiversity-focused protection of the seabed delivercarbon benefits? A U.K. case study (July 2022) 1: Developing a UK seagrass carbon code (July 2023) https://www.naturebasedsolutionsinitiative.org/wp-content/uploads/2023/06/Developing_UK_Seagrass_Carbon_Code_2023.pdf | 4
O.1.4
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Employ a post-doctoral researcher at the University of Exeter, supervised by Professor Callum Roberts and Dr Julie Hawkins, to collate, interrogate and deploy the latest and best-available science on blue carbon ecosystems to support the development of conservation investments in habitat protection and restoration. Prof. Roberts is BLUE’s Chief Scientific Advisor and both he and Dr Hawkins have extensive experience within marine conservation research*, specifically marine habitat protection**
|  |  | A.1.2 | Review evidence on the levels of carbon capture and sequestration by different habitats. Examine how conservation interventions can increase rates of uptake and storage. Identify and evaluate key sources of uncertainty and gaps in scientific understanding
|  |  | A.1.3 | Produce calculations that estimate the value added byconservation/restoration to blue carbon functions in a range of key habitats.
|  |  | A.1.4 | Quantify and value the co-benefits associated with marine restoration and protection of blue carbon habitats, which may include ecosystem services such as storm protection, reduction of coastal erosion, provision of nursery habitat to ecologically and commercially important species and improved water quality.
A.1.5
A.1.6
"1"
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note - this was previously 2.4.1 and is reflected as such in the impact stats document/Barclays impact reporting

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | A coalition of world leading experts is convened by BLUE to shape the research findings and outputs. | O.2.1 | Number of experts brought together within the coalition | 20 | Number of partnerships | 4.3.1 | MoUs/contracts in place confirming partnership | [7 empty] | 28 | 28 member organisations of UK blue carbon forum |  |  | 0 | Indicator achieved | 28
|  |  | O.2.2 | Number of coalitions | 1 | Coalition | 5.4.2 | Written evidence of formation of coalition | [5 empty] | 1 |  | 1 | UK Blue carbon forum launched in Nov 2021 |  |  | 0 | Indicator achieved
|  |  | O.2.3 | Number of outputs published by the forum | 5 | Number of outputs | 5.1.1 | Papers published | [11 empty] | 0 | Nothing formally published to date
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Invite, brief and engage the following prospective partners to provide specialist advice on this project, including: [SEE GRANT DOC LIST]
|  |  | A.2.2 | At project commencement, extensive due diligence will be conducted to identify further prospective partners
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maddie Millington-Drake - what month and year was this formed? Reply: @Maddie Millington-Drake - was this in 2022?

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Initial findings are showcased at UNFCCC COP26 (at project sites in the Solent and Sussex) at UNFCCC COP26. | O.3.1 | Relationship built with Defra | NA | NA | NA - progress | Correspondence with Defra | [7 empty] | 7 | Variety of meetings and engagements with Defra, including linking with the Defra blue carbon evidence group. (May-June 2022) |  |  | 0 | Indicator achieved | 7
|  |  | O.3.2 | Number of project case studies prepared in collaboration with Max Bello | NA | NA | NA - progress | Case studies developed, correspondence with Max Bellow | [7 empty] | 1 | Jersey showcased some of their work on blue carbon at COP26 (Nov 2021) |  |  | 0 | Indicator achieved | 1
|  |  | O.3.3 | Correspondence with key COP/ocean climate stakeholders to secure project update slots at future COPs | 15000 | Stakeholders reached | 4.2.1 | Correspondence with key stakeholders/attendee records |  |  |  | 93300 | 300 (via conference) 93k social media blue carbon content seen |  |  | 20017 | 17: We are engaged in discussions with Comms Inc, Plymouth Marine Laboratory, Commonwealth, IOC UNESCO, the Scottish Blue Carbon forum, the UK Blue Carbon Forum, the Blue Carbon initiative, Silvestrum Climate Associates, TNC, Bloomberg, RARE, GO-BC, IPBC, DEFRA, VERRA Seascape Carbon Initiative, IUCN, 20000: Blue Carbon reel showcased constantly at COP26. 40k attendees, assumed conservative estimate of half viewed reel (Nov 2021) |  |  | 0 | Indicator achieved
|  |  | O.3.4 | Number of conferences/events attended where work has been showcased | 1 | Outreach events | 4.2.2 |  |  |  |  | 1 | 1 x conference |  |  | 4 | We have showcased our work at COP26, the UN Ocean Conference, and during the first meeting of the UK Blue Carbon Forum. Dan Crockett presented our blue carbon work at a webinar in association with EARTHLY (Nov 2021, May 2022, June 2022) |  |  | 0 | Indicator achieved
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Develop relationship with Defra climate team through meetings.
|  |  | A.3.2 | Liaise with Max Bello to convey findings and present case for inclusion of project case studies at COP26.
|  |  | A.3.3 | Lay the foundation for significant updates on project progress at subsequent COPs.
A.3.4
A.3.5
A.3.6
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maddie Millington-Drake for all 4 rows, please could you put the months against each of these numbers? Reply: @Maddie Millington-Drake
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note this was previously 4.2.2 but should have been 4.2.1

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Research findings are incorporated into a review of potential financial mechanisms that can support blue carbon restoration / conservation projects. | O.4.1 | Reports produced showing review of potential financial mechanisms that can support blue carbon restoration/ conservation projects | 2 | Reports | 5.1.1 | Copy of reports | [7 empty] | 1 | A report on the science, policy, co-benefits and market interests of blue carbon in the UK and overseas territories was published, which provides advice and evidence on the voluntary carbon market in the UK (Nov 2021) | 0 | Captured in output 1 | 0 | captured in output 1 | 1
O.4.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | Incorporate blue carbon and co-benefit valuation results into financial and economic analyses. This will underpin the design of financial investments based on blue carbon capture.
|  |  | A.4.2 | Produce a review on potential financial mechanisms that can support blue carbon/restoration conservation projects in collaboration withe BLUE Economics team and external financial consultants
A.4.3

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
1 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | A proposition that unlocks investment into blue carbon capture is created (linked to BLUE Economics – Connection 5). | O.5.1 | Number of partnerships formed with financial partners (or similar, specify) | 1 | Number of partnerships | 4.3.1 | [8 empty] | 1 | Finance Earth |  |  | 0 | Indicator achieved | 1
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Drawing on the key findings from the economic and financial analyses and review, BLUE will form a proposition that unlocks investment into blue carbon capture.
A.5.2
A.5.3
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maddie Millington-Drake please include month here Reply: @Maddie Millington-Drake

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Publicly available report is produced, presenting key findings and recommendations | O.6.1 | Number of reports produced | 12 | Reports | 5.1.1 | Number of reports published | [7 empty] | 0 | captured in output 1 | 0 | Papers captured in output 4 | 1 | We published a paper in Conservation Letters (Nov 22). | 5
O.6.2
O.6.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Compile research findings (both ecological and financial) into public-facing report, featuring the benefit of conserving and/or restoring BLUE project sites that feature blue carbon habitats.
A.6.2
A.6.3
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maddie Millington-Drake please include month Reply: @Maddie Millington-Drake Reply: @Maddie Millington-Drake also please could you provide more detail on what they are so I can check they haven't been included in other logframes? Reply: done - all captured elsewehere Reply: Ok cool, I am changing the value to zero from 5 so it doesn't add them to the calcs

## Output 7
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 7 | O.7 | Findings and recommendations are presented to key stakeholders and BLUE’s wider conservation network through a workshop event. | O.7.1 | Number of events/workshops held | 1 | Outreach activities/tools run | 4.2.2 | [8 empty] | 0 | Not started | 0 | Not started | 0 | Event will be held on the 18th October after the end of this funding
|  |  | O.7.2 | Number of attendees | 50 | Stakeholders reached | 4.2.1 | [8 empty] | 0 | Not started | 60 | We are aiming to have 60 attendees present | 0 | The final numbers have are unknown as the event has not occurred yet
O.7.3
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 7 Activities | A.7 |  | A.7.1 | Network with key stakeholders and host workshop to catalyse policy change. This will likely include key policy makers, marine authorities, researchers, NGOs, academics and the corporate/financial industry.
A.7.2
A.7.3
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many expected across lifetime of project?
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many expected across lifetime of project?

## Output 8
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 8 | O.8 | The profile of blue carbon is raised as a climate change mitigation strategy, encouraging inclusion within the government’s Nationally Determined Contributions (NDCs). | O.8.1 | Uptake of blue carbon recommendations/advice from Blue Marine within government | 2 | Evidence uptake by govt | 5.1.3 | [8 empty] | 0 | After a range of meetings and conversations with Defra and the CCC regarding blue carbon. Blue Marine was happy to see two progressions – 1) A CCC briefing on blue carbon, with advice and recommendations to BEIS to pursue blue carbon policy; 2) The potential for “blue carbon value” notified by the MMO within new areas closed to fishing. | 0 | We are having productive calls with the gov't but progress is slow for them to add blue carbon into the NDC. We are waiting for DEFRAs evidence needs statement | 0 | We are having productive calls with the gov't but progress is slow for them to add blue carbon into the NDC | 2
O.8.2
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 8 Activities | A.8 |  | A.8.1 | Synthesise the results from this project, integrated ecosystem restoration (Restoration – 1), kelp restoration in Sussex (Sustainable Management – 2), any other projects where climate impact has been quantified through this project, such as the blue carbon habitats of Jersey (Protection – 4), and BLUE Economics.
|  |  | A.8.2 | Package and present all relevant evidence at the highest possible political level.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many expected across lifetime of project?
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: could possibly be 2.4.1 if the nature of reports are more about restoration of blue carbon habitats)
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Maddie Millington-Drake please include month Reply: I'm really sorry I don't know when this happened - it was before me! I would say March - April Reply: no worries at all - an estimate will do fine in that case :) could you please pop that into the cell text?

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 4 | 8 | O.1 | O.1.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 4 | 8 |  | O.1.3 | 0% | 0% | 0% | 133.3% | 0% | 133.3% | 33.33% | 100% | 233.3% | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | O.1.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 1 | 5 | O.2 | O.2.1 | 0% | 0% | 0% | 140% | 0% | 140% | 0% | 0% | 140% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 3 | 7 |  | O.2.2 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 7 | 3 | 7 |  | O.2.3 | 0% | 0% | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 8 | 2 | 6 | O.3 | O.3.1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | 0% | 622% | 0% | 133.4% | 0% | 755.4% | 0% | 0% | 755.4% | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | 0% | 0% | 0% | 50% | 0% | 50% | 0% | 0% | 50% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 8 |  | O.6 | O.6.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 8.333% | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.7 | O.7.1 | 0% | 0% | 0% | 0% | 0% | 0% | 6000% | 0% | 0% | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.2 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.7.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.8 | O.2.1 | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0% | 0% | 0% | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! | #DIV/0! | #DIV/0! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 93300 | 20017 | 0 | 0 | 0 | 0 | 113317 | 0 | 113317 | 15050 | 0 | 0 | 0
[14 empty] | 4.2.2 | 1 | 4 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 1 | 0 | 0 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 29 | 0 | 0 | 0 | 0 | 29 | 0 | 29 | 0 | 29 | 29 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 5 | 4 | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 10 | 10 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0