## Instructions
This logframe document is to help with the design and tracking of the NIMPA+ Project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
2024-03-01
2024-04-01
2024-05-01
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01
2026-02-01
2026-03-01
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01

## Detailed Theory of Change
Note on T5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not essential to have TOC but have included it in case it helps simplify this logframe and the relationships between each reporting level. Feel free to amend if anything has been missed/misinterpreted. Typically, TOCs have inputs as well, however I've left these out.

## Goal (Impact)
Goal (Impact/Overall Objective) |  |  | Indicators | [9 empty] | Tracking/Reporting
| Code | Description | Goal Indicator (BAF) | Measureable Indicators | Related outputs | Related BMF sub-indicators (Impact) | Related BMF Core Impact Indicators | Base value (at project start) | Target value (end of project) | Status | Means of verification | Important Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
[13 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Goal (Impact/Overall Objective) | G.1 | Networks of globally significant protected areas and their sustainable use zones are conserved | G.1 | At the end of the project, the biomass of one or more relevant umbrella/ indicator species is maintained or increased in the project areas | [5 empty] | Not started (as planned) | For the African Penguin Climate change and flooding cause risk, as well as rouge seals creating havoc and increase in Kelp Gull predation. | Populations of selected indicator species are not adversely impacted by external influences (e.g., introduction of disease, environmental conditions or unsustainable extraction arising beyond MPA boundaries)
|  |  | G1a | # Active nests (breeding pairs) of African penguins across all NIMPA sites | 1 | 2.2.1, 2.2.3 | 2.2 | G1a. Active nests (breeding pairs) of African penguins: Total of 485 pairs across all NIMPA sites | G1a. Active nests (breeding pairs) of African penguins: Total of 534 pairs (10% increase of active nests (breeding pairs) of African penguins across all NIMPA sites) | Not started (as planned) |  | For the African Penguin Climate change and flooding cause risk, as well as rouge seals creating havoc and increase in Kelp Gull predation. | 0 | Establish baseline value | 0 | Baseline established | Baseline value maintained | Deploy 3 seabird rangers; Operationalise NAMCOB
|  |  | G1b | # Chondrichthyans species in NIMPA | 1 | 2.2.1 | 2.2 | G1b. Chondrichthyans species: TBD by Q4/2023 | G1b. Chondrichthyans species: Baseline maintained | Not started (as planned) | Elasmobranch species: BRUV surveys to provide ‘maxN’ information on relative abundance of elasmobranch species for all 3 sites | For elasmobranch work, risks would be rough sea conditions and low visibility generally, in NIMPA strong winds are hazardous | 0 | Establish baseline value | 0 | Baseline establishment delayed due to hazardous strong winds | 0 | Establish baseline value
|  |  | G1c | # Chondrichthyans species in Cape Fria | 1, 4 | 2.2.1 | 2.2 | G1c. Chondrichthyans species: TBD by Y3 | G1c. Elasmobranch species: Baseline maintained | Not started (as planned) |  |  | 0 | Not yet expected | 0 | Not yet expected | 0 | Not yet expected | 0 | Not yet expected
|  |  | G1d | # Elasmobranch species in Namibe | 1, 4 | 2.2.1 | 2.2 | G1d. Elasmobranch species: TBD by Y3 | G1d. Elasmobranch species: Baseline maintained | Not started (as planned) |  |  | 0 | Not yet expected | 0 | Not yet expected | 0 | Not yet expected | 0 | Not yet expected
|  |  | G1e | # Cape fur seal in Cape Fria | 1, 4 | 2.2.1 | 2.2 | G1e. Cape fur seal colony: TBD during inception phase | G1e. Cape fur seal colony: Baseline maintained | Not started (as planned) | Cape fur seal: Annual arial survey report data for South Africa, Namibia, and Angola Scat analysis pilot within the NIMPA, providing critical information regarding available forage species, which in turn will inform management decisions. | For Cape fur seal: the international survey of Namibia, South Africa and Angola is taking place annually and data will be derived thereof. At times there is fog, hence there is a possibility that one would not get data from all colonies for all years | 41911 | Establish baseline value | 41911 | Established baseline
|  |  | G1f | # Cape fur seal in Namibe | 1, 4 | 2.2.1 | 2.2 | G1f. Cape fur seal colony: TBD during inception phase | G1f. Cape fur seal colony: Baseline maintained | Not started (as planned) |  |  | 3707 | Establish baseline value of seal pups | 3707 | Established baseline value of seal pups | 3707 | Maintain baseline
| G.2 |  | G.2 | At the end of the project, improved livelihood conditions of affected households in project areas |  |  |  | Household incomes of affected people in Lüderitz to be determined during Inception Phase | Household incomes of affected people in Lüderitz have increased by 20% (in real terms) over the project period | Not started (as planned) | Socioeconomic household surveys conducted by consortium during inception phase and last year of project | Livelihoods are not adversely impacted by external shocks, (e.g., natural disasters or political crises) during project delivery | 0 | Identify target groups; Establish baseline value | 0 | Baseline established for target groups | Baseline value + x%
|  |  | G.2a |  | 2, 3 | 4.1.1, 4.2.3 | 4.1, 4.2 | X % of households affected in the project area (Lüderitz) have a positive attitude toward the protection of marine biodiversity (to be determined during inception phase) | An increase of 50% of households in project areas have a positive attitude towards protection of marine biodiversity | Not started (as planned) | Knowledge, Attitude and Practice (KAP) surveys conducted by consortium during inception phase and last year of project | By communicating the values of marine ecosystem services to local communities, they will develop more positive attitudes to marine biodiversity | 0 | Establish baseline value | 88% | Baseline value established however not a true reflection of the attitudes of community towards marine biodiversity | 0 | KAP Baseline survey to be revised; sample size to be increased
On Track
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You may want to check through the NIMPA+ Planned activities document and add in all output links or even specific indicators/activities if it's useful for you and the team to highlight how these higher level goals are linked with the other output/activity tabs. Up to you.
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note these are Blue Marine impact indicator codes. You don't need to change these, they are included on all our project logframes to help us quantify progress towards Blue Marine's own core impact indicators/impact pillars that reflect our own organisation mission. I have included 'BMF' to flag that these are Blue Marine-relevant. Feel free to 'hide' these columns if you'd prefer.
Note on K4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This section was blank in the NIMPA+ Logframe. Please add text if available to descriibe the indicator
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities

## Outcome
Outcome |  |  | Indicators | [9 empty] | Tracking/Reporting
| Code | Description | Outcome Indicator Number | Measureable Indicators | Status | Related outputs | Related BMF sub-indicators (Impact) | Related BMF Core Impact Indicators | Base value (at project start) | Target value (end of project) | Means of verification | Important Assumptions | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
[13 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Outcome | OC.0 | Namibia’s marine protected areas network is strengthened and expanded | OC.0.1 | Namibia expands its national MPA coverage | Not started (as planned) | 2,4 | 1.1.1, 1.2.1, 4.1.1, 4.2.1, 4.2.2 | 1.1, 1.2, 4.1, 4.2 | MPA coverage 9,500 km2 (1.7% of Namibia EEZ) | MPA coverage 15,775km2 (2.7% of Namibia EEZ) | Formal government gazettement of two (2) new MPAs (Namibe and Cape Fria) | There is sufficient political will for the expansion of the national MPA system | 0 | Not yet expected | 0 | Not yet expected | 0 | Initiate discussion with MFMR on progression of MSP for Northern and Southern Namibia
|  |  | OC.0.2 | NIMPA’s management effectiveness score (using NAMETT, or similar assessment tool) | Not started (as planned) | 1 | 4.1.2 | 4.1 | x/110 (TBD in inception phase) | NIMPA’s management effectiveness score (using NAMETT, or similar assessment tool) increases by at least 33% by the end of project | Management effectiveness assessments using the ‘NAMETT’ management effectiveness tool | Those broader sectoral policies and regulations (e.g., fisheries permitting, hydrogen production or mining) do not undermine efforts to improve NIMPA effectiveness | 0/110 | Establish baseline value | 45/114 | Baseline established | 45/114 | Annual scoring no increase expected because the management plan is not implemented
|  |  | OC.0.3 | Indicative percentage of small-scale fishers who report positive change in their ability to engage in MPA co-management | Not started (as planned) | 3 | NA | NA | 0% of small-scale fishers | Over 50% of small-scale fishers report positive change in ability to engage in MPA co-management | SSF association membership and social survey post-project on co-management situation | The MPA is more likely to be successful if co-management opportunities are broadened | 0 | Define SSF association membership and governance structure | 0 | Membership criteria established | 0 | Establish membership base; combine co-management survey with socio-economic survey (conduct with SSF association); engage SSF members to get involved in monitoring, control and surveilance and catch monitoring (ABALOBI)
|  |  | OC.0.4 | Livelihoods of women enhanced | Not started (as planned) | 3 | 4.1.2, 4.2.2 | 4.1, 4.2 | 0% of women living off coastal resources have diversified their income (N=x) | By the end of the project, 10% of women living off coastal resources have diversified their income (N=y). | Social survey post-project results from vocational training and livelihoods projects, SSF association membership | Sufficient interest from women in Lüderitz for project livelihood activities | 0 | Establish baseline value; SDFN surveyed (socio-economic) |  | Supported SDFN to aqcuire funds for community projects
On Track
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that we haven't included output 5 in terms of a link up to the outcome. My interpretation is that output 5 is more to demonstrate effective project delivery and M&E. please amend if you feel otherwise!
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities

## Output 1
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
4 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | NIMPA’s formal management system is improved and implemented | O.1.1 | Revised NIMPA management framework including gender considerations | 1 | Frameworks changed |  | Outdated NIMPA management framework with no reference to gender considerations | Updated NIMPA management framework endorsed with direct reference to gender considerations | MFMR endorsement of revised NIMPA management framework including; management plan, regulations, zoning, financing and operational requirements. Monitoring, control and enforcement system in place. Sustainable financing plan report. | MFMR endorses the framework | Not started (as planned) | 0 | Management framework review | 0 | Management framework reviewed | 1 | Framework approved and endorsed
|  |  | O.1.2 | Data and information system required for NIMPA’s ongoing management is created and endorsed | 1 | data and information system | NA | No data and information system | 1 data and information system | Copies of data, or outputs (e.g., reports, maps) generated by system/s | The data and information system proposed is supported by MFMR and they endorse it | Not started (as planned) | 0 | Conduct scoping for data management system | 0 | Scoping done for data management system | 1 | Data management system implemented
|  |  | O.1.3 | Number of key MFMR personnel trained / capacitated in MPA management | 20 | Beneficiaries (people trained) | 4.1.2 | 0 key MFMR personnel trained / capacitated in MPA management | 20 key MFMR personnel trained / capacitated in MPA management | Copies of training reports, participation lists, formal government notices, media articles | There is unmet demand within NIMPA authority for capacity building support | Not started (as planned) | 0 | Not yet expected | 0 | Not yet expected | 20 | Conduct capacity needs assessment and skills audit
|  |  | O.1.4 | Number (percentage) of measures in updated management plan that have been implemented |  | Implemented measures | NA | 0% of measures in updated management plan are being implemented | 50% of measures in updated management plan are being implemented | Reports from management planning meetings and workshops including management assessments, workplan reviews | Assumes MFMR endorses the management plan and allocates resources for implementation | Not started (as planned) | 0 | Establish baseline value through review process | 0 | Baseline established 45 meausres included in the revised framwork | 0 | Framework approved and endorsed before implementation starts (not yet expected)
Activities | [11 empty] | On Track
| Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status | Notes
Output 1 Activities | A.1 |  | Indicator 1.1 | Revised NIMPA management framework |  |  | Delayed
|  |  | Activity 1.1.1 | Review and revise NIMPA’s existing management framework | NNF; Blue Marine; SAERI; Grid-Arendal | 2025-12-31 | On Track
|  |  | Deliverable 1.1.1 a | Technical review of NIMPA’s existing management framework | NNF; Blue Marine; SAERI | 2023-12-31 | Complete
|  |  | Deliverable 1.1.1 b | Reviewed and update NIMPA regulations | NNF; Blue Marine; SAERI | 2024-06-30 | Complete
|  |  | Deliverable 1.1.1 c | Reviewed NIMPA zonation system and access restrictions | SAERI | 2023-12-31 | In progress
|  |  | Deliverable 1.1.1 d | Reviewed NIMPA management plan | NNF; Blue Marine | 2024-12-31 | In progress
|  |  | Deliverable 1.1.1 e | Implementation guidelines for MPAs in Namibia | Blue Marine | 2024-06-30 | Not started (as planned)
|  |  | Deliverable 1.1.1 f | NIMPA’s updated Management framework validated and approved | NNF; Blue Marine | 2025-06-30 | Not started (as planned)
|  |  | Deliverable 1.1.1 g | NIMPA work plans | NNF; Blue Marine | 2025-09-30 | Not started (as planned)
|  |  | Deliverable 1.1.1 h | NIMPA communications plan | Grid-Arendal | 2024-06-30 | In progress
|  |  | Deliverable 1.1.1 i | 20 people involved in MPA management processes attend gender focused discussions | NNF | 2025-09-30 | Not started (as planned)
|  |  | Activity 1.1.2 | Develop a Monitoring, Control, Surveillance (MCS) system for NIMPA | NNF | 2024-09-30 | Delayed
|  |  | Deliverable 1.1.2 a | Risk Assessment & MCS scoping for NIMPA including capacity needs | NNF | 2024-06-30 | In progress
|  |  | Deliverable 1.1.2 b | SMART, EarthRanger (or other) module for the Namibian Marine Ecosystem developed | NNF | 2023-12-31 | Delayed
|  |  | Deliverable 1.1.2 c | 20 users of monitoring system trained | NNF | 2024-06-30 | Not started (as planned)
|  |  | Activity 1.1.3 | NIMPA and the two new MPAs have a sustainable financing plan | NNF; Blue Marine | 2026-03-31 | Delayed
|  |  | Deliverable 1.1.3 a | Scoping report on the potential finance mechanisms and blended finance options for NIMPA & developing MPAs | Blue Marine | 2023-12-31 | Delayed
|  |  | Deliverable 1.1.3 b | Sustainable financing plan | NNF, Blue Marine | 2025-03-31 | Not started (as planned)
|  |  | Deliverable 1.1.3 c | On-going budgeting support to MFMR provided | NNF, Blue Marine | 2028-03-31 | In progress
|  |  | Deliverable 1.1.3 d | Technical recommendations and communication of ecosystem services studies to demonstrate the benefits of NIMPA | NNF, Blue Marine | 2024-06-30 | Not started (as planned)
|  |  | Deliverable 1.1.3 e | Technical recommendations on feasible options and mechanisms for the sustainable financing of NIMPA | NNF, Blue Marine | 2025-06-30 | In progress
|  |  | Deliverable 1.1.3 f | Tools, processes and templates for broader financing needs across Namibia’s developing MPA network developed | NNF, Blue Marine | 2025-12-31 | Not started (as planned)
|  |  | Activity 1.1.4 | Establish and support a Marine Protected Area Advisory Board (MPAAB) | NNF | 2024-12-31 | On Track
|  |  | Deliverable 1.1.4 a | MPAAB established | NNF | 2024-09-30 | Not started (as planned)
|  |  | Deliverable 1.1.4 b | MPAAB annual meetings | NNF | 2027-09-30 | Not started (as planned)
|  |  | Indicator 1.2 | Data and information systems required for NIMPA’s ongoing management are created and endorsed |  |  | On Track
|  |  | Activity 1.2.1 | Develop a monitoring and research strategy | SANCCOB; NAMCOB; NNF | 2024-12-31 | On Track
|  |  | Deliverable 1.2.1 | Monitoring and research strategy | SANCCOB; NAMCOB; NNF | 2024-09-30 | Not started (as planned)
|  |  | Activity 1.2.2 | Design and implement an information management support system for NIMPA | SAERI | 2025-06-30 | On Track
|  |  | Deliverable 1.2.2 a | Data management portal | SAERI | 2024-06-30 | In progress
|  |  | Deliverable 1.2.2 b | Training on data management portal | NNF; SAERI | 2025-03-31 | Not started (as planned)
|  |  | Activity 1.2.3 | Undertake periodic monitoring of indicator species | SANCCOB; NAMCOB; NNF | 2028-03-31 | On Track
|  |  | Deliverable 1.2.3 a | Support to MFMR with establishing baseline information on the key indicator species | NNF | 2023-09-30 | In progress
|  |  | Deliverable 1.2.3 c | Annual African penguin population survey | SANCCOB; NAMCOB | 2027-12-31 | Complete
|  |  | Deliverable 1.2.3 d | App-based recreational angler and small-scale fisher survey (NIMPA) | NNF | 2024-12-31 | Not started (as planned)
|  |  | Deliverable 1.2.3 e | 2 Assessments of elasmobranch bycatch in commercial fisheries (demersal hake trawlers) for Namibia | NNF | 2025-12-31 | In progress
|  |  | Deliverable 1.2.3 f | Seasonal chondrichthyan survey using Baited Remote Underwater Videos (BRUVs) - for NIMPA | NNF | 2024-12-31 | In progress
|  |  | Deliverable 1.2.3 g | Seasonal elasmobranch survey using Baited Remote Underwater Videos (BRUVs) - for Cape Fria and Namibe; where feasible | NNF | 2027-12-31 | Not started (as planned)
|  |  | Deliverable 1.2.3 h | Passive telemetry assessment - data on patterns of movement and habitat use of individual chondrichthyans | NNF | 2025-12-31 | Not started (as planned)
|  |  | Deliverable 1.2.3 j | Baselines on Elasmobranch species (Cape Fria / Namibe) | NNF | 2025-12-31 | Not started (as planned)
|  |  | Deliverable 1.2.3 k | Annual monitoring of seals (NIMPA); spatial distribution and diets | NNF | 2027-12-31 | In progress
|  |  | Deliverable 1.2.3 l | Baselines for Cape fur seals (Cape Fria / Namibe) | NNF | 2025-12-31 | Complete
|  |  | Indicator 1.3 | Number of key MFMR personnel trained/capacitated in MPA management |  |  | On Track
|  |  | Activity 1.3.1 | Design and implement a Training and Capacity Plan for MFMR in support of MPA management | NNF; SAERI | 2025-03-30 | On Track
|  |  | Deliverable 1.3.1 a | Capacity and Structural Needs Assessment and Skills Audit | NNF; SAERI | 2024-03-30 | In progress
|  |  | Deliverable 1.3.1 b | Training and capacity plan | NNF; SAERI | 2024-03-30 | In progress
|  |  | Deliverable 1.3.1 c | 8 MFMR trained key staff - local | NNF | 2024-06-30 | In progress
|  |  | Deliverable 1.3.1 d | 8 key MFMR staff trained - national | NNF | 2024-06-30 | In progress
|  |  | Deliverable 1.3.1 e | 4 MFMR staff trained - regional/ exchange | NNF | 2024-12-31 | In progress
|  |  | Activity 1.3.2 | Conduct transformative gender programme | NNF | 2025-09-30 | On Track
|  |  | Deliverable 1.3.2 a | Develop a transformative gender training program | NNF | 2025-03-30 | Not started (as planned)
|  |  | Deliverable 1.3.2 b | Workshop on transformative gender programme | NNF | 2025-06-30 | Not started (as planned)
|  |  | Indicator 1.4 | 50% of measures in the revised draft of the management plan are implemented by the project end |  |  | On Track
|  |  | Activity 1.4.1 | Asses MPA performance and management effectiveness | NNF | 2028-03-30 | In progress
|  |  | Deliverable 1.4.1 | Annual assessment of MPA performance and management effectiveness | NNF | 2027-12-31 | In progress
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The original logframe for this project says percentage of measures updated but we report on number - by calculating the percentage we must know the number so it shouldn't make extra work to find this number
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Input target value here to get value in analysis tab
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.5 measures implemented by 2028
Note on M8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Output 2
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
4 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Effective management of NIMPA is supported by an active civil society and engaged coastal communities of Lüderitz | O.2.1 | Local community members are engaged in project outreach activities related to marine conservation and protected areas | 1000 | Stakeholders reached (coastal community) | 4.2.1 | 0 coastal community members are engaged in outreach activities related to marine conservation and protected areas | 10% of (relevant) coastal community members are engaged in outreach activities related to marine conservation and protected areas, equating to at least 1,000 (relevant) coastal community members | Copies of attendance lists at NIMPA’s events, post-activity exit surveys, other relevant community feedback | Assumes willingness and availability of community to engage | Not started (as planned) | 200 | Conduct outreach activties for schools for coastal community members | 275 | Conducted outreach activties for schools for coastal community members | 200 | Conduct outreach activties for schools; crayfish festival; finalise ocean literacy toolkit
|  |  | O.2.2 | New conservation NGO NAMCOB is formalised and operationalised | 1 | Newly formalised and operationalised NGO | NA | NAMCOB is formalised with a signed constitution and elected board and is currently recruiting | NAMCOB is operationalised; it has an endorsed organisational strategy, and key staff are active in their roles | Copies of, relevant strategic documents, annual reports, or activity reports | Assumes MFMR acceptance of NAMCOB’s role / function in NIMPA management | Not started (as planned) | 0 | Formalise NAMCOB; Establish ExCo | 0 | Formalised NAMCOB; Establish ExCo | 1 | Employ key staff positions; operationalise NAMCOB (procurement of equipment, recontruction of buildings, access to islands etc
|  |  | O.2.3 | NAMCOB provides effective support to the management of NIMPA | 4 | Seabird rangers | 4.1.1 | NAMCOB does not provide effective support to the management of NIMPA | NAMCOB provides effective support to the management of NIMPA through the deployment of 4 seabird rangers to the main breeding sites (island) and actively monitors and rescues seabirds | Annual reports NAMCOB in line with monitoring and research strategy | Assumes MFMR acceptance of NAMCOB’s role / function in NIMPA management | Not started (as planned) | 4 | Deploy 4 seabird rangers to breeding sites | 0 | 6 Seabird rangers interviewed; psychological interviews conducted; 3 potential rangers taken for an exposure trip to the breeding sites | 3 | Seabird rangers trained at SANCCOB and deployed to Luderitz; access to islands granted by MFMR
|  |  | O.2.4 | Ocean Literacy Toolbox and SMART lessons are developed | 2 | Resources | 4.2.2 |  |  | Copies of toolbox and lessons, digital. | Assumes willingness and availability of education stakeholders to input, and that there is unmet demand for marine education locally | Not started (as planned) | 0 | Develop draft of ocean literacy toolkit; SMART lesson not yet expected | 0 | Draft of ocean literacy toolkit developed; SMART lesson not yet expected | 2 | SMART lesson and Ocean Literacy Toolkit developed |  |  | 0 | Draft toolbox will be produced, but not finalised. SMART lessons = 2024 output. | 0 | Q1: NA. Q2: Toolbox draft is underway, workshop event is planned for August to bring education stakeholders together.
Activities | [11 empty] | On Track
| Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status | Notes
Output 2 Activities | A.2 |  | Indicator 2.1 | Local community and stakeholders are engaged in project outreach activities related to marine conservation and protected areas |  |  | Delayed
|  |  | Activity 2.1.1 | Assess and communicate current knowledge attitudes and practices of local communities in relation to NIMPA | NNF; Grid-Arendal, COSDEC | 2028-03-31 | On Track
|  |  | Deliverable 2.1.1 | 1 KAP surveys conducted and analysed | NNF; Grid-Arendal; COSDEC | 2023-09-30 | In progress
|  |  | Deliverable 2.1.1 | 2 KAP surveys conducted and analysed | NNF; Grid-Arendal; COSDEC | 2025-12-31 | Not started (as planned)
|  |  | Deliverable 2.1.1 | 3 KAP surveys conducted and analysed | NNF; Grid-Arendal; COSDEC | 2028-03-30 | Not started (as planned)
|  |  | Activity 2.1.2 | Develop and implement local marine education | NNF; Blue Marine; COSDEC; | 2028-03-31 | Delayed
|  |  | Deliverable 2.1.2 a | Ocean literacy toolbox for Namibia | NNF; COSDEC; Blue Marine; Grid-Arendal | 2023-12-31 | Delayed
|  |  | Deliverable 2.1.2 b | Digital (Smart) lessons for ocean literacy in Namibia | NNF; COSDEC; Blue Marine; Grid-Arendal | 2024-03-30 | In progress
|  |  | Deliverable 2.1.2 c | Ocean literacy outreach in Lüderitz | NNF; COSDEC; Blue Marine; Grid-Arendal | 2028-03-30 | In progress
|  |  | Deliverable 2.1.2 d | Schools outreach with youth in Lüderitz | NNF; COSDEC; Blue Marine; Grid-Arendal | 2028-03-30 | In progress
|  |  | Deliverable 2.1.2 e | Ocean literacy outreach at national events | NNF; COSDEC; Blue Marine; Grid-Arendal | 2028-03-30 | In progress
|  |  | Deliverable 2.1.2 f | By the end of the project coastal community members are engaged in outreach activities (X participants) | NNF; COSDEC | 2028-03-30 | In progress
|  |  | Activity 2.1.3 | Facilitate the formulation of a “NIMPA Users Forum” | NNF; COSDEC | 2025-09-30 | On Track
|  |  | Deliverable 2.1.3 a | Community mobilisation and facilitation | NNF; COSDEC | 2025-06-30 | Not started (as planned)
|  |  | Deliverable 2.1.3 b | 2 NIMPA Users Forums conducted | NNF; COSDEC | 2025-09-30 | Not started (as planned)
|  |  | Indicator 2.2 | New conservation NGO NAMCOB is formalised and operationalised |  |  | Delayed
|  |  | Activity 2.2.1 | NAMCOB organisational strategy, management plan and financial plan are developed and implemented | NNF; SANCCOB; NAMCOB | 2024-12-31 | Delayed
|  |  | Deliverable 2.2.1 a | MOU with MFMR |  | 2023-12-31 | Delayed
|  |  | Deliverable 2.2.1 b | NAMCOB’s organizational strategy |  | 2023-12-31 | Delayed
|  |  | Deliverable 2.2.1 c | NAMCOB’s management plan |  | 2023-12-31 | Delayed
|  |  | Deliverable 2.2.1 d | Recruit and train NAMCOB’s director and seabird rangers, seabird rehabilitator, administrative assistant |  | 2023-12-31 | Delayed
|  |  | Deliverable 2.2.1 e | Annual work plans |  | 2027-12-31 | Delayed
|  |  | Deliverable 2.2.1 f | Financial strategy that for NAMCOB’s long-term sustainability |  | 2024-12-31 | Not started (as planned)
|  |  | Deliverable 2.2.1 g | NAMCOB board annual meetings |  | 2027-12-31 | Not started (as planned)
|  |  | Activity 2.2.2 | The NAMCOB centre is set-up and operationalised | NNF; SANCCOB; NAMCOB | 2028-03-31 | Delayed
|  |  | Deliverable 2.2.2 a | Oil response Equipment on Mercury, Ichaboe, Possession and Halifax island |  | 2023-12-31 | Delayed
|  |  | Deliverable 2.2.2 b | NAMCOB Centre development (building renovation) |  | 2024-12-31 | In progress
|  |  | Deliverable 2.2.2 c | NAMCOB Centre development (equipment) |  | 2027-12-31 | In progress
|  |  | Deliverable 2.2.2 d | 20 x local volunteers and interns trained at NAMCOB to assist with educational tours around the centre, as well as working hands-on with the seabirds. |  | 2028-03-31 | Not started (as planned)
|  |  | Indicator 2.3 | NAMCOB provides effective support to the management of NIMPA |  |  | Delayed
|  |  | Activity 2.3.1 | Develop and implement NAMCOB’s ecological monitoring plan in support of NIMPA | SANCCOB; NAMCOB; SAERI | 2025-03-31 | On Track
|  |  | Deliverable 2.3.1 a | Standardised data collection and seabird monitoring system document | SANCCOB; NAMCOB; SAERI | 2024-03-31 | Not started (as planned)
|  |  | Deliverable 2.3.1 b | A Fishery-seabird mitigation interventions and new emerging threats to seabird ecosystem health document is developed | SANCCOB; NAMCOB; SAERI | 2024-12-31 | Not started (as planned)
|  |  | Activity 2.3.2 | Deployment of Seabird Rangers and implement seabird monitoring system | SANCCOB; NAMCOB | 2024-03-31 | Delayed
|  |  | Deliverable 2.3.2 a | Seabird rangers deployed on island | SANCCOB; NAMCOB | 2023-12-31 | Delayed
|  |  | Deliverable 2.3.2 b | 5 x First-responder training: Rescuing and stabilising seabirds along the coast until the seabirds are transported to NAMCOB for care | SANCCOB; NAMCOB | 2023-12-31 | Delayed
|  |  | Deliverable 2.3.2 c | Seabird monitoring system developed and implemented | SANCCOB; NAMCOB | 2023-12-31 | Delayed
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not in NIMPA+ Logframe document
Note on M8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Output 3
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
4 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Coastal livelihoods are diversified and strengthened | O.3.1 | A fisher’s association is created to support small-scale fishers operating in NIMPA waters | 1 | Working groups | NA | 0 small-scale fisher’s association operating in NIMPA waters | 1 small-scale fishers association operating in NIMPA waters | Constitution; Minutes of AGM, association constitution/rules, membership lists, media articles | Sufficient ability of SSF to commit to a small-scale fishers association process for duration of project | Not started (as planned) | 0 | Conduct scoping | 0 | Engaged with existing SSF association and supported them in getting operationalised | 1 | Support organisational setup and operationalisation
|  |  | O.3.2 | New livelihood diversification opportunities created | 35 | Beneficiaries (non monetary) | 4.1.2 | 0 participants | 35 participants in livelihood diversification opportunities: Opportunity A (TBD in inception period): x number of participants (y women; z men) Opportunity B (TBD in inception period): x number of participants (y women; z men) Opportunity C (TBD in inception period): x number of participants (y women; z men) | Opportunity registration forms, attendance records, completion certificates, SME registers | Sufficient interest, trust, goodwill among community and partners to develop these strategies | Not started (as planned) | 0 | Identify livelihood diversification opportunities | 0 | Identified 4 livelihood diversification opportunities | 30 | Support tour guides; provide horticulture training; provide opportunities via msme revolving fund
|  |  | O.3.3 | Number of women participating in project livelihoods activities | 33 | Beneficiaries (non monetary) | 4.1.2 | 0 women participating in project livelihoods opportunities at present | 33 women participating in project livelihoods opportunities | Opportunity registration forms, attendance records, completion certificates, SME registers | Sufficient interest from women in Lüderitz for project livelihood opportunities | Not started (as planned) | 0 | Conduct scoping on identifying livelihood diversification opportunities; engage with groups prodimantly working with women | 0 | Identified 4 livelihood diversification opportunities; engaged with SDFN as a target group for project livelihood activities
|  |  | O.3.4 | A platform for Corporate Social Responsibility (CSR) activities coordinates measures of maritime industry stakeholders to address vulnerabilities of the coastal community | 1 | Platform (outreach activity) | 4.2.2 | No platform exists | A platform is created and coordinates maritime stakeholders in CSR activities to address vulnerabilities of the coastal community | Evidence of CSR contributions, media articles, attendance lists from CSR activities | Assumes sufficient goodwill / contributions on behalf of maritime industries | Not started (as planned)
Activities | [11 empty] | On Track
Output 3 Activities | Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status | Notes
| A.3 |  | Indicator 3.1 | A fisher’s association is created to support small scale fishers (SSF) operating in NIMPA waters |  |  | On Track
|  |  | Activity 3.1.1 | Design and develop a Fishers Association to support SSF operating in NIMPA waters | NNF; COSDEC | 2025-03-31 | On Track
|  |  | Deliverable 3.1.1 a | Scoping of SSF Association (including gleaners and SSFs) | NNF; COSDEC | 2023-09-30 | Complete
|  |  | Deliverable 3.1.1 b | Operationalised Association of SSF | NNF; COSDEC | 2024-12-31 | In progress
|  |  | Deliverable 3.1.1 c | SSF Association members trained in monitoring, climate change adaption and other capacity needs as identified | NNF; COSDEC | 2026-12-31 | Not started (as planned)
|  |  | Deliverable 3.1.1 d | 155 small-scale fisheries (SSF), benefitting from practical sustainable livelihood measures which benefit all SSFs | NNF; COSDEC | 2028-03-31 | Not started (as planned)
|  |  | Deliverable 3.1.1 e | 60 SSFs attend gender awareness sessions | NNF | 2025-09-30 | Not started (as planned)
|  |  | Activity 3.1.2 | Establish community catch monitoring to assist management of community fisheries | NNF | 2025-09-30 | On Track
|  |  | Deliverable 3.1.2 a | Citizen science monitoring training support for SSFs | NNF | 2025-06-30 | Not started (as planned)
|  |  | Deliverable 3.1.2 b | Develop & distribute species ID guides | NNF | 2024-12-31 | In progress
|  |  | Indicator 3.2 | Number of participants in new livelihood diversification opportunities |  |  | Delayed
|  |  | Activity 3.2.1 | Develop opportunities for local tour guides | NNF; COSDEC | 2024-12-31 | On Track
|  |  | Deliverable 3.2.1 a | Tailor-made tour guide training material | NNF | 2024-12-31 | In progress
|  |  | Deliverable 3.2.1 b | 10 tour guides trained and successfully gaining incomes from tourism | NNF; COSDEC | 2024-09-30 | Not started (as planned)
|  |  | Activity 3.2.2 | Assess and develop new coastal livelihoods opportunities | NNF; COSDEC | 2024-06-30 | Delayed
|  |  | Deliverable 3.2.2 a | Feasibility of a local market | NNF; COSDEC | 2023-09-30 | Complete
|  |  | Deliverable 3.2.2 b | Feasibility study mariculture | Blue Marine | 2023-09-30 | Delayed
|  |  | Deliverable 3.2.2 c | Pending outcomes feasibility studies either (1) business plan and financing strategy for the artisanal local market and/or (2) pilot mariculture MSME with local community beneficiaries | NNF | 2024-03-31 | In progress
|  |  | Activity 3.2.3 | Provide business support and mentoring to new coastal MSMEs | NNF; COSDEC | 2025-03-31 | On Track
|  |  | Deliverable 3.2.3 | Training on business support and mentoring new coastal MSMEs | NNF; COSDEC | 2024-12-31 | In progress
|  |  | Activity 3.2.4 | Provide microfinance to coastal community livelihoods enterprises | NNF; COSDEC | 2025-03-31 | On Track
|  |  | Deliverble 3.2.4 a | Revolving loan fund for MSMEs established and operational | NNF; COSDEC | 2024-12-31 | In progress
|  |  | Deliverble 3.2.4 b | 10 people are trained mentored and have received a loan to start or strengthen their MSME and have increased their incomes by 20% |  | 2028-03-31 | Not started (as planned)
|  |  | Indicator 3.4 | A platform for Corporate Social Responsibility (CSR) activities coordinates measures of maritime industry stakeholders to address vulnerabilities of the coastal community |  |  | On Track
|  |  | Activity 3.4.1 | Establish and facilitate a platform for corporate social responsibility (CSR) managers with coastal industries in Lüderitz | NNF | 2025-03-31 | On Track
|  |  | Deliverable 3.4.1 a | CSR platform established | NNF | 2024-12-31 | Not started (as planned)
|  |  | Deliverable 3.4.1 b | Gender transformative training for CSR managers | NFF | 2025-09-30 | Not started (as planned)
|  |  | Deliverable 3.4.1 c | 5 maritime stakeholders engaged in corporate social responsibility (CSR) activities to address vulnerabilities (social and gender risks) of the coastal community | NNF | 2025-12-31 | Not started (as planned)
|  |  | Deliverable 3.4.1 d | CSR managers annual meetings | NFF | 2027-12-31 | Not started (as planned)
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on M8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Output 4
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
2 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Scaling up NIMPA success to support the expansion of the national MPA system | O.4.1 | Technical recommendations and roadmap support the designation of two new MPAs based on high conservation priority EBSAs |  | km2 in new MPAs | 1.1.1 | 0 Technical recommendations and roadmap supporting designation of two new MPAs provided to MFMR | Technical recommendations and roadmap supporting designation of two new MPAs are provided to MFMR | Formal notice of MPA designation by MFMR | There is political will within MFMR for MPA expansion, and they will support recommendations | Not started (as planned)
|  |  | O.4.2 | Management frameworks for new MPAs at Namibe and Cape Fria are formally adopted | 2 | New management plans | 1.2.1 | 0 management frameworks currently exist for Namibe and Cape Fria | 2 Management frameworks are formally adopted: 1 for Namibe and 1 for Cape Fria | Copies of management plans, attendance records of management planning meetings and workshops | MFMR provides institutional support for management planning for Namibe and Cape Fria | Not started (as planned)
Activities | [11 empty] | On Track
| Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status |  |  | Notes
Output 4 Activities | A.4 |  | Indicator 4.1 | Technical recommendations and roadmap support the designation of two new MPAs based on high conservation priority EBSAs |  |  | On Track
|  |  | Activity 4.1.1 | Marine Spatial Planning (MSP) in support of MPA expansion | NNF; Blue Marine; SAERI; Grid-Arendal | 2025-06-30 | On Track
|  |  | Deliverable 4.1.1 | Draft MSP plan for north region validated |  | 2025-03-30
|  |  | Activity 4.1.2 | Formally propose two new MPAs at Cape Fria and Namibe | NNF; Blue Marine; SAERI; Grid-Arendal | 2026-03-31
|  |  | Deliverable 4.1.2 | Technical recommendations and a roadmap on the formal establishment of new MPAs |  | 2025-12-31
|  |  | Indicator 4.2 | Management frameworks for two new MPAs at Namibe and Cape Fria are formally adopted |  |  | On Track
|  |  | Activity 4.2.1 | Develop management frameworks for the new MPAs | NNF; Blue Marine; SAERI; Grid-Arendal | 2026-12-31 | On Track
|  |  | Deliverable 4.2.1 | Draft management plans in collaboration with MFMR |  | 2026-03-31
|  |  | Deliverable 4.2.1 | Provide technical recommendations on zonation plans and management regulations |  | 2026-09-30
|  |  | Deliverable 4.2.1 | Provide management recommendations to MFMR including staffing, operational systems, and budgetary requirements, based on NIMPA |  | 2026-09-30
|  |  | Activity 4.2.2 | Undertake baseline assessments of the two sites | NNF | 2026-03-31 | On Track
|  |  | Deliverable 4.2.2 | Baseline for key indicator species (Cape fur seals, elasmobranchs), values and current threats, and socio-economic factors including utilisation of natural resources | NNF | 2025-12-31
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Input value here to get value in analysis tab
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Output 5
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
1 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Effective project governance and implementation | O.5.1 | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring are established by the end of inception phase | 1 | New governance structures, tools and data etc | NA | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring not in place | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring in place by the end of inception phase; (including project management unit (PMU), project steering committee (PSC), ESMP, M&E Plan) | Copies of project governance document/s including steering committee membership, ESMP documents, M&E and governance plans | NA | Not started (as planned)
Activities | [11 empty] | On Track
| Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status | Notes
Output 5 Activities | A.5 |  | Indicator 5.1 | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring are established by the end of inception phase |  |  | On Track
|  |  | Activity 5.1.1 | Establish and support a Project Steering Committee (PSC) | NNF | 2024-03-31 | On Track
|  |  | Deliverable 5.1.1 a | PSC established and operationalised | NNF | 2023-12-31
|  |  | Deliverable 5.1.1 b | Blue Action Fund Atlantic cohort exchange established with regular meeting | NNF | 2028-03-31
|  |  | Deliverable 5.1.1 c | NIMPA+ Project M&E Plan | NNF | 2023-09-30
|  |  | Activity 5.1.2 | Implement the Environmental Social Management Plan (ESMP) to manage and mitigate project risk | NNF | 2024-03-31 | On Track
|  |  | Deliverable 5.1.2 a | Socio-economic baseline survey | NNF | 2023-09-30
|  |  | Deliverable 5.1.2 b | Grievance mechanism established and operationalised | NNF | 2023-09-30
|  |  | Deliverable 5.1.2 c | Finalise/Updated ESS instruments (stakeholder engagement plan, ESMP, Grievance Mechanism, Gender Action Plan) | NNF | 2023-12-31
|  |  | Deliverable 5.1.2 d | Conduct stakeholder engagements | NNF | 2027-09-30
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Direct Beneficiaries
Outputs |  |  | Indicators | [9 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | BMF Impact Indicator | Base value (at project start) | Target value (end of project) | Means of verification | Assumptions | Status | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
7 | [12 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Direct Beneficiaries | O.6 | Individuals directly benefitting from the project | 0.6.1 | People supported to adopt sustainable livelihood options | 1 | New governance structures, tools and data etc | NA | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring not in place | Governance structures, tools and data required for successful NIMPA+ project delivery and impact monitoring in place by the end of inception phase; (including project management unit (PMU), project steering committee (PSC), ESMP, M&E Plan) | Copies of project governance document/s including steering committee membership, ESMP documents, M&E and governance plans | NA | Not started (as planned)
|  |  | 0.6.2 | People supported to adopt diversified livelihood options (incl. aquaculture, agriculture, tourism, etc.) |  |  | NA |  | 100 (m), 55 (f) | Stakeholder engagement plan and membership list. |  | Not started (as planned)
|  |  | 0.6.3 | People benefitting from trainings and knowledge exchange |  |  | 4.1.2 |  |  |  |  | Not started (as planned)
|  |  | 0.6.4 | People benefitting from awareness raising |  |  | 4.1.2 |  |  |  |  | Not started (as planned)
|  |  | 0.6.5 | People receiving salaries and other financial compensation from the project |  |  | 4.1.1 |  |  |  |  | Not started (as planned)
|  |  | 0.6.6 | People receiving non-monetary compensation from the project |  |  | 4.1.2 |  |  |  |  | Not started (as planned)
|  |  | 0.6.7 | People actively benefitting from project investments. |  |  | 4.1.2 |  |  |  |  | Not started (as planned)
Activities | [11 empty] | To schedule
| Activity Code |  | Indicator Code | Description | Partners | Expected completion date | Status | Notes
Output 6 Activities | A.6 |  | Indicator 6.1 | People supported to adopt sustainable livelihood options |  |  | On Track
|  |  | Activity 6.1.1 |  |  |  | On Track
|  |  | Deliverable 6.1.1 a | 155 small-scale fisheries (SSF), benefitting from practical measures which benefit all SSFs, (not counting ones engaged below in forming an organisation)
|  |  | Activity 6.1.2 |  |  |  | On Track
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There isn't technically an output 6, however keeping the codes and formats for consistency.
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all activity/deliverable lines, select from the drop down menu in the cell
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables and activities
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To complete if desired.
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was less clear if these were activities or targets (information from the NIMPA+ Direct Beneficiaries document)
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't edit this cell, it is based off the status of the deliverables

## Unplanned Outputs
Outputs |  |  | Indicators |  |  |  | Tracking/Reporting
Output | Description | Indicator value | Unit | Related BMF sub-indicators (Impact) | Notes | Means of verification | Progress Planned in 2021 |  | Progress achieved in 2021 |  | Progress Planned in 2022 |  | Progress achieved in 2022 |  | Progress Planned in 2023 |  | Progress achieved in 2023 |  | Progress Planned in 2024 |  | Progress achieved in 2024 |  | Progress Planned in 2025 |  | Progress achieved in 2025
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Stakeholders reached through activities | 100 | Number of stakeholders | 4.2.1 |  |  |  |  | 45 | Workshops on MPA and stakeholder engagement – recent visit
U.2
U.3
U.4
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14
U.15
U.16
U.17
U.18
U.19
U.20
U.21
U.22
U.23
U.24
U.25
U.26
U.27
U.28
U.29
U.30
U.31
U.32
U.33
U.34
U.35
U.36
U.37
U.38

## Analysis
Formula Assistance |  |  | Output Tracking | [9 empty] | Impact Indicator Tracking
[13 empty] | Defined in original outputs |  |  | Unplanned |  |  |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Progress Planned in 2023 | Progress achieved in 2023 | Progress Planned in 2024 | Progress achieved in 2024 | Progress Planned in 2025 | Progress achieved in 2025 | Achieved to date | Impact Indicator | Progress achieved in 2023 | Progress achieved in 2024 | Progress achieved in 2025 | Progress achieved in 2021 | Progress achieved in 2022 | Progress achieved in 2023 | Progress achieved in 2024 | Progress achieved in 2025 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total expected | Direct Beneficiaries
Output 1 | 4 | 8 | O.1 | O.1.1 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 4 | 8 |  | O.1.2 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 4 | 8 |  | O.1.3 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4 | 2 | 6 |  | O.1.4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 1 | 5 | O.2 | O.2.1 | 20% | 27.5% | 20% | 0% | 0% | 0% | 27.5% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.2 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | O.2.3 | 100% | 0% | 75% | 0% | 0% | 0% | 0% | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.2.4 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.3 | O.3.1 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | 0% | 0% | 85.71% | 0% | 0% | 0% | 0% | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 5 | [10 empty] | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
[12 empty] | 4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
[12 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 4.2.1 | 275 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 275 | 45 | 320 | 0
[12 empty] | 4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[12 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This table is just for creating the right formulae in the subsequent tables
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This table determines how far through (as a percentage) the targets each output indicator is. If it says '#DIV/0!' - this means no target has been set in the output tab (in column F of the relevant output tab.
Note on P1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This table provides a the total sum reached of each of the BMF indicators. Note that many lines in this logframe do not have an associated BMF indicator so will not feature in this table
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note that unplanned goes back to 2021 as there is a data entry for 2021 in the unplanned outputs tab