## Instructions
This logframe document is to help with the design and tracking of a Blue Marine Foundation project. It uses the structure of a logframe to inform project managers and project teams on the indicators of their project, and ties the outputs from all projects together to be able to inform Blue Marine Foundation's impact at an organisational level. For more information on logframe reporting, project managers are advised to read Blue Marine Foundation's M&E Guide (1), look at the logframe instructions (2) and see the example logframe (3). To see all the Impact Indicators listed in a word doc, please see the Imapact Indicator list (4). | 1 | M&E Guide
| 2 | Logframe Instructions and Examples
| 3 | Example logframe
| 4 | Impact Indicator List

## Key Updates
Month | Activities | Comments/links
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01 | Photos and images of underwater environment from GoPros (used to record activities for various projects – plastics, shark tagging and BRUVS).
Media bank creation using hard drives.
Photos and images of life on board the RRS Discovery – including mini media clips of eDNA and plastic project updates.
Interviews from local community on Ascension’s marine environment using Rode mics and DSLR camera.
Drama club film about fisheries compliance for IMPAC presentation and later distribution via social media
Three interns recruited and arrived on Ascension Nov-Dec 2022.
Trained in turtle emergence and nest monitoring and temperature logger deployment
Commenced daily turtle monitoring from Dec 22
Clearance of invasive weeds on Long Beach, Georgetown, Deadman’s and Pan Am Beaches, Assist with Mexican thorn removal from Long Beach, North East bay and Pan Am Nature Reserves
Assist with maintenance of Green Mountain National Park
Assist with endemic plant restoration work
2023-02-01
2023-03-01
2023-04-01 | Creation and delivery of regular social media posts (3-5 posts per week). Posts vary of pictures and videos of Ascension’s marine life, MPA Youth Committee updates and updates of the marine team’s work (e.g. plastics project video - which was also delivered at the St Helena Whale Shark Festival).
Growth of followers and engagement across all social media platforms.
Growth of MPA Youth Committee, around 18 regular students. Recent sessions include eDNA rock pool session, invasive species awareness week (large turtle mural made of invasive weeds created), zooplankton session, weekend hike to Shelly Beach to see anchialine pools, shark talk from visiting ZSL scientists, Earth Hour Session and an Easter egg-extravaganza session.
Delivery of two school assemblies and launch of turtle naming competition.
Organising of MPA Festival and fishing competition– scheduled for 10th of June.
Weekly rehearsals of the Deep Sea adventure play with drama club to be performed at the MPA Festival.
Additional interview for Ascension Island Voices documentary with hopes to schedule more in soon.
Delivery of school lesson using resources provided by Blue Belt (with more scheduled in the year).
Providing extra support with field work (e.g. shark tagging and crab work).
Turtle emergence and nest counts on three protected beaches
Deployment of 49 temperature loggers in turtle nests on protected beaches to monitor impacts of climate change
Nest excavations on protected beaches to look at hatching success
Rescue of stranded turtles
Deployment of 11 satellite tags and collection of biopsy samples for isotope analysis for project with Blue Belt and University of Exeter looking at migration and foraging areas of Ascension turtles
Assistance with the work of the Conservation Marine Team including plankton sampling, shark tagging and logger retrieval
Assistance with the work of the National Park and endemic plant teams
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01

## Impact and Outcome
Impact | Ascension Island’s MPA as a replicable model for other remote island communities, proving that marine protection can bring greater socio-economic benefits than the sale of offshore fishing licenses
Outcome |  |  | Indicators
| Code | Description | Outcome Indicator Number | Measureable Indicators | Related outputs | Related sub-indicators (Impact) | Related Core Impact Indicators | Means of verification | Important Assumptions
Outcome | OC.0 | The largest no-take MPA in the Atlantic is secured and supported with a major endowment fund that provides permanent income (4-5% annual return) to the Ascension Island community, and global research activities in the MPA are attracted and established using a media campaign. | OC.0.1 | Enable creation of the largest no-take MPA in the Atlantic and the eighth largest in the world, taking the percentage of UK waters protected from 26 to 32 per cent | NA | NA | NA | Formal protection/designation announcement | Government continues to support the designation of a NTZ MPA Local communities and businesses continue to support the NTZ designation Endowment fund generates consistent returns Funds are successfully distributed to commujnity and conservation projects
|  |  | OC.0.2 | Ensure the establishment of an MPA brings lasting benefits to the island community by establishing a £2m conservation endowment fund for Ascension which will deliver a 4-5 per cent annual return (£80,000-£100,000) for community projects. Ensure local buy-in for the endowment fund and thus for the MPA. | 1, 2 | 6.1.1, 4.1.2, 4.2.1, 6.1.5 | 4.1, 4.2, 6.1 | Financial records
|  |  | OC.0.3 | Use Ascension to demonstrate as a case-study that marine protection can bring greater socio-economic benefits to a small island than the sale of licences to offshore (non-local) fishing effort. | 4 | 3.3.2, 1.4.1, 1.2.1 | 1.2, 1.4, 3.3 | Records of monitoring evidence inc. financial records before and after designation
|  |  | OC.0.4 | Using media assets (film, articles, social media), celebrate Ascension's MPA and establish Ascension as a hub of scientific and conservation excellence which will attract marine biologists from all over the world to come and study these exceptionally pristine waters | 5 | 4.2.2, 4.2.1 | 4.2 | Links, reach stats screenshots of media outputs
|  |  | OC.0.5 | Use Ascension as a world-leading example of an MPA attracting a major endowment fund, which delivers an income in perpetuity to an island community. A successful model could have a knock-on effect on other UK overseas territories, such as Tristan da Cunha, and also Commonwealth islands who would rather preserve their natural capital, but need a source of philanthropic income to do so. | 6 | 1.4.1, 4.2.1, 4.2.2 | 1.4, 4.2 | Financial records of income, repeat of model used elsewhere within the commonwealth
|  |  | OC.0.6 | NEW - Secure long-term support from HMG for monitoring and enforcement of Ascension's waters | 3 | 2.4.2 | 2.4 | Written record of support from HMG
| 1 | Establish a £2m conservation trust fund (CTF) for Ascension
| 2 | Increase community understanding and appreciation of the CFT (i.e. generate community support for designation/ 'hosting' an MPA)
| 3 | Secure long-term support from HMG for monitoring and enforcement of Ascension’s waters.
| 4 | Publish best-practice management plan for Ascension’s MPA
| 5 | Produce social media plan/assets to promote implementation of 100 per cent MPA with global reach and engagement
| 6 | Develop a ‘model of protection’ handbook for remote islands that can have application not only to other UK Overseas Territories, but around the world.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please check that these are correct, I have added them in as a best guess
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is new, and has been inserted to ensure that Output 3 is captured in these higher level Outcomes, please check you're happy with this

## Output 1
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 1 | O.1 | Establish a £2m conservation trust fund (CTF) for Ascension | O.1.1 | Independent charity/board of trustees [number of] established | 1 | Number of boards | NA - progress | Official CTF contracts signed and completed showing board of trustees etc. |  | 1 | Proposed for completion in Y1 | 1 | Completed in Y1 | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete
|  |  | O.1.2 | Amount (£) invested into the fund | 2000000 | £ | 6.1.1 | Financial records of investment |  | 2000000 | Proposed for completion in Y1 | 2000000 | Money invested into fund in Y1 | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 1 Activities | A.1 |  | A.1.1 | Find the best way to house the CTF, either by setting up an independent charity and identifying a board of trustees, or by using an existing charity. |  |  | Complete
|  |  | A.1.2 | Use financial and legal advice to identify an investment strategy, invest £2m grant and oversee first board meetings to ensure the successful birth and establishment of the CTF. |  |  | Complete
A.1.3
A.1.4
A.1.5
A.1.6
"1"

## Output 2
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 2 | O.2 | Increase community understanding and appreciation of the CFT (i.e. generate community support for designation/ 'hosting' an MPA) | O.2.1 | Number of community stakeholders engaged with |  | Stakeholders reached | 4.2.1 | Evidence of diverse stakeholder engagement (meeting minutes, correspondence, workshops) | The local community is engaged and willing to support designation | [6 empty] | 800 | Whole community as articles in Islander newspaper and many community events
|  |  | O.2.2 | Number of beneficiaries benefitting from community projects through fund disbursement |  | Number of beneficiaries | 4.1.2 | Contracts/project plans outlining how support from the fund will be used for conservation |  |  |  | 780 | 800 community members will benefit from community projects (700 adults, 80 children) |  |  | 160 | Ladybirds Climbing frame and toys /materials 7 degrees south Music equipment Ascension Fishers Scales Ascension Fishers Sun Sail Path bashing Tools Community Centre Toilets and sewer upgrade Ascension Boot Camp Gym Equipment Library Resource Centre Equipment Expected 150-200 people to benefit following arrival of all equipment (took conservative estimate of 150 10: number of people in conservation team provided with ~£5k filming equipment and training awaiting Jude response
|  |  | O.2.3 | Amount of funds (£) provided for the community while endowment fund is maturing |  | £ | 6.1.5 | Financial documents demonstrating funds provided for community | [8 empty] | 20000 for community projects 16500 for turtle interns x 4
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 2 Activities | A.2 |  | A.2.1 | Explain process of establishing CTF and the benefits that it will deliver to the Island Administrator and Island Council. |  |  | Complete | meeting held March 2023
|  |  | A.2.2 | Ask island community to propose members of Spending Committee to select projects for disbursement, via conference calls with island community. |  |  | Complete | change of method - projects to be proposed by community to AIG and AIG to provide details of proposals to AIMPACT board as per an agreed MoU
|  |  | A.2.3 | Secure buy-in of island community by providing community funds as bridging grant while the endowment fund is maturing in 2021. |  |  | Complete | £80k given for sports field (not yet spent); £20k for communtiy projects given
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please input anticipated figures for across the lifetime of the project (Y1-Y3)

## Output 3
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
3 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 3 | O.3 | Secure long-term support from HMG for monitoring and enforcement of Ascension’s waters. | O.3.1 | Number of presentations/meetings/reports/discussions with relevant political stakeholders |  | Meetings/reports/discussions | NA - progress | Copies of presentations, meeting minutes | HMG is open to providing support Evidence to date shows positive change due to designation | [6 empty] | 4 | Meetings with Bluebelt coordinator at FCDO
|  |  | O.3.2 | Number of parliamentary briefings |  | Briefings | 2.4.2 | Copy of briefings | [7 empty] | 0
|  |  | O.3.3 | Number of responses to government consultations |  | Consultation responses | 2.4.2 | Copy of consultation responses | [7 empty] | 0
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 3 Activities | A.3 |  | A.3.1 | Continue to engage with UK Government, via meetings and correspondence, to make the economic, scientific and political case for a long-term spending commitment to the Ascension MPA. |  |  | In Progress | Met with FCDO in Feb 2023; continue to advocate for Bluebelt funding through GBO
|  |  | A.3.2 | This will involve presentations to ministers and officials, a parliamentary briefing event (likely online) |  |  | In Progress | Planning underway with GBO for event in 2023
|  |  | A.3.3 | Responding to government consultations. |  |  | In Progress | Provided feedback to UKOT biodiversity strategy
A.3.4
A.3.5
A.3.6
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you estimate some numbers for across the project lifetime (just an approx is fine)

## Output 4
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 4 | O.4 | Publish best-practice management plan for Ascension’s MPA | O.4.1 | Number of changes/improvements in strategies for inshore fishing |  | Number of fisheries with improved management measures | 3.3.2 | Written evidence of change to fisheries | Achieve findings to be released as part of best practice management plan Sufficient comparable management plans exist | [6 empty] | 0 | Still in draft
|  |  | O.4.2 | Number of changes/improvements in strategies for monitoring and enforcement |  | Number of fisheries with improved management measures | 3.3.2 | Written evidence of change to fisheries | [7 empty] | 0 | Continual review of success of enforcement strategies by OceanMind under Bluebelt programme
|  |  | O.4.3 | Number of analyses produced on comparable management plans, with reports/datasets provided on external scientific advice | 1 | Reports/new pieces of evidence | 1.4.1 | Written evidence of reports/datasets compiled | [7 empty] | 1 | Annual review of Marine Management Plan outputs by AIG completed
|  |  | O.4.4 | Number of management plans produced | 1 | Number of marine management plans | 1.2.1 | Copy of management plan |  | 1 | Planned for Y1 | 1 | Completed in Y1 | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete | 0 | Indicator complete
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 4 Activities | A.4 |  | A.4.1 | Work with Head of Conservation on Ascension to ensure Ascension’s MPA has a best-practice management plan and strategies to deal with inshore fishing interests as well as offshore monitoring and enforcement. |  |  | In Progress | Marine management plan in place, Inshore fishing regs with legal draftsperson for drafting
|  |  | A.4.2 | Provide comparative analysis with comparable management plans and introducing independent external scientific advice. |  |  | Complete | Feedback provided on MMP
A.4.3
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you provide an estimate for these across the lifetime of the project - also please see the comment further along this row to check the wording is correctly capturing what is being done
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jude - can I check whether a new management measure was introduced in Y2? If not we might need to change our wording, perhaps worth a chat to make sure I'm clear on what this indicator is
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this number correct for across the lifespan of the project?

## Output 5
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
2 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 5 | O.5 | Produce social media plan/assets to promote implementation of 100 per cent MPA with global reach and engagement | O.5.1 | Number of media assets produced (broken down by film, social media content and articles) |  | Outreach tools | 4.2.2 | Screenshots, copies of and links to media assets | Social media achieves significant reach and is received positively | [6 empty] | 10 | Number of AIG MPA social media articles (10 articles) Not included in final number: 57 tweets
|  |  | O.5.2 | Stakeholders reached through social media by region (reach, engagement) |  | Stakeholders reached | 4.2.1 | Social media stats/video views/website visits | [7 empty] | 1379 | Number of AIG MPA social media followers (Twitter: 346, Facebook: 637, Insta: 396)
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 5 Activities | A.5 |  | A.5.1 | Media assets produced (broken down by film, social media content and articles)
|  |  | A.5.2 | Publicise 100 per cent MPA at time of its announcement and in the years following |  |  | In Progress | Large publicity at time of announcement, contiued MPA awareness including at international events
|  |  | A.5.3 | Monitor social media reach/engagement by region |  |  | In Progress
A.5.4
A.5.5
A.5.6
A.5.7
A.5.8
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you insert a number for the number of produced tools over the lifetime of the project?
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please could you insert a number for the reach over the lifetime of the project? This will be very approximate as so hard to gauge!

## Output 6
Outputs |  |  | Indicators | [6 empty] | Tracking/Reporting
No. of Indicators | Output code | Description | Indicator code | Measureable Indicators | Indicator value | Unit | Impact Indicator | Means of verification | Assumptions | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end) |  | Progress achieved 2022 (for Appin to do)
4 | [9 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
Output 6 | O.6 | Develop a ‘model of protection’ handbook for remote islands that can have application not only to other UK Overseas Territories, but around the world. | O.6.1 | Data collected the reflects learnings from establishing an MPA around Ascension [reports, data, scientific/socioeconomic evidence, anecdotal feedback |  | Pieces of evidence | 1.4.1 | Databases produced and scientific advice has guided the review of available information | [7 empty] | 4 | Published papers: Goodwin, C., Brown, J., Downey, R., Trieu, N., Brewin, P.E., and Brickle, P. (2021) Demosponges from Ascension Island with a description of nine new species. Journal of the Marine Biological Association of the United Kingdom 1–24. https://doi.org/10.1017/S0025315421000709 Weber, S.B., Richardson, A.J, Brown, J., Bolton, M., Clark, B.L, Godley, B.J., Leat, E., Oppel, S., Shearer, L., Soetaert, K.E.R., Weber, N., Annette C. Broderick, A,C. (2021). Direct evidence of a prey depletion halo surrounding a pelagic predator colony. Proceedings of the National Academy of Sciences Jul 2021, 118 (28) e2101325118; DOI: 10.1073/pnas.2101325118. Thompson, C.D.H., Meeuwig, J.J., Brown, J., Friedlander, A.M., Miller, P.I., Weber, S.B (2021) Spatial variation in pelagic wildlife assemblages in the Ascension Island Marine Protected Area: implications for monitoring and management. Frontiers in Marine Science 8:634599. doi: 10.3389/fmars.2021.634599 | 1 | Not published yet: Age, growth and maturation of yellowfin tuna at Ascension Island, central tropical Atlantic scientific paper submitted to journal for publication
|  |  | O.6.2 | Website (created by Diane Baum) is launched and is publicly accessible | 1 | Website (outreach tool) | 4.2.2 | Link to website | [7 empty] | 1 | Website launched: Home - Ascension Island (ascensionmpa.ac) | 0 | Indicator complete | 0 | Indicator complete
|  |  | O.6.3 | MPA manual condensing learnings is created and hosted online | 1 | Manual | 1.4.1 | MPA manual can be easily accessed/downloaded |  | 0 | Due in late 2022 | 0 | Due in late 2022 | 0 | Due in late 2022 | 0 | Due in late 2022 | 1 | MPA manual created but due for launch in October 2022 and will then be made publicly available
|  |  | O.6.4 | Success of distribution |  | reach, engagement, number of downloads | 4.2.1 | Significant reach/engagement with the website and management plan achieved |  | 0 | Not able to be calculated until release of MPA manual in late 2022 | 0 | Not able to be calculated until release of MPA manual in late 2022 | 0 | Not able to be calculated until release of MPA manual in late 2022 | 0 | Not able to be calculated until release of MPA manual in late 2022 |  | TBD after release of above indicator in Oct 2022
Activities
| Activity Code |  | Indicator Code | Description |  |  | Status | Notes
Output 6 Activities | A.6 |  | A.6.1 | Work with Diane Baum to use the learnings from establishing an MPA around Ascension to produce a manual which will be available via a dedicated website for Ascension’s MPA. |  |  | Complete | MPA blueprint created and on Blue website including case study for Ascension
|  |  | A.6.2 | This will not only serve as a guide to other territories who want to set up an MPA, but will celebrate Ascension’s achievements in hosting one of the best managed MPAs in the world. |  |  | Complete | Ascension Marine life guide book produced
|  |  | A.6.3 | Through regular contact with Diane Baum, BLUE will provide advice on website, content of guide and distribution. |  |  | Complete | Blueprint complete and on Blue Marine website
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please insert a number here for anticipated number of reports etc across lifetime of project - can be an estimate
Note on T4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 29/11/23 still unpublished, has lengthy peer review comments following submission
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is potentially now the MPA blueprint so is covered elsewhere
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please insert a number here for anticipated reach

## Unplanned Outputs
Outputs | [6 empty] | Tracking/Reporting
Output | Description | Indicator value | Unit | Impact Indicator | Notes | Means of verification | Progress Planned in Y1 (July 2020–June 2021) |  | Progress achieved in Y1 (July 2020–June 2021) |  | Progress planned in Y2 (July 2021–June 2022) |  | Progress achieved in Y2 (July 2021–June 2022) |  | Progress planned in Y3 (July 2022–Project end) |  | Progress achieved in Y3 (July 2022–Project end)
[7 empty] | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description | Value | Description
U.1 | Turtle hatching blog - views | 2000 | Stakeholders reached | 4.2.1 | Views of turtle hatchling blog | Stats from website | [6 empty] | 2000 | Blog released in Jan 2022
U.2 | Jude - book published, reach | 400 | Stakeholders reached | 4.2.1 | 400: assuming that half of total number of books distributed (total of 800) have reached readers | Distribution records | [6 empty] | 400 | Book publication in September 2021. 800 distributed
U.3 | Jude - book published, outreach tool generated | 1 | Number of outreach tools | 4.2.2 | Published Sept 2021 | Copy of book | [6 empty] | 1 | Book publication in Sept 2021
U.4 | Y1 Barclays Impact - MPA designation | 445000 | km2 | 1.1.2 |  |  |  |  | 445000 | (Aug 2020, highly protected) designated,
U.5
U.6
U.7
U.8
U.9
U.10
U.11
U.12
U.13
U.14

## Analysis
Formula Assistance |  |  | Output Tracking | [11 empty] | Impact Indicator Tracking
[15 empty] | Defined in original outputs |  |  | Unplanned |  |  | Totals
List of Sheets to use | Objectives per output | Cell range to call from | Output | Indicator | Planned for Y1 | Achieved in Y1 | Planned for Y2 | Achieved in Y2 | Achieved in Y3 | Achieved at end of Y1+Y2 | Planned for Y2 | Achieved in Y3 | Achieved at end of Y1+Y2+Y3 | Impact Indicator | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Achieved in Y1 | Achieved in Y2 | Achieved in Y3 | Total achieved | Total unplanned | Total achieved (planned and unplanned) | Total Expected | 2022 | 2022 planned | 2022 unplanned
Output 1 | 2 | 6 | O.1 | O.1.1 | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2 | 3 | 7 |  | O.1.2 | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3 | 3 | 7 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.1.2 | 0 | 0 | 0 | 445000 | 0 | 0 | 0 | 445000 | 445000 | 0 | 0 | 0 | 0
Output 4 | 4 | 8 |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | 1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 5 | 2 | 6 | O.2 | O.2.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 6 | 4 | 8 |  | O.2.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0
|  |  |  | O.2.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.3 | O.3.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.3.3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.4 | O.4.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #REF! | #DIV/0! | #DIV/0! | 1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.4.3 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O.5 | O.5.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.1 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 2 | 0 | 0 | 0
|  |  |  | O.5.2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outputs: | 6 |  | O.6 | O.6.1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.2 | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O.6.3 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 2.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | 3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.1.2 | 780 | 160 | 0 | 0 | 0 | 0 | 940 | 0 | 940 | 0 | 0 | 0 | 0
[14 empty] | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.2.1 | 0 | 2179 | 0 | 0 | 2400 | 0 | 2179 | 2400 | 4579 | 0 | 0 | 0 | 0
[14 empty] | 4.2.2 | 0 | 11 | 0 | 0 | 1 | 0 | 11 | 1 | 12 | 1 | 0 | 0 | 0
[14 empty] | 4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.1 | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | 0 | 0
[14 empty] | 6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0